## Phase 1 Rescue Phase
PHASE 1: RESCUE
NO | FOCUS AREA | KEY ASSESSMENT FINDING (BASELINE) | KEY ACTIVITIES | RESOURCES REQUIRED | RESOURCES MOBILISED | RESPONSIBLE | START DATE | END DATE | KEY PERFORMANCE INDICATOR | PORTFOLIO OF EVIDENCE | BUDGET PARAMETER/ REVENUE TARGET/ SPENDING LIMIT | MUNICIPAL PROGRESS REPORT
[12 empty] | STEPS TAKEN | PROGRESS MADE | FINANCIAL IMPACT | OTHER NOTEWORTHY DEVELOPMENTS
PILLAR ONE: GOVERNANCE
1 | OVERSIGHT STRUCTURES OF COUNCIL | Inadequate implementation of Council resolutions. No tracking of the Implementation of Council Structures Resolutions. Culture of ill-discipline and lack of accountability at political and administrative level. Ineffective reporting mechanism to enhance council oversight. Non-compliance with Council Calendar. Portfolio committees not seating since the inception of the new council. Ward Committees not effective and no Ward Based Planning. Councillors and staff owing for services rendered. Inadequate oversight over Executive and Administration. System of Delegations not reviewed. | Develop a tool for tracking implementation of Committee and Council Resolutions | In-house | In-House | Manager: office of the Speaker | 02/01/2023 | 2023-03-31 | Approved tool | Council resolution
|  |  | Track the implementation of Resolutions/recommendations | In-house | In-house | Manager: office of the Speaker | 02/01/2023 | Quarterly | Resolution Register | Quarterly report and signed Council resolution
|  |  | Development of the policy frameworks to give effect to Code of Conduct for Councillors and officials. | In-house | In-house | Manager office of the Speaker | 02/01/2023 | 01/04/2023 | Policies in place | Council approved report and signed resolution
|  |  | Develop a Report Flow Process for Council to ensure compliance and enforcement of delegations | In-house | In-house | General Manager: Corporate Services | 02/01/2023 | 2023-03-31 | Approve Report Process Flow | Council report and signed Council resolution
|  |  | Ensure adherence to Council and committee Calendar of meetings | In-house | In-house | Manager: Office of the Speaker | 02/01/2023 | Monthly/Quarterly | Council functional and meeting at least quarterly as required. | Signed Council Minutes
|  |  | Develop and approval of institutional annual calendar of Council and committee meetings | In-house | In-house | Manager: Office of the Speaker | 02/01/2023 | 2023-03-31 | Approved institutional calendar | Council report and signed resolution
|  |  | Timeous approval of statutory and oversight reports | In-house | In-house | Speaker | 02/01/2023 | MFMA calendar dates | MFMA reporting compliance | Approved and submission of statutory and oversight reports
|  |  | Development and approval of operational Plans for ward committees | In-house | In-house | Manager: office of the Speaker | 02/01/2023 | 2023-03-31 | Approved Operational Plans | Council report and signed resolution
|  |  | Facilitate meetings of ward committees | In-house | In-house | Manager: Office of the Speaker | 02/01/2023 | Monthly/Quarterly | Functional ward committees | Ward committee meetings minutes
|  |  | Investigate arrears owed by councillors and staff | In-house | In-house | CFO | 02/01/2023 | 2023-03-31 | Investigation report | Council report and resolution
|  |  | Enter into payment arrangements with councillors and staff owing the municipality for services rendered | In-house | In-house | CFO | 02/01/2023 | 2023-03-31 | Collection of arrear debt | Signed acknowledgement of debt and payment arrangements
|  |  | Monthly collection of arrears and payment of cutrrent accounts | In-house | In-house | CFO | 02/01/2023 | Monthly | Collection of arrear debt and revenue | Financial report and Council resolution
|  |  | Train Councillors on oversight and delegations | COGTA>SALGA | In-house | General manager: Corporate Services | 02/01/2023 | 2023-03-31 | Report on training | Attendance registers and training programme
|  |  | Review system of delegations for approval by Council | In-house | In-house | General manager: Corporate Services | 02/01/2023 | 2023-03-31 | Approved process plan and system of delegations | Approved system of delegations and Council resolution
|  |  | Sub-delegate powers and functions by MM | In-house | In-house | Municipal Manager | 02/01/2023 | Quarterly | Sub-delegations effected | Acknowledgement of sub-delegations and updated delegations register
|  |  | Update and Maintain delegations register | In-house | In-house | General manager: Corporate Services | 02/01/2023 | Monthly | Updated delegations | Delegations register
|  |  | Appointment of the members of the Disciplinary Board | In-house | In-house | Council/COO | 02/01/2023 | 2023-03-31 | Fully functional DC | Signed and Accepted appointment letters
2 | PUBLIC PARTICIPATION | There is no regular and structured engagement with Stakeholders. Negative perception by stakeholders resulting into non-payment of services and lack of confidence in EMLM. Current Policies are fragmented, content duplicated and framework not consistent, neither there is evidence that they are approved by Council. | Develop, approve and implement stakeholder engagement strategy and plan (Pending Council approval) | In-house | In-house | General Manager: Corporate Services | 02/01/2023 | 31/03/2023 Monthly | Reports on engagements & Attendance registers | Council report and signed resolution
|  |  | Facilitate regular engagement with various stakeholders | In-house | In-house | Municipal Manager | 02/01/2023 | Monthly | Reports on engagements & Attendance registers | Minutes of stakeholder engagements
|  |  | Develop and approve communication plan that includes updates on implentation progress of FRP | In-house | In-house | General Manager: Corporate Services | 02/01/2023 | 2023-03-31 | Approved plan and reports | Approved Communication plan and signed resolution
|  |  | Review and update public participation policy and strategies | In-house | In-house | General Manager: Corporate Services | 02/01/2023 | 2023-03-31 | Approved policies | Approved policies and signed Council resolution
3 | AUDITOR-GENERAL AUDIT ACTION PLAN | Negative Audit Outcomes | Update the AG Audit action plan plan | In-house | In-house | Chief Audit Executive | 02/01/2023 | 2023-03-31 | Updated audit action plan | Council report and signed Council resolution
|  |  | Implement and report on AG audit action plan | In-house | In-house | CFO | 02/01/2023 | Monthly/Quarterly | Progress reports | Council and Audit committee reports and signed resolutions
|  |  | Develop and implement a risk based audit plan | In-house | In-house | Chief Audit Executive | 02/01/2023 | 2023-03-31 | Approved risk based audit plan and Quarterly Risk Reports | Approved risk based audit plan, Audit and Risk committee and Council signed resolutions
|  |  | Convene weekly Audit Steering Committee meetings | In-house | In-house | Municipal Manager | 02/01/2023 | Weekly | Dashboard reports | Signed minutes of weekly steering committee meetings
4 | UNAUTHORISED, IRREGULAR, FRUITLESS AND WASTEFUL EXPENDITURE | Escalating UIF&W expenditure. Late payment of creditors. Section 32 MFMA investigations not done. Non-compliance with supply chain policy and processes. Allegations of financial misconduct not investigated. Disclosed UIF&W expenditure not true reflection. No internal controls for recognition and record of expenditure. No consequence management. Overspending on budget | Investigation on unauthorised, fruitless, wasteful and irregular expenditure in accordance with sec 32 of the MFMA and investigation of financial misconduct | In-house | In-house | Council/MPAC | 02/01/2023 | Quarterly | Investigations reports | Council and MPAC reports with signed resolutions
|  |  | Implement Consequence management for UIF&W expenditure | In-house | In-house | Executive Mayor | 02/01/2023 | Monthly | Reduction in UIF&W expenditure | Consequence management register and Council progress reports and signed resolutions
|  |  | Identify and report on irregular, unauthorised, fruitless and wasteful expenditure in accordance with sec 32 of the MFMA and MFMA circular 68 | In-house | In-house | CFO | 02/01/2023 | Quarterly | Compliane with reporting requirements | Quarterly reports on UIF&W expenditure and Mayoral Committee resolutions
|  |  | Implement UIFW expenditure policy | In-house | NT-MFMA Unit/MPAC unit | CFO | 02/01/2023 | Quarterly | Implementation report and legislative compliance | Quarterly Mayorial reports on UIFW
5 | RISK MANAGEMENT | Ineffective risk management. Culture of non-compliance. Destruction of records through arson | Develop a consequence management framework | In-house | In-house | Chief Risk Officer | 02/01/2023 | 2023-03-31 | Reports on consequence management cases | Council report and signed resolution
|  |  | Identify transgressions and ensure consequence management implementation | In-house | In-house | Chief Risk Officer | 02/01/2023 | 2023-03-31 | Consequence management register | Consequence management register
|  |  | Conduct campaigns and workshops on anti-fraud and corruption policy | In-house | In-house | Chief Risk Officer | 02/01/2023 | 2023-03-31 | Report on campaigns and workshops | Attendance registers and campaign and workshop materials
|  |  | Monitor the implementation of the Enterprise Wide Risk Management Plan | In-house | In-house | Chief Risk Officer | 02/01/2023 | 2023-03-31 | Quarterly Risk Reports | Council report and signed resolutions
|  |  | Monitor and report to council on cases opened for criminal investigations | In-house | In-house | Chief Risk Officer | 02/01/2023 | Quarterly | Improved accountability | Quarterly reports and signed Council resolutions
|  |  | Finalise, implement and report on recommendations of the investigation into irregularities and misappropriation of assets | External service provider | External service provider | Chief Audit Executive | 31/01/2023 | Monthly/Quarterly | Investigation reports | Council report and signed resolution
6 | INFORMATION AND COMMUNICATION TECHNOLOGY | Structure of ICT, Strategy in place but not institutionalised. ICT steering committee not established. Inadequate disaster recovery plan | Capacitate the unit | In-house | SALGA | ICT Manager | 01/01/2023 | 2023-03-31 | capacitated ICT unit | Approved capacity plan
|  |  | Review, develop and implement ICT general controls | In-house | In-house | ICT Manager | 01/01/2023 | 31/03/2023 Monthly | No findings by Auditor-General | Auditor-General report System generated report to track controls
|  |  | Set up an ICT Steering Committee | In-house | In-house | ICT Manager | 01/01/2023 | 2023-03-31 | Steering committee established | Minutes of steering committee meetings
|  |  | Update the municipality website | In-house | In-house | ICT Manager | 01/01/2023 | Monthly | Updated website | Updated website
|  |  | Secure data storage, back up and recovery solution | In-house | SALGA | ICT Manager | 01/01/2023 | 2023-03-31 | Data secured and integrity guaranteed | Internal audit report and AG audit report
|  |  | Report on Back office Turnaround times in resolving help desk queries | In-house | In-house | ICT Manager | 01/01/2023 | Monthly | Satisfied customers Increased revenue. 95 % of work orders completed | Monthly work order reports
7 | LITIGATION AND CONTINGENT LIABILITY | Inadequate Legal Compliance register Contingent liability at R26 714 044.00 Low Risk financial exposure Material non-compliance with legislation | Develop a regulatory compliance register | In-house | In-house | General Manager: Legal services | 01/01/2023 | 2023-03-31 | MFMA compliance register | Approved Regulatory Compliance Register
|  |  | Ensure monthly monitoring and reporting of the MFMA compliance | In-house | In-house | General manager: Legal Services | 01/01/2023 | Monthly/Quarterly | Monthly/Quarterly Compliance reports | Compliance reports
|  |  | Conduct diagnostic analysis on root causes of litigation and claims against the bmunicipality | In-house | In-house | General manager: Legal Services | 01/01/2023 | 2023-03-31 | Mitigation of financial exposure | Council report and signed resolution
8 | POWERS AND FUNCTIONS | Municipality mandated to provide library services and licensing services (Underfunded mandate - Province to take over completely) | Conduct an in-depth analysis of cost implications | In-house | In-house | CFO | 01/01/2023 | 2023-03-31 | Cost analysis report | Cost analysis report
|  |  | Re-negotiate mandate agreements | In-house | In-house | CFO/HEAD:LEGAL SERVICES | 01/01/2023 | 2023-03-31 | All inclusive fully funded mandate agreement | Reviewed and signed mandate agreements alternatively termination notices
9 | IMMOVABLE PROPERTY MANAGEMENT | Inadequate institutional arrangements. Loss of revenue. Ineffective collection of revenue on leased properties. | Audit of Council owned immovable property portfolio | In-house | In-house | Chief Audit Executive | 01/01/2023 | 2023-03-31 | Accountability enhanced and increse in revenue | Audit report and Council and Audit committee resolution
|  |  | Review of all lease agreements - | In-house | In-house | CFO/General Manager: legal services | 01/01/2023 | 2023-03-31 | Market related rentals | Reviewed and signed lease agreements
|  |  | Collection of market related rentals from tenants | In-house | In-house | CFO | 01/01/2023 | Monthly | 95% collection of revenue | Monthly Tenant management and financial report
|  |  | Reconcile alienation transactions with Deeds office records for the past five years | In-house | In-house | General Manager: legal services | 01/01/2023 | 2023-03-31 | Deeds search completed for past five years | Council approved Deeds search and reconciliation report and signed resolution
|  |  | Identify immovable properties not required for basic municipal services | In-house | In-house | General manager: Corporate services | 01/01/2023 | 2023-03-31 | Process plan for inviting private sector developments | Council approved report and signed resolution
10 | CONTRACT MANAGEMENT | Inadequate contract management. Payments for services not done within thirty days, irregularly awarded contracts. Outdated Contract register. Irregularly awarded contracts | Audit and review all contracts | In-house | In-house | Chief Audit Executive | 01/01/2023 | Quarterly | All contracts audited | Quarterly Audit report and Audit committee signed resolutions
|  |  | Identify goods and services required on an ongoing basis and appoint service providers on three year contracts | In-house | In-house | CFO | 01/01/2023 | 2023-03-31 | Reduction in operational costs, Reduction in irregular deviations | List of all goods and services, process plan and appointment letters.
|  |  | Submission of monthly performance monitoring reports on contracts | In-house | In-house | CFO | 01/01/2023 | Monthly | value for money, compliance with legislation | Monthly performance monitoring reports
|  |  | Negotiate and sign affordable payment arrangements with creditors | In-house | In-house | CFO | 01/01/2023 | 2023-03-31 | Honouring of financial commitments and arrear debt payment | New affordable agreements signed off by all parties
PILLAR TWO: INSTITUTIONAL
1 | Employee Costs | High Employee Costs as a results of Gross over-grading of jobs in TASK. | A report on the findings on incorrect Salary grading and overpayment must be tabled in Council. | In-house | In-house | General manager: Corporate services | 01/01/2023 | 2023-06-30 | Achieved completeness of employee costs. Attained buy-in & support. Report approved for implementation. | Copy of the report on the Salary findings Council resolution Copies of the court applications | In line with the approved budget and the funding plan.
To set aside the incorrect salary grading through a Court application.
To set aside the 2023/24 salary increment through a Court application.
Employees will be placed on the salary notch on the new pay scale for the applicable TASK grade which is the closest higher salary notch to their existing salary notch.
Employees whose current salary notch is lower than the minimum of the applicable TASK grade scale will be placed on the minimum of the applicable new TASK salary scale.
Employees whose jobs are correctly graded and whose existing basic salary is not higher than 20% of the maximum of the corrected TASK grade maximum will retain their existing basic salary on a personal-to-holder basis.
2 | Organisational Structure | The Organisational Structure was reviewed and approved a year after the amalgamation but has not been implemented. The structure is not based on a fit for purpose operating model and is therefore incorrectly layered and is top heavy with management layers (Directors, Senior Managers and Managers). Current job descriptions are irrelevant. There is no Placement Policy. | Review the Organisational Structure in line with the Municipal Staff Regulations and the strategic objectives of the newly elected Council. | In-house | In-house | General manager: Corporate services | 01/01/2023 | 2023-06-30 | Functions properly aligned to strategic objectives and legal mandate. Achieved affordability. All jobs in new structure graded in TASK, correlated with the job evaluation results. Employees placed correctly in accordance with their job descriptions. | Approved Organisational Structure Council resolution Agenda, Minutes & attendance register of the LLF meetings Copy of the approved placement policy Council resolution Placement letters Job Evaluation report | In line with the approved budget and the funding plan.
Consultation with the LLF.
Submit the draft organisational structure to Council for approval and implementation.
Develop and review all job descriptions of the employees.
Submit the reviewed job descriptions to the Provincial job evaluation committee for evaluation of the jobs.
Develop and seek council approval of the placement policy to guide placement process in the de novo orgainisational structure.
3 | Filling of the Vacant S56 positions and other related critical positions. | The following S56/57 positions are vacant and advertised;MM,Community Services,Corporate Services,Human Settlement and Infrastructure Planning & Economic Development. | The municipality should adhere to the timelines as provided for in the Municipal regulations on appointment and conditions of senior managers to fast track the recruitment process. All non-critical vacancies must not be filled until the implementation of the approved organisational structure. Given the liquidity position of the Municipality, the payroll budget must be strictly controlled but plan for the acquisition of skills in line with cash flow improvements. | In-house | In-house | General manager: Corporate services | 01/01/2023 | 2023-06-30 | Filled Vacant S56/7 critical postions | Copies of adverts for the critical positions.Copies of the Shortlisted candidates Copies of the Assessment reports of recommended candidates Copies of appointment & acceptance letters | In line with the approved budget and the funding plan.
4 | Staff Verification | Staff verification (head counts) are not conducted. | Conduct staff verification against the payroll. Implement constant auditing of the payroll. | In-house | In-house | General manager: Corporate services | 01/01/2023 | 2023-01-31 | Completeness of employee related costs. | Staff verification report Copy of the Payroll | In line with the approved budget and the funding plan.
5 | Overtime | Current budget does not make provision for compensation of overtime. | Make provision for overtime during the budget adjustment process, however this must be mitigated to the point of absolute necessary and limited to the value to be gained. Introduce measures and procedures to approve, monitor overtime work and compensations – use Divisional Agreement and BCEA to guide internal processes. Introduce and conclude an Essential Services Agreement with Organised Labour. Conduct an analysis on the overtime expenditure for the period ending 2020/2021 and 2021/2022 to determine trend and areas of excessive overtime and the cause, recommend and implement measure to reduce the expenditure. | In-house | In-house | General manager: Corporate services | 2023-02-01 | 2023-06-30 | Approved Overtime Policy Compliance to BCEA & Divisional requirements | Attendance register, agenda & Minutes of the LLF consultative meeting. Council resolution Copy of the approved overtime policy | In line with the approved budget and the funding plan.
PILLAR THREE: FINANCIAL MANAGEMENT
1 | REVENUE & DEBTORS MANAGEMENT - ELECTRICITY, REFUSE & RATES AND TAXES | Delay in the finalisation of the supplementary valuation objections leading to loss of revenue. | Valuation tribunal to finalise valuation | o EMLM BTO Revenue Manager | In-house | o CFO | 2023-01-01 | 2023-03-31 | REVENUE & DEBTORS - Electricity, Refuse & Rates and Taxes SV2 completed | Valuation Roll data clean report | Efficiency Gains
|  | Incomplete reconciliation between billing system & valuation roll and approved tariffs. | Valuation roll to be update on billing system and correct the usage tariffs. | o EMLM BTO Revenue Manager | In-house | o CFO | 2023-01-01 | 2023-03-31 | o A sustainable financially sound municipality delivering services to its residents in a cost reflective manner | Valuation Reconciliation report | Efficiency Gains
|  | Reconciliation of the financial system with the land use management system. | Commence valuation roll process now to meet the next full valuation process | o EMLM BTO Revenue Manager | In-house | o CFO | 2023-01-31 | Monthly | o A robust billing system for services provided | Reconciliation report | Efficiency Gains and improve Rates & Taxes Revenue
|  | Outdated financial by-laws. | Review and enforce all financial by-laws | EMLM BTO Revenue Manager | EMLM BTO Revenue Manager | EMLM BTO Revenue Manager | 2023-01-31 | Monthly | EMLM BTO Revenue Manager | Application of by-law reports and Council Approval Resolution | Efficiency Gains
|  | Revenue not recorded in the correct accounting period | Meter reading should be done monthly and variances , estimates and malfunctining meters attended to promptly | EMLM BTO Revenue Manager | EMLM BTO Revenue Manager | EMLM BTO Revenue Manager | 2023-01-31 | Monthly | EMLM BTO Revenue Manager
|  | Inadequate & incomplete reconciliation between Electricity Purchased and Billed. | Reconcile the check meter units to billings and Eskom purchases. | EMLM BTO Revenue Manager | In-house | o CFO | 2023-01-01 | monthly | o Units Difference reduced over time | Reconciliation Report | Efficiency Gains
2 | CUSTOMER CARE | Inadequate Centralised Customer Care Call Centre. | Review of customer care technology. | BTO Revenue & IT Manager | In-house | o CFO | 2023-01-01 | 2023-03-31 | o CRM Implemented | Call Centre operationalised | Efficiency Gains
|  | Inadequate customer turnaround times in addressing queries | Service delivery standards with turn around times. | BTO Revenue & IT Manager | In-house | o CFO | 2023-01-01 | 2023-03-31 | o CRM Implemented | Communication issued from EMLM | Customer satisfaction and efficiency gains
3 | DEBTORS CREDIT CONTROL AND DEBT MANAGEMENT | Lack of preparation and distribution of month statements | Monthly accounts to be distributed using various means available e.g. email etc | BTO Revenue & IT Manager | In-house | o CFO | 2023-01-01 | 2023-03-31 | o Record of Statement Deliveries | Statistical report of distribution of customer accounts. | Revenue Enhancement & Cash Collection
|  | Lack of continuous campaigns to advocate payment for services. | Communication campaign programme | BTO Revenue & IT Manager | In-house | o MM & CFO | 2023-01-01 | On-Going | o Community Town Halls, Advertising, Ward Meeting | Council Approved programme & Monthly implementation reports. | Efficiency Gains
|  | Inadequate enforcement of the credit control policy & by-law for disconnections. | Revenue management to ensure technical services effects disconnections within 48 hours. | BTO Revenue & IT Manager | In-house | o CFO | 2023-01-01 | Monthly | o Improved Reporting - Disconnections reports | Disconnection reports and reconnection fees. | Revenue enhancement
|  | Inadequate & ineffective debt collection. | Implement aggressive debt collection mechanisms by taking legal action. | BTO Revenue & IT Manager | In-house | o CFO | 2023-12-01 | Monthly | o Improved Collection Rates | Improvement in collections after customer outreach | Revenue Collection Enhanced
|  | Inadequate process for the write off of old debt and excessive impairments. | Table of write offs to Council for approval. | BTO Revenue & IT Manager | In-house | o CFO | 01/01/2023 | Quarterly | o Account with small balances cleared | Council approved reports and signed resolutions. | Efficiency Gains
4 | INDIGENT MANAGEMENT | Poor Identification of indigents and register updated | Report to council on mobilisation programme for registration of Indigents | BTO Revenue & IT Manager | In-house | o CFO | 2022-12-01 | Monthly | o Mobilization Programme | o Council approve Report & resolution | Efficiency Gains
5 | COST CONTAINMENT AND CASH FLOW MANAGEMENT | Inadequate cashflow as required by MFMA circular 71. The ratio is below the norm of 1.5-: 2.1 | Prepare a plan to achieve norm of between 1-3 months | BTO Management Accountant | In-house | o CFO | 01/01/2023 | monthly | Cash Flow Management performed daily, weekly & monthly and results reported to Executive management | M | Planning efficiency & Risk management
|  | Inadequate institutional arrangements to monitor cashflow. | Establishment and Weekly meetings of the Cashflow management committee. | BTO Management Accountant | In-house | o CFO | 2023-01-01 | Weekly | o Sufficient Cash Flow generated to meet projected expenditure and capital requirements for each month of the fiscal year | No shortfall or borrowings from Capital Projects or other sources e.g. Banks, Suppliers extended Credit terms | Planning efficiency & Risk management
6 | SUPPLY CHAIN MANAGEMENT | Inadequate control by supply chain to manage procurement costs. | Implementation of the cost containment policy. | BTO SC Manager | In-house | o CFO | 2023-01-01 | monthly | SCM Demand management processes implemented | Financial report on Procurement cost savings. | Efficiency Gains
|  | Unfunded procurement plan. | Annual procurement plan is only effected if funding is available | BTO SC Manager | In-house | o CFO | 2023-01-01 | monthly | Level of Unfunded procurement | Report of financial performance against annual procurement plan. | Efficiency Gains
7 | EXPENDITURE & CREDITORS MANAGEMENT | Non-payment of creditors within 30 days. Current payment period of +/- 400/500 days. | Aggressive collection of receivables for settlement of creditors within 30 days. | CFO | In-house | o CFO | 2023-01-01 | monthly | o All creditors paid within 30 days | Monthly creditors age analysis | Financial Improvement
|  | Abuse of Electricity collections to cross subsidise expenditure, leading to Non-payment of Eskom Arrear Debt and Current Account. | Re-negotiation with Eskom on Arrear Debt and payment of Current Account timeously. | CFO | In-house | o CFO | 2023-01-01 | 2023-03-31 | o Negotiations concluded with agreement | Signed agreement and approval by council | Financial Improvement
|  | Outdated SOP for Expenditure and creditors. | Update SOP for expenditure and creditors. | BTO Management Accountant | In-house | o CFO | 2023-01-01 | 2023-03-31 | Expenditure in line with approved SOP. | Management approved SOP | Financial Improvement
8 | FUNDED BUDGET | Collection rate an average of 67% | Accurate budgeting for linked to cash collection
|  | Unauthorised expenidture | Accurate budgeting for non cash items
|  | Unfunded Budget | Funding plan inline with collection rate and expenditure limits | CFO | In-house | o CFO | 2023-01-01 | 2023-02-28 | Updated and approved Funded plan. | Council Approved & signed resolution | Going concern risk mitigated.
PILLAR FOUR: SERVICE DELIVERY
1 | ELECTRICITY: REVENUE ENHANCEMENT | The disfunctional relationships between the Municipality and it's residents, businesses and service providers hampers service delivery | Formalize partnerships with local communities and implement structures to report vandalism, illegal connections and meter tampering | Dir: Technical Services | Social Facilitator | Technical Services | 2023-01-02 | 2023-06-30 | Reliable reporting tool for community members to report vandalism, tampering or theft to EMLM and SAPS | A community reporting tool for reporting theft and vandalism. Works orders that are generated by Technical Services based on reports received (faults/vandalism/tampering).
2 | ELECTRICITY: REVENUE ENHANCEMENT | The Municipality's electricity operations run at a recurring deficit due to the high non-technical losses, poor billing and revenue collection. The municipality is sharing 30% of revenue with Utility World (Pty) Ltd, 50% with Musi Electrical Engineering and 50% with Parallax Endurance Energy | Effective management of existing Smart Meter contracts. Determine the proposed value add by service providers | CFO, Dir: Technical Services | Existing Service Provider | Technical Services | 2023-01-02 | 2023-06-30 | SLA's with Smart Meter Service providers to be renegotiated to depart from revenue sharing remuneration model and refocus scope of works towards managing Eskom Bulk Purchases Account and collecting revenue. Electricity Billing and collection improvement tracked monthly against historical baseline. | Monthly billing and collection statements indicating budgeted vs actual figures
|  |  | Set aside the 50/50 (Musi and Parallax) sharing arrangement or 30/70 sharing arrangement (Utility World) | MM, CFO, Dir: Technical Services | Existing Service Provider | Technical Services | 2023-01-02 | 2023-06-30 | Revised SLA. | Revised SLA.
|  |  | Remuneration of the service providers must be based on value added. | MM, CFO, Dir: Technical Services | Existing Service Provider | Technical Services | 2023-01-02 | 2023-06-30 | No. of meters installed, cost of the meters, labour cost of installing the meters, cost of taking the meter readings and actual collection of revenue. | No. of meters installed, cost of the meters, labour cost of installing the meters, cost of taking the meter readings and actual collection of revenue.
|  |  | Conduct a meter audit on all households across the municipality to ensure they are metered. | CFO, Dir: Technical Services | Existing Service Provider | Technical Services | 2023-01-02 | 2023-06-30 | Generate an exception report for households that are not metered | Generate an exception report for households that are not metered
|  |  | Conduct an audit to determine the functionality of installed meters | CFO, Dir: Technical Services | Existing Service Provider | Technical Services | 2023-01-02 | 2023-06-30 | Generate a report of faulty meters | Generate a report of faulty meters
|  |  | Review the payment plan for Eskom | In-house | In-house, Contracted Services, ESKOM | MM, Technical Director, CFO | 2023-01-02 | 2023-06-30 | Proof of payment in line with the payment plan | Proof of payment in line with the payment plan
|  |  | Pay Eskom current account | In-house | In-house, Contracted Services, ESKOM | MM, Technical Director, CFO | 2023-01-02 | 2023-06-30 | Proof of payment in line with the current account | Proof of payment in line with the current account
|  |  | Pay Eskom historical account | In-house | In-house, Contracted Services, ESKOM | MM, Technical Director, CFO | 2023-01-02 | 2023-06-30 | Proof of payment in line with payment plan | Proof of payment in line with payment plan
|  |  | Develop a Energy Demand Side Management (EDMS) strategy to reduce electricity losses to below 10%. | In-house | In-house, Contracted Services | MM, Technical Director | 2023-01-02 | 2023-06-30 | EDMS Strategy Document | EDMS Strategy Document
|  |  | Implementation of the EDMS strategy | In-house | In-house, Contracted Services | MM, Technical Director | 2023-01-02 | 2023-06-30 | Baseline Assessment and retrofit schedule. Implementation of cut-offs and removal of illegal connections register | Baseline Assessment and retrofit schedule. Implementation of cut-offs and removal of illegal connections register
3 | ELECTRICITY: REVENUE ENHANCEMENT | The Municipality's electricity operations run at a recurring deficit due to the high non-technical losses, poor billing and revenue collection | Effective deployment of internal technical personnel to enforce debt control policy and bylaws. | Dir: Technical Services | Internal Municipal Staff, Existing Service Provider | Revenue Protection | 2023-01-02 | 2023-06-30 | Disconnect defaulting customers as per debt control policy. | Monthly disconnection reports
4 | ELECTRICITY: REVENUE ENHANCEMENT | Tariffs are not cost reflective | Deliver an up to date and comprehensive Cost of Supply Study for the entire EMLM signed off by a suitably qualified and experienced Electrical Engineer. | Dir: Technical Services | Professional Electrical Engineer | Finance | 2023-01-02 | 2023-06-30 | Deliver a Cost of Supply Study for submission to NERSA. Obtain NERSA approval for Cost of Supply study | Appointment of Service Provider, Progress Reports, NERSA approval of final COS
5 | ELECTRICITY: REVENUE ENHANCEMENT | The Municipality's electricity operations run at a recurring deficit due to the high non-technical losses, poor billing and revenue collection | Formalise a response plan to address: • Communicate intent to eradicate illegal connections. • Partnership with communities who support removal of illegal connections. • Amnesty period and conditions. • Disconnection of illegal connections by EMLM personnel. • Partnership with SAPS for areas where EMLM personnel are threatened. | Meter inspectors, Revenue Enhancement Project Service Providers | External Communications Teams, Funding for communications | Revenue Protection | 2023-01-02 | 2023-06-30 | Disconnection of illegal electricity connections | Monthly reconciliation of Non-Technical Losses
6 | ELECTRICITY: COMPLIANCE | The Municipality is not complying with the minimum requirements of the OHS Act and General Machinery Regulations | Appoint / Allocate suitable resource for GMR 2.1 role. | Dir: Technical Services | Training Institution for exam readyness if internal candidates are considered. | Technical Services | 2023-01-02 | 2023-06-30 | Compliance with GMR 2.1 and OHS Act to be addessed via immediate short term appointment of a qualified resource. Medium to long term strategy to be aligned with restructuring of Technical services as per the approved structure design | Employment Contract for a suitably qualified Engineer, duly appointed to fulfill the GMR 2.1 role for the EMLM
7 | ELECTRICITY: COMPLIANCE | The Municipality is not complying with the minimum requirements of the OHS Act and General Machinery Regulations | Send field technicians for ORHVS training and accreditation. | Dir: Technical Services | Training Institution for exam readyness if internal candidates are considered. | Technical Services | 2023-01-02 | 2023-06-30 | Electrical Team leaders shall have passed their ORHVS course and attained accreditation to operate the Medium Voltage Network | ORHVS course entries ORHVS Course test results
8 | ELECTRICITY: COMPLIANCE | The Municipality is not complying with the minimum requirements of the OHS Act and General Machinery Regulations | Review and update EMLM H&S specification for Electrical Contracts. Document safe operating procedures. | Dir: Technical Services | Internal Municipal Staff | Technical Services | 2023-01-02 | 2023-06-30 | Produce an updated OHS Specification for use with electrical contracts in EMLM | Updated OHS Specification for use with electrical contracts in EMLM
9 | ELECTRICITY: SECURITY OF BULK ELECTRICAL SUPPLY | Electricity customers in EMLM are subjected to frequent and prolonged interruptions to supply | Servicing of primary and secondary plant components at EMLM 66kV / 1kV Substations. | Dir: Technical Services | Internal Municipal Staff | Technical Services | 2023-01-02 | 2023-06-30 | Address oil leaks, transformer overloading, malfunctioning protection, compromised access control and perimeter security at the four primary substations. | Appointment of Service Provider, Progress Reports, Completion certificates
10 | ELECTRICITY: IMPROVE PERFORMANCE OF DISTRIBUTION NETWORKS | Electricity customers in EMLM are subjected to frequent and prolonged interruptions to supply | Implement a secure equipment and materials stores control system to equip personnel. Deploy technicians to locate and repair faults on priority ring feed cables. | Dir: Technical Services | Internal Municipal Staff | Technical Services | 2023-01-02 | 2023-06-30 | Locate and repair cable faults on redundant 11kV cable feeds to restore ring feeding functionality and reduce outages. | Documented and approve Material and Equipment Stores Management System.
11 | ELECTRICITY: IMPROVE PERFORMANCE OF DISTRIBUTION NETWORKS | Electricity customers in EMLM are subjected to frequent and prolonged interruptions to supply | Assess the level of information currently on record and engage with past service providers to obtain the balance of relevant information. | Dir: Technical Services | Internal Municipal Staff | Technical Services | 2023-01-02 | 2023-06-30 | Obtain complete and updated drawings of all EMLM substation primary and secondary plant installations. | Schematic Drawing database for 11kV and 66kV network
12 | ELECTRICITY: IMPROVE PERFORMANCE OF DISTRIBUTION NETWORKS | Electricity customers in EMLM are subjected to frequent and prolonged interruptions to supply | Prioritize the 26 switching substation within EMLM and perform maintenance and servicing of primary and secondary plant at the most critical sites. | Dir: Technical Services | Internal Municipal Staff | Technical Services | 2023-01-02 | 2023-06-30 | Address protection system failures at switching substations as prioritized in a Short Term Maintenance Plan. | Short Term Maintenance Plan Completion Certificates for each individual substation for servicing and maintenance
13 | ELECTRICITY: IMPROVE PERFORMANCE OF DISTRIBUTION NETWORKS | Electricity customers in EMLM are subjected to frequent and prolonged interruptions to supply | Formalise partnership with business sector to leverage private security involvement in patrolling and monitoring critical switching substation sites. | Dir: Technical Services | Internal Municipal Staff | Technical Services | 2023-01-02 | 2023-06-30 | Address security risks at switching substations and record progress in a site register. | Formalized Service Level Agreement in partnership with local business
14 | ELECTRICITY: IMPROVE PERFORMANCE OF DISTRIBUTION NETWORKS | Public lighting installations in EMLM are in a state of disrepair. | Restore streetlights to a functional state along main routes. Restore prioritized high mast lights to functional state. | Dir: Technical Services | Internal Municipal Staff | Technical Services | 2023-01-02 | 2023-06-30 | Restore streetlights to a functional state along main routes. Restore prioritized high mast lights to functional state. | Progress to be recorded monthly and reflected in EMLM Asset Register
15 | ELECTRICITY: IMPROVE PERFORMANCE OF DISTRIBUTION NETWORKS | EMLM does not have an up to date Electricity Master Plan for the entire Municial Supply Area | Deliver an up to date and comprehensive Electricity Master Plan for the entire EMLM signed off by a suitably qualified and experienced Electrical Engineer. | Dir: Technical Services | Internal Municipal Staff | Technical Services | 2023-01-02 | 2023-06-30 | Electricity Master Plan to be developed by either an external resource or via assistance from MISA or DBSA | Appointment / SLA for competent Engineering resource to develop the Electricity Master Plan for EMLM Progress Reports Completion Certificate
16 | ELECTRICITY: IMPROVE PERFORMANCE OF DISTRIBUTION NETWORKS | EMLM maintenance expediture is not informed by any long term and holistic planning exercise | Develop a short term maintenance plan to inform critical repairs and maintenance activities | Dir: Technical Services | Internal Municipal Staff | Technical Services | 2023-01-02 | 2023-06-30 | Review the 2014 Lukhanji Master Plan to extract critical short term maintenance priorities Investigate funding sources for implementation of critical maintenance work. | Appointment / SLA for competent Engineering resource to extract a short term maintenance plan for Komani from the existing Lujhanji LM Master Plan. Progress Reports Completion Certificate
17 | ELECTRICITY: IMPROVE PERFORMANCE OF DISTRIBUTION NETWORKS | Short term insurance claims for theft and vandalism of infrastructure are regularly repudiated and EMLM therefore are unable to recover the cost for repairs and replacement of assets damaged through criminal activity | Engage with short term insurance provider to confirm adherence to minimum requirements and avoid repudiation of future claims | Dir: Technical Services | Internal Municipal Staff | Finance | 2023-01-02 | 2023-06-30 | Engage with short term insurance provider to confirm adherence to minimum requirements and avoid repudiation of future claims | MOU confirming the measurable requirements from short term insurers. Documented proof of EMLM compliance with the said requirements
18 | FLEET MANAGEMENT | The EMLM vehicle fleet is inadequate to provide reliable services trhoughout the Municipality's jurisdiction. | Carry out Fleet Needs Assessment and allocate availability to service departments accordingly | Dir: Technical Services | Internal Municipal Staff | Finance | 2023-01-02 | 2023-06-30 | Field staff to record "standing time" whenever fleet unavailability is responsible for unproductive, idle man hours | Fleet Needs Assessment Detailed, monthly records of idle time recorded by field staff
19 | ROADS AND STORMWATER | The EMLM is not recovering costs for damage caused by third party installations to their roads and stormwater infrastructure. | Assess damage to roads caused by third parties and issue notices to recover costs for the repair thereof. | Dir: Technical Services | Internal Municipal Staff | Technical Services; Finance | 2023-01-02 | 2023-06-30 | Formal notices issued in terms of approved By Laws Receipt of payment for damages by third parties. | Record of notices issued to third parties who have caused damage to roads and stormwater assets
20 | ROADS AND STORMWATER | Traffic lights throughout EMLM are in a state of disrepair, leading to congestion and increased safety risk | Appoint a suitably qualified and experienced service provider to repair and synchronize traffic lights throughout EMLM. | Dir: Technical Services | Internal Municipal Staff | Technical Services | 2023-01-02 | 2023-06-30 | Traffic lights throughout EMLM to be repaired and synchronized | Appointment / SLA for competent resource to perform the required work. Progress Reports Completion Certificate
21 | ROADS AND STORMWATER | Roads and stormwater infrastructure in EMLM is generally in a poor condition with pot holes being common even in town centres. | Prioritize critical sites and deploy field personnel to repair potholes and stormwater drainage infrastructure | Dir: Technical Services | Internal Municipal Staff | Technical Services | 2023-01-02 | 2023-06-30 | Potholes and stormwater drainage infrastructure repaired at critical sites as per prioritization in a Roads and Stormwater Master Plan | Appointment / SLA for competent resource to perform the required work. Progress Reports Completion Certificate
22 | PLANNING AND DEVELOPMENT | Spatial Development Framework is not up to date for the entire EMLM | Review and update Spatial Development Framework | Dir: Community Services | Internal Municipal Staff | Technical fervices | 2023-01-02 | 2023-06-30 | SDF as prepared by MISA to be reviewed and approved or ammended as required in order to be approved | Record of formal approval of an updated SDF for the entire EMLM.
23 | WASTE MANAGEMENT | Tariffs are not cost reflective | Develop cost reflective tariffs for waste collection and disposal services throughout EMLM. | Dir: Community Services | Internal Municipal Staff | Technical rervices | 2023-01-02 | 2023-06-30 | Updated tariffs to be published | Cost analysis report for Waste Management Services Record of approved Waste collection and disposal tariffs
|  | No billing on vehicles desposing waste due to lack of the weighbgidge | Develop and implement a billing schedule for vehicles entering the landfill site based on the vehicle entering in order to compensate for the absence of a weighbridge | Dir: Community Services | Internal Municipal Staff | Technical rervices | 2023-01-02 | 2023-06-30 | Vehicle billing template | Collected revenue report
24 | WASTE MANAGEMENT | Compliance with OHS Act and Environmental Regulations is poor | Assess current levels of compliance with National Environmental Management Act and OHS Act and address shortfalls. | Dir: Community Services | Internal Municipal Staff | Technical rervices | 2023-01-02 | 2023-06-30 | Risk associated with the EMLM poor compliance record in terms of the National Environmental Management Act and OHS Act must be reduced | Compliance audit report Record of steps taken to address findings in the Compliance Report Risk assessment confirming that the actions taken have improved the EMLM risk profile
25 | WASTE MANAGEMENT | Waste Management sites are not fully licensed | Develop and adopt a process plan to achieve licensing of waste management sites. | Dir: Community Services | Internal Municipal Staff | Technical oervices | 2023-01-02 | 2023-06-30 | Achieve licensing of waste management sites. | Achieve licensing of waste management sites.
26 | ASSET MANAGEMENT | Overall Asset Management is poor | Develop Budgeting tools to ensure that relevant information from the EMLM GRAP Compliant Asset Register is considered in budgeting for maintenance and repairs. | Dir: Technical Services Dir: Community Services Dir: Development and Planning | Internal Municipal Staff | Technical aervices | 2023-01-02 | 2023-06-30 | Maintenance, repair and replacement of obsolete items must be realistically reflected in annual expenditure budgets | Budgeting Tool agreed upon for implementation by Technical Services and Finance Departments Detailed Expenditure budgets
27 | ASSET MANAGEMENT | Overall Asset Management is poor | Develop Master Plans for all fixed asset groupings not covered by the Electricity and Roads & Stormwater Master Plans | Dir: Technical Services Dir: Community Services Dir: Development and Planning | Internal Municipal Staff | Technical Services | 2023-01-02 | 2023-06-30 | Master Plans for all fixed asset groupings not covered by the Electricity and Roads & Stormwater Master Plans | Appointment / SLA for competent resource to perform the required work. Progress Reports Completion Certificate
28 | SPATIAL PLANNING AND HUMAN SETTLEMENTS | Current spartial planning environment not conducive to speedy development and there is a demand for developments but there is difficulty for developers to develop infrastructure and human settlements effectively. | Increase revenue by making land available and attractive to private sector developers. | In-house | In-house | MM, Technical Director, Corporate Services | 2023-01-02 | 2023-06-30 | List of land available for sale or lease. Government owned land parcels which could be donated to the municipality | List of land available for sale or lease. Government owned land parcels which could be donated to the municipality
|  |  | Review development and land use tariffs. Such as rezoning costs. Update where necessary. Promulgate updated by-laws as required. | External / Service provider | In-house | Dir: Planning and Development | 2023-01-02 | 2023-06-30 | Reviewed the tariffs | Reviewed Tariffs
|  |  | Enforcement of Land Use Scheme and By-law to cub the high number of Illegal land uses | External / Service provider | External / Service provider | Dir: Planning and Development | 2023-01-02 | 2023-06-30 | By-law transgression fines register | By-law transgression fines register.
|  |  | Conduct assessments and the alienation and disposal of some of the Council Owned Properties | External / Service provider | External / Service provider | Dir: Planning and Development | 2023-01-02 | 2023-06-30 | Land Disposal Schedule | Land Disposal Schedule
|  |  | Tribunal Applications; Submit applications to Tribunal and Processing of applications for approval | External / Service provider | In-house | Dir: Planning and Development | 2023-01-02 | 2023-06-30 | Number of applications processed | Updated council resolution for the Spartial Planning Tribual. Tribunal Minutes
|  |  | Develop and Implement the 30% Project Sub-contract Policy for to support local companies | External / Service provider | External / Service provider | Dir: Planning and Development | 2023-01-02 | 2023-06-30 | Percentage expenditure on sub-contractor per project monthly spend | Percentage expenditure on sub-contractor per project monthly spend calculation
|  |  | Printing of Maps | In-house | In-house | Dir: Planning and Development | 2023-01-02 | 2023-06-30 | Revenue Generated | Revenue Generated
|  |  | Issue Zoning certificates | In-house | In-house | Dir: Planning and Development | 2023-01-02 | 2023-06-30 | Register for issue of certificates | Register for issue of certificates

## Phase 2 Stabilization (2)
PHASE 2: STABILIZATION
NO | FOCUS AREA | KEY ASSESSMENT FINDING (BASELINE) | KEY ACTIVITIES | RESOURCES REQUIRED | RESOURCES MOBILISED | RESPONSIBLE | START DATE | END DATE | KEY PERFORMANCE INDICATOR | PORTFOLIO OF EVIDENCE | BUDGET PARAMETER/ REVENUE TARGET/ SPENDING LIMIT | MUNICIPAL PROGRESS REPORT
[12 empty] | STEPS TAKEN | PROGRESS MADE | FINANCIAL IMPACT | OTHER NOTEWORTHY DEVELOPMENTS
PILLAR ONE: GOVERNANCE
1 | UNAUTHORISED, IRREGULAR, FRUITLESS AND WASTEFUL EXPENDITURE | Escalating UIF&W expenditure. Late payment of creditors. Section 32 MFMA investigations not done. Non-compliance with supply chain policy and processes. Disclosed UIF&W expenditure not true reflection. No internal controls for recognition and record of expenditure. No consequence management. Overspending on budget | Implement UIF&W expenditure reduction plan. | In-house and NT-MFMA unit | In-house and NT-MFMA unit | Chief Finance Officer | 2023-07-01 | Monthly | UIF&W expenditure reduction plan implementation and percentage reduction in historical expenditure | Quarterly Council reports on progress on implementation of the reduction plan
|  |  | Implement measures to prevent and address unauthorised, irregular, fruitless and wasteful expenditure | In-house | In-house | MM, CFO, Directors | 2023-07-01 | Monthly | Percentage reduction in current UIF&W expenditure | AG Audit report and internal audit reports
|  |  | Identify, and report on irregular, unauthorised, fruitless and wasteful expenditure as per legislation | In-house | In-house | Council, MPAC, Disciplinary Board | 2023-07-01 | Quarterly | Quarterly reports on UIF&W expenditure and investigations | Council approved quarterly reports, MPAC oversight reports, Disciplinary Board's reports and related resolutions
|  |  | Implement Consequence management | In-house | In-house | Disciplinary Board, Executive Mayor and MM | 2023-07-01 | Quarterly | Transgressors disciplined | Written outcome of disciplinary hearings
2 | SYSTEM OF DELEGATIONS | System of Delegations not reviewed No updated delegations register No sub-delegations below Heads of Directorates | Maintain an updated delegations register | In-house | In-house | General Manager: Corporate Services | 2023-07-01 | Quarterly | Sub-delegations emanating from approved System of delegations signed-off by MM and Heads of Directorates | Approved system of delegations, signed-off sub-delegations. Updated delegations register
3 | CONTRACT MANAGEMENT | 3.Inadequate contract management. Payments for services not done within thirty days, irregularly awarded contracts. Outdated Contract register. Irregularly awarded contracts | Maintain an updated contract register | In-house | In-house | General Manager: Corporate Services and CFO | 2023-07-01 | Monthly | No irregular, unnecessary or expired contracts, and contracts register in place | Updated contract register
|  |  | Monitor deviations to identify other goods and services required on an ongoing basis and appoint service providers on three year contracts | In-house | In-house | CFO | 2023-07-01 | Monthly | Reduction in operational costs, Reduction in irregular deviations, compliance with legislation | Reduction in procurement costs as per procurement plan, and appointment letters
|  |  | Submission of monthly performance monitoring reports on contracts | In-house | In-house, Contracted Services | CFO | 2023-07-01 | Monthly | value for money, compliance with legislation | Monthly performance monitoring reports
|  |  | Implementation of contract management framework | In-house and COGTA/SALGA | In-house and COGTA/SALGA | CFO/General Manager: Corporate Services | 2023-07-01 | Monthly | Effective contract management and comliance with legislation. | AG audit reports and quarterly Internal audit reports
|  |  | Implement long term procurement for goods and services required on an ongoing basis | In-house | In-house | CFO | 2023-07-01 | Monthly | Reduction in operational costs related to procurement | Approved reviewed procurement plan and Council resolution
4 | LEGAL COMPLIANCE, LITIGATION AND CONTINGENT LIABILITY | Contingent liability at R26 714 044.00 Low Risk financial exposure Material non-compliance with legislation | Monthly update litigation register | In-house | In-house | General Manager: corporate Services | 2023-07-01 | Monthly | Reduction in legal costs, updated litgation regster in place | Monthly updated litigation register
|  |  | Implementation of MFMA Legal compliance matrix | In-house | In-house and NT-MFMA unit | General manager: corporate Services | 2023-07-01 | Monthly | Legislative compliance | AG annual audit reports and quarterly internal audit reports
5 | RISK AND INTERNAL AUDIT | Risk management policy approved Chief Risk Officer not appointed Ineffective Risk management Poor internal controls Risk management documents for FY2022/23 not approved Inadequate implementation of risk strategies and plans | Maintain an updated risk register | In-house | In-house | Chief Audit Executive | 2023-07-01 | Monthly | Effective management of corporate risks | Updated risk register
|  |  | Quarterly reports on implementation of internal audit plan | In-house | In-house | Chief Audit Executive | 2023-07-01 | Quarterly | Effective mitigation of risks | Quarterly reports and Council resolutions
|  |  | Quarterly progress reports on implementation of remedial actions to mitigate against corporate risks | In-house | In-house | Chief Risk officer | 2023-07-01 | Quarterly | Effective management of identified risks | Quarterly reports and Council resolutions
|  |  | Approval of annual audit plan and risk management documents for the financial year 2022/23 financial year |  | In house | Chief Audit Executive/ Chief Risk officer | 2023-07-01 | 2024-03-31 | Policies and plans in place | Approved annual audit plan and risk management documents, and related Council resolutions
6 | POWERS AND FUNCTIONS | Municipality mandated to provide library services and licensing services | Monitor and report on actual operational costs against total funding received in terms of the mandate agreement | In-house | In-house | CFO | 2023-07-01 | Quarterly | Fully funded mandates | Quarterly Financial analysis reports
7 | BY-LAWS AND ENFORCEMENT | Ineffective enforcement of by-laws Inadequate institutional arrangements for enforcement No reporting on revenue generated from enforcement of by-laws | Enforcement of By-laws | In-house | In-house, NPA and Department of Justice | General Manager: Community safety | 2023-07-01 | Monthly | Effective enforcement of by-laws. Reduction in electricity and water losses. | Quarterly audited reports on revenue generated from enforcement of by-laws.
|  |  | Report on revenue generated | In-house | In-house | General Manager: Community safety | 2023-07-01 | Monthly | Increase in revenue | Quarterly audited reports on revenue generated from enforcement of by-laws.
8 | OVERSIGHT STRUCTURES OF COUNCIL | Inadequate implementation of Council resolutions. No tracking of the Implementation of Council Structures Resolutions. Culture of ill-discipline and lack of accountability at political and administrative level. Ineffective reporting mechanism to enhance council oversight. Non-compliance with Council Calendar. Portfolio committees not seating since the inception of the new council. Ward Committees not effective and no Ward Based Planning. Councillors and staff owing for services rendered. Inadequate oversight over Executive and Administration. System of Delegations not reviewed. | Development of annual schedule of meetings and adherence for council and committees for 2023/24 financial year | In-house | In-house | General Manager: Corporate Services | 2023-07-01 | 2024-03-31 | Schedule of meetings in place and adhered to. | Approved schedule of meetings and Council resolution
|  |  | Convene meetings of TROIKA | In-house | In-house and COGTA/SALGA | MM/General Manager: Corporate Services | 2023-07-01 | Monthly | Effective political and administrative interface | Minutes of meetings
|  |  | Maintain annual institutional calendar of council and committee meetings | In-house | In-house | General Manager: Corporate Services | 2023-07-01 | Monthly | Organised and focused TROIKA | Approved schedule of meetings and Council resolution
|  |  | Track implementation of Council resolutions | In-house | In house | Manager: Office of the Speaker | 2023-07-01 | Monthly | Accelerated service delivery | Updated Council resolution register
|  |  | Monitoring and reporting on allegations of misconduct made against any councillor and progress on pending cases with regard to the code of conduct for councillors | In-House | In-house | Speaker of Council | 2023-07-01 | Monthly | Disciplined councillors and adherence to legal prescripts | Quarterly reports on compliance with code of conduct by Councillors
|  |  | Section 32 investigation on UIF&W expenditure and financial misconduct investigation reports to Council | In house | In house | Disciplinary Board, Executive Mayor and MM | 2023-07-01 | Quarterly | Effective Consequence management | Council approved section 32 investigation reports
|  |  | Implementation of the report on forensic investigation into investigation into irregularities and misappropriation of assets | In House | In House | Council/ Executive Mayor | 2023-07-01 | Quarterly | Effective Consequence management and improved workforce discipline | Oversight Council reports on quarterly implementation progress reports
|  |  | Investigate non payment for services by Councillors and administrative officials | In House | In House | CFO | 2023-07-01 | Quarterly | Compliance with Code of Conduct | Audit report
|  |  | Enter into payment arrangements with Councillors and Administrative officials on arrears for services and monitor honoring of payment arrangements | In House | In House | CFO General Manager: Corporate Services | 2023-07-01 | Quarterly | Increase in revenue and reduction of debt owed to the municipality | Signed payment arrangements and financial statements
|  |  | Develop schedule and implementation of meetings for Executive management meetings | In-house | In-house | MM | 2023-07-01 | Monthly | Effective and efficient co-ordination of administration and service delivery | Approved schedule of meetings and Council resolution
|  |  | Develop and implement training programme for councillors on governance, financial management and oversight; | In-house | In-house | General Manager: Corporate Services | 2023-07-01 | Bi-annually | Empowered Councillors to execute their responsibilities | Council approved training programme and resolution, and attendance register.
9 | PUBLIC PARTICIPATION | There is no regular and structured engagement with Stakeholders. Negative perception by stakeholders resulting into non-payment of services and lack of confidence in EMLM. Current Policies are fragmented, content duplicated and framework not consistent, neither there is evidence that they are approved by Council. | Monthly reporting on stakeholder engagement activities in line with approved strategy | In-house | In-house | General Manager: Corporate Services | 2023-07-01 | Monthly | Meaningful stakeholder partcicipation in affairs of the municipality | Reports on engagements & Attendance registers Quarterly Council reports and signed resolutions
|  |  | Monthly reporting on communication activities in line with the approved communication plan | In-house | In-house | General Manager: Corporate Services | 2023-07-01 | Monthly | Informed community and stakeholders | Reports on communication activities
|  |  | Reporting to Council on outcome of stakeholder surveys | In-house | In-house | General Manager: Corporate Services | 2023-07-01 | Quarterly | Stakeholder survey reports | Stakeholder survey report and signed Council resolution
10 | INFORMATION AND COMMUNICATION TECHNOLOGY | Structure of ICT, Strategy in place but not institutionalised. ICT steering committee not established. Inadequate disaster recovery plan | Implementation of ICT Governance framework more specifically general controls | In-house | In-house | Manager: ICT | 2023-07-01 | Monthly | Effective ICT general controls, assurance on confidentiality and integirty of data. | AG Audit report and internal quarterly audit reports
|  |  | Report on Back office Turnaround times in resolving help desk quiries | In house | In house COGTA | All Heads of Directorates | 2023-07-01 | Monthly | Satisfied customers Increased revenue. 95 % of work orders completed | Customer saticfaction survey and Monthly work order reports
|  |  | Update the website | In house | In house COGTA | ICT Manager | 2023-07-01 | Monthly | Updated website | Updated website
11 | IMMOVABLE PROPERTY PORTFOLIO | Inadequate institutional arrangements. Loss of revenue. Ineffective collection of revenue on leased properties. | Disposal of strategic land parcels for economic development | In house | In house | MM | 2023-07-01 | Quarterly | Facilitate economic development, Increased revenue( rates and taxes, and electricity and watersales) | Deeds of Transfer
|  |  | Collection of market related rentals from tenants | In house | In house | CFO | 2023-07-01 | Monthly | Increase in revenue | Financial report
|  |  | Non paying tenants be ejected from the properties | In house | In house | General Manager:Corporate services | 2023-07-01 | Monthly | Increase in revenue | Tenant management report
PILLAR TWO: INSTITUTIONAL
1 | EMPLOYEE COSTS | High Employee Costs as a results of Gross over-grading of jobs in TASK. | All non-critical vacancies must not be filled and there should be zero percent increase on employee salaries. Conduct a cost-benefit-analysis for outsourced and insourcing of services and submit to council with recommendations for implementation. Given the liquidity position of the Municipality, the payroll budget must be stricly controlled but plan for the acquisition of skills in line with cash flow improvements. | In house | In-house | General manager: Corporate services | 2023-07-01 | 2024-06-30 | Achieved completeness of employee costs. Attained buy-in & support. | Report on the cost benefit analysis for outsourced & insourcing of services. Council resolution. | In line with the approved budget and the funding plan.
2 | Organisational Structure | The Organisational Structure was reviewed and approved a year after the amalgamation but has not been implemented. The structure is not based on a fit for purpose operating model and is therefore incorrectly layered and is top heavy with management layers (Directors, Senior Managers and Managers). Current job descriptions are irrelevant. There is no Placement Policy. | Implementation of the approved organisational Structure. Placement of staff in the approved organisational structure. Implemenation of the job evaluation results. Consultation with the LLF | In-House | In-House | General manager: Corporate services | 2023-07-01 | 2024-06-30 | Functions properly aligned to strategic objectives and legal mandate. Right people in right jobs Correct Grading in TASK Achieved affordability. | Approved Organisational Structure Council resolution Agenda, Minutes & attendance register of the LLF meetings Copy of the placement report. Copy of the job evaluation results. | In line with the approved budget and the funding plan.
3 | Policy Review and development | The Municipality do have documented policies and procedures to guide its operations, however compliance with these policies was not monitored resulting in instances of non-compliance | Review and update all HR Policies. Implementation and monitoring. Conduct workshop for the LLF and employees on the approved policies. Enforce consequence management for non-compliant with the municipal policies and other related legislation/directives. Schedule time into the corporate calendar for regular reviews. | In-houae | In-house | General manager: Corporate services | 2023-07-01 | Ongoing | Policies aligned to HR Strategy + IDP. Employee motivation, organisation reputation and the ability to attract and retain talent. | Policies completed as per list. Council Resolution LLF minutes & attendance registers. Attendance registers of employees on the workshops conducted. Copy of the corporate calendar for regular reviews. | In line with the approved budget and the funding plan.
4 | HR STRATEGY | HR Strategy not finalised and not approved by Council. | Review the HR Strategy Consultation with the LLF Submit to Council for approval and implementation | In-house | in-house | General manager: Corporate services | 2023-07-01 | 2024-06-30 | HR strategy alignnment with IDP and new structure implications | HR Strategic Plan. Council resolution. LLF minutes & attendance register. | In line with the approved budget and the funding plan.
5 | Leave Management and Absenteeism | Disregard of legislated processes and complete lack of supervision | Introduce a clocking system linked to Payroll (considered automated options). Authorise Payroll to individual employees based on the timesheet signed by the departmental head or someone delegated. Enforcement of leave procedures and consequence management for transgressions. Assist affected staff with medical boarding applications. Request the EC Liquor Board to assist alcohol abuse counselling and support (as part of their CSI programmes). | In-house | In-house | General manager: Corporate services | 2023-07-01 | 2024-06-30 | Re-affirmed accountability and discipline | Disciplinary outcomes and sanctions | In line with the approved budget and the funding plan.
6 | STAFF DISCIPLINE & CONSEQUENCE MANAGEMENT | Political interference. High rate of disregard for work procedures and respect for work protocols. Certain employees doing business with the municipality. Lack of stringent control measures hampering successful outcome of disciplinary procedures. Delays in the conclusion of disciplinary cases. | xpedite all outstanding matters and finalise them. Source the services of the district and other state organs to assist with presiding and prosecuting of all matters. Submit a report to council on the employees doing business with the municipality and apply consequence management to those involved. Train s56 and other senior managers to be used as Presiding Officers and Prosecutors. Expedite the appointment of Manager Legal and Industrial Relations Officer. Municipal Manger to engage Councillors through the office of the Mayor & the speaker to desist from interfering with disciplinary processes. Develop and implement Consequence Management Policy. Develop and regularly update the disciplinary case management register | In-House | In-house | General manager: Corporate services | 2023-07-01 | Ongoing | Reduced number of disciplinary cases Professionalism | Records with details of trained officials. Disciplinary case manegement register. | In line with the approved budget and the funding plan.
7 | LABOUR RELATIONS | LLF established and functional. | Institutionalization of attendance of LLF meetings. Provide training for Organized Labour on local labour forum issues. Enforce consequence management on non-attendance of members to the planned meetings. Municipal Code of conduct for employees should be communicated to the members of the LLF and staff regularly. | In-house | In-house | General manager: Corporate services | 2023-07-01 | Ongoing | Sound Labour Relations | Calendar of meetings,attendance register,minutes of the LLF meetings and Agenda. | In line with the approved budget and the funding plan.
8 | Performance Management | Enoch Mgijima Local Municipality developed and adopted a Performance Management System Framework and Policy. Performance management is only limited to the accounting officer and to the managers that are directly accountable to the municipal manager. It is not yet cascaded to positions below that. | Review & seek council approval of the PMS policy. Institutionalize PMS to all line managers as part of their performance agreements. Cascade PMS to employees lower than the S56/7 managers. Signing of Performance agreement with all managers reporting directly to the municipal manager. Conduct quarterly assessment for senior managers and submit reports to council. Enforce consequence management for poor performance | In-house | In-house | General manager: Corporate services | 2023-07-01 | Ongoing | Improved performance management system | Adopted Performance management systems aligned to regulation 8 of municipal planning and performance management regulation. Council resolution. LLF minutes andt attendance register. Implementation plan on cascading PMS to other levels of employees. Copies of the PA of s56/7 managers. Quarterly Performance assessment reports of s56/7 managers | In line with the approved budget and the funding plan.
9 | SKILLS AUDIT & COMPETENCIES | Limited capacity and skills. | Conduct skills audits to identify existing skills and skills gaps within the organisation. Develop and implement Work skills Plan. Ensure that all Senior, middle managers, and financial officials are assisted to meet the minimum competency levels as required by the Municipal Regulations on Minimum Competency Levels 2007. Conduct verification of qualifications of all the employees. Work in partnership with various departments, training providers to improve the level of skills, knowledge, and behaviour of employees and citizens, enabling them to be active participants in the economic development and growth of the city. Institutionalize the role and responsibilities of managers in the skills development committees as well as training & development of their subordinates. Develop a transparent framework for selection of employees to undergo training and development. Mangers to make provisions in their budgets for implementation of the identified training interventions. Ringfenced the mandatory grants for training and development. | In-house | In-house | General manager: Corporate services | 2023-07-01 | Annually | Management and staff perform to the standards. Compliance with the prescribed minimum competency levels required for the position. | Skills Audit report. Work Skills Plan Council resolution Minutes & attendance register of the Training Committee & LLF Annual Training Report Status report on staff competency levels. Staff qualification verification report | In line with the approved budget and the funding plan.
10 | RECORDS MANAGEMENT | Council records are kept in different directorates. No proper filling systems in place and several delays were encountered during the audit in management providing the required information | Implementation and monitoring of the Records management Policy. Implementation and monitoring of the approved File plan. Designate an individual as the records manager. Centralization of all records of the municipality. Control storage and access. Provide Training on document management and POPIA (Protection of Personal Information Act). Implementation of electronic filling system. Implementation of offside record storage. | In-house | In-house | General manager: Corporate services | 2023-07-01 | 2024-06-30 | Improved referencing system and records managegment Improved Compliance Protection of information Accesibility | Approved File Plan Approved Policy Council Resolution LLF Minutes & A ttendance register | In line with the approved budget and the funding plan.
11 | Change Management | No change management strategy in place. | Conduct employee satisfaction survey. Develop and implement a Change Management strategy. Develop and implement a Communication Strategy/Plan to ensure free flow of information during the intervention Regular reporting on the implementation of Change management activities. There is a need for council and management to ensure that everyone rallies behind turning around the finances of the municipality by reducing expenditure, adhering to legislation and commitment to change. | In-House | In-house | General manager: Corporate services | 2023-07-01 | Ongoing | Achieved buy-in and support/ Set tone for change. Staff morale boosted. Enhanced service delivery & performance. Increased productivity to support Revenue Management operations. | Completed Employee satisfaction Survey Questions. Copy of the Change Management Strategy/Policy. Copy of the report on Change management activities. | In line with the approved budget and the funding plan.
PILLAR THREE: FINANCIAL MANAGEMENT
1 | REVENUE & DEBTORS MANAGEMENT - ELECTRICITY, REFUSE & RATES AND TAXES | Delay in the finalisation of the supplementary valuation objections leading to loss of revenue. | o Valuation tribunal to finalise valuation | o EMLM BTO Revenue Manager | In-house | o CFO | 2023-07-01 | 2023-03-31 | REVENUE & DEBTORS - Electricity, Refuse & Rates and Taxes SV2 completed | Valuation Roll data clean report | Efficiency Gains
|  | Incomplete reconciliation between billing system & valuation roll and approved tariffs. | o Valuation roll to be update on billing system and correct the usage tariffs. | o EMLM BTO Revenue Manager | In-house | o CFO | 2023-07-01 | 2023-03-31 | o A sustainable financially sound municipality delivering services to its residents in a cost reflective manner | Valuation Reconciliation report | Efficiency Gains
|  | Reconciliation of the financial system with the land use management system. | o Commence valuation roll process now to meet the next full valuation process | o EMLM BTO Revenue Manager | In-house | o CFO | 2023-07-01 | Monthly | o A robust billing system for services provided | Reconciliation report | Efficiency Gains and improve Rates & Taxes Revenue
|  | Outdated financial by-laws. | o Review and enforce all financial by-laws | o EMLM BTO Revenue Manager | In-house | o CFO | 2023-07-01 | 2023-03-31 | o Delivering services that are economical, efficient and effective | Application of by-law reports and Council Approval Resolution | Efficiency Gains
|  | Inadequate & incomplete reconciliation between Electricity Purchased and Billed. | Reconcile the check meter units to billings and Eskom purchases. | o EMLM BTO Revenue Manager | In-house | o CFO | 2023-07-01 | monthly | o Units Difference reduced over time | Reconciliation Report | Efficiency Gains
2 | CUSTOMER CARE | Inadequate Centralised Customer Care Call Centre. | Review of customer care technology. | o BTO Revenue & IT Manager | In-house | o CFO | 2023-07-01 | 2023-03-31 | o CRM Implemented | Call Centre operationalised | Efficiency Gains
|  | Inadequate customer turnaround times in addressing queries | Service delivery standards with turn around times. | o BTO Revenue & IT Manager | In-house | o CFO | 2023-07-01 | 2023-03-31 | o CRM Implemented | Communication issued from EMLM | Customer satisfaction and efficiency gains
3 | DEBTORS CREDIT CONTROL AND DEBT MANAGEMENT | Lack of preparation and distribution of month statements | Monthly accounts to be distributed using various means available e.g. email etc | o BTO Revenue & IT Manager | In-house | o CFO | 2023-07-01 | 2023-03-31 | o Record of Statement Deliveries | Statistical report of distribution of customer accounts. | Revenue Enhancement & Cash Collection
|  | Lack of continuous campaigns to advocate payment for services. | Communication campaign programme | o BTO Revenue Manager | In-house | o MM & CFO | 2023-07-01 | On-Going | o Community Town Halls, Advertising, Ward Meeting | Council Approved programme & Monthly implementation reports. | Efficiency Gains
|  | Inadequate enforcement of the credit control policy & by-law for disconnections. | o Revenue management to ensure technical services effects disconnections within 48 hours. | o EMLM BTO Revenue Management | In-house | o CFO | 2023-07-01 | Monthly | o Improved Reporting - Disconnections reports | Disconnection reports and reconnection fees. | Revenue enhancement
|  | Inadequate & ineffective debt collection. | Implement aggressive debt collection mechanisms by taking legal action. | o EMLM BTO Revenue Manager | In-house | o CFO | 2023-07-01 | Monthly | o Improved Collection Rates | Improvement in collections after customer outreach | Revenue Collection Enhanced
|  | Inadequate process for the write off of old debt and excessive impairments. | Table of write offs to Council for approval. | BTO Revenue Manager | In-house | o CFO | 2023-07-01 | Quarterly | o Account with small balances cleared | Council approved reports and signed resolutions. | Efficiency Gains
4 | INDIGENT MANAGEMENT | Poor Identification of indigents and register updated | Report to council on mobilisation programme for registration of Indigents | o BTO Revenue Manager | In-house | o CFO | 2023-07-01 | On-Going | o Mobilization Programme | o Council approve Report & resolution | Efficiency Gains
5 | CASH FLOW MANAGEMENT | Inadequate cashflow as required by MFMA circular 71. | o Prepare a plan to achieve norm of between 1-3 months | o BTO Management Accountant | In-house | o CFO | 2023-07-01 | On-Going | Cash Flow Management performed daily, weekly & monthly and results reported to Executive management | Record of cashflow management activities | Planning efficiency & Risk management
|  | Inadequate institutional arrangements to monitor cashflow. | o Establishment and Weekly meetings of the Cashflow management committee. | o BTO Management Accountant | In-house | o CFO | 2023-07-01 | Weekly | o Sufficient Cash Flow generated to meet projected expenditure and capital requirements for each month of the fiscal year | No shortfall or borrowings from Capital Projects or other sources e.g. Banks, Suppliers extended Credit terms | Planning efficiency & Risk management
6 | SUPPLY CHAIN MANAGEMENT | Inadequate control by supply chain to manage procurement costs. | o Implementation of the cost containment policy. | o BTO SC Manager | In-house | o CFO | 2023-07-01 | monthly | SCM Demand management processes implemented | Financial report on Procurement cost savings. | Efficiency Gains
|  | Unfunded procurement plan. | Annual procurement plan is only effected if funding is available | o BTO SC Manager | In-house | o CFO | 2023-07-01 | monthly | Level of Unfunded procurement | Report of financial performance against annual procurement plan. | Efficiency Gains
7 | EXPENDITURE & CREDITORS MANAGEMENT | Non-payment of creditors within 30 days. Current payment period of +/- 400/500 days. | Aggressive collection of receivables for settlement of creditors within 30 days. | o CFO | In-house | o CFO | 2023-07-01 | monthly | o All creditors paid within 30 days | Monthly creditors age analysis | Financial Improvement
|  | Abuse of Electricity collections to cross subsidise expenditure, leading to Non-payment of Eskom Arrear Debt and Current Account. | Re-negotiation with Eskom on Arrear Debt and payment of Current Account timeously. | o CFO | In-house | o CFO | 2023-07-01 | Monthly | o Negotiations concluded with agreement | Signed agreement and approval by council | Financial Improvement
|  | Outdated SOP for Expenditure and creditors. | o Update SOP for expenditure and creditors. | o BTO Management Accountant | In-house | o CFO | 2023-07-01 | 2023-03-31 | Expenditure in line with approved SOP. | Management approved SOP | Financial Improvement
8 | Financial Control environment | The municipality does not have a fully functioning core financial system. Internal Audit Function: - Not adequately structured and resourced - - Design and system of internal control inadequate - Risk management not adequately implemented – - Municipality not addressing issues raised by the AGSA. Poor contract performance by service provider. (mSCOA). Manual interventions to extract and upload data strings. SOPs not fully developed due to mSCOA challenges. | Budget funding for the implementation of a fully functional financial system with embedded financial controls, including adequately training to staff to use all the installed functions of the compliant system. Establish and maintain effective risk management to: - Put effective mechanisms in place to ensure compliance with law, policies and regulations - Prevent UIFW - Ensure compliance with basic requirements of financial management (revenue and expenditure management) - Ensure delivery against set targets Implement a fully functional mSCOA system with embedded financial controls Adequately train staff to use all the installed functions of the mSCOA system. Investigate and address all the material irregularities identified by the AGSA in the 2020/21 management letter. Develop and align SOPs for manual and automated processes and procedures. Install or activate an audit trail module to assist with accountability etc. Train management on risk identification and mitigation. | Inhouse | Inhouse | MM and CFO | 2023-07-01 | 30.04.2024 | Updated SOP financial management | AG Reports Training Schedules SOPs Risk Management System | Budget prepared directly on the financial system
9 | mSCOA | The municipality does not have a roadmap in place to assist with the smooth sailing of mSCOA Implementation No functional Technical Committee after the service provider’s contract was terminated. The municipality is manually inputting the data strings to ensure submission to the portal as the function is not available in the financial system. Municipality does not lock the system before submission to National Treasury as corrections can be made in the month, which is due, this is in contravention to Treasury regulations on mSCOA | Setup functional mSCOA Steering Committee Implementation of mSCOA Road Map Timeously Submission of credible data strings Revise and implement plan for non-functional modules NT and PT support on mSCOA implementation | Inhouse | Inhouse | MM and CFO | 2023-07-01 | 28.02.2024 | Functional mSCOA Steering Committee Approved mSCOA Road Map Timeously submission of credible data strings Full functionality of all modules on the core system | Terms of Reference for mSCOA Steercom Minutes of meetings for SteerCom Approved mSCOA roadmap Accurate data strings Progress report on implementation of mSCOA | Not applicable
PILLAR FOUR: SERVICE DELIVERY
1 | ASSET MANAGEMENT | Lack of skills, Non-compliance with Asset Management Policy and Procedure Manual, Lack of asset replacement strategy. | Development and implementation of Asset Management policy and strategy. Development and implementation of a long-term Asset Management Master Plans that will investigate long term investments, replacement, maintenance and sustainability of the municipality, amongst others Development of Property Plant and Equipment maintenance plan Audit of current infrastructure to determine state, taking into consideration service backlogs and long-term strategy aligned to the operating model IDP, budget and long-term financial plan Update and maintain Asset Register Maintenance of Property Plant and Equipment through internal capacity and outsourced services Review contracts and tariffs on municipal buildings being leased and hired. | In-house | In-house | MM, CFO, Technical Director | 2023-04-01 | 2024-03-31 | Asset maintenance plans Approved building maintenance plan Update and maintained Asset Register | Target 8% of OPEX
2 | ROADS AND STORMWATER | Poor Road condition and Road surface marking visibility | Implement the roads and stormwater master plan Develop and implement the Roads and Stormwater Maintenance plan Maintenance of roads infrastructure through internal capacity and outsourced services Rehabilitate roads as per Maintenance Plan Implement internal roads programme | In-house | In-house | MM, Director: Technical Services | 2023-04-01 | 2024-03-31 | Approved Maintenance Plan Repaired roads Rehabilitated roads Completed roads projects | N/A
3 | BUILDING CONTROL | Unit incapacity, Poor Feedback/communication with stakeholders, Lack of Resources | Streamline the building plans approval process Set cost reflective building approval tariffs Address building contraventions and enforce the building bylaws. This includes compliance with zoning status. Obtain a functionary from MISA or a shared services option to render land use planning services. | In-house | In-house | MM, Director: Development and Planning | 2023-04-01 | 2024-03-31 | To continuously ensure uniformity and compliance to building regulations and improve on turn- around times for such approval | N/A
4 | WASTE AND REFUSE REMOVAL | Inappropriate vehicles and equipment for refuse removal. Expired license for operating a landfill, | Develop and implement Refuse Removal Management Maintenance and Refurbishment Plan Operationalise the operation and maintenance plan Review tariffs to cost reflective. Promulgate updated by-laws as required. Enforcement of bylaws. Conduct awareness campaigns on illegal dumping and enforce municipal by-laws. Appointment of service providers for as & when contracted services | In-house | In-house | MM, Director: Community Services | 2023-04-01 | 2024-03-31 | Approved Maintenance Plan Updated tariffs, policy and by-laws. Safe and clean environment SLA Concluded | N/A
5 | ELECTRICITY SUPPLY | Outstanding Eskom Account, Distribution Losses. | Timeous payment of Eskom Current Account and Arrear debt payment as per payment plan. Compile and implement Electricity Maintenance and Refurbishment plan Refurbish / upgrade electrical network according to priority implementation programme Review SLA with Eskom to ensure that it adequately address all technical, service delivery and financial matters. Review tariffs and policy. Update. Promulgate updated by-laws as required. | In-house | In-house Approach MISA for capacity support | MM, Director: Technical Services | 2023-04-01 | 2024-03-31 | Approved Maintenance and refurbishment Plan Ensure provision of efficient and sustainable electricity supply to the consumers within the municipality’s licensed areas of supply Signed amended SLA Reliable bulk electricity agreement Enhance revenue collection and sustainable electricity supply | INEP to be fully utilised
6 | RECREATIONAL FACILITIES, LIBRARIES, PARKS AND CEMETERIES | Improved provision of recreational facilities, libraries, parks and cemeteries | Develop and implement Recreational Facilities Maintenance Plan Review the Maintenance and Operation Plan (cost) in order to be effective Refurbish priority facilities Review tariffs and policy. Promulgate updated by-laws as required. Introduce of Cost reflective tariff on all services rendered; Introduction of cost reflective tariffs on (pruning of trees, cleaning of erfs) Review leases for Public Amenities i.e. swimming pool, soccer stadium etc: Leases of public amenities (swimming pool, soccer stadium, outdoor gym) Cemeteries; Verification of the Indigent Register to curb provision of free burial sites to non-indigent residents Library Services; Negotiate with DSRAC with the view of requesting financial funding for library services | In-house | In-house | MM, Director: Community Services | 2023-04-01 | 2024-03-31 | Approved Recreational Facilities Maintenance Plan Approved O&M Plan Rehabilitated facilities Reviews policy, facilities use tariffs Cost reflective tariffs Functional and utilized sport facilities managed by PPP Data Cleansing of the indigent register Funding for Library Services 100% expenditure of capital budget for the project. Completed Sportsfield | N/A
7 | PUBLIC SAFETY, TRAFFIC AND LICENSING | Law enforcement activities is affected by Inadequate equipment. Lack of Human resources Outdated By-Laws. | Law enforcement across divisions Fire, Traffic and Security. Renewal of trading permits | In-house | In-house | MM, Director: Community Services | 2023-04-01 | 2024-03-31 | Intensive Law enforcement activities. Monthly operations. Intensify inspection of trading permits. Compliance | N/A
8 | SPATIAL PLANNING AND HUMAN SETTLEMENTS | Lack of housing development, and bulk infrastructure | Implement the spatial development plan Increase revenue by making land available and attractive to private sector developers. Review development and land use tariffs. Such as rezoning costs. Update where necessary. Promulgate updated by-laws as required. Enforcement of Land Use Scheme and By-law to cub the high number of Illegal land uses Conduct assessments and the alienation and disposal of some of the Council Owned Properties Tribunal Applications; Submit applications to Tribunal and Processing of applications for approval Develop and Implement the 30% Project Sub-contract Policy for to support local companies Review and implement application Fees for land development application Printing of Maps Issue Zoning certificates | In-house | In-house | MM, Director: Planning and development | 2023-04-01 | 2024-03-31 | Spatial development Framework Review of municipal investment property and proposed future uses. Reduced land use contravention Reduced land use contravention Review of municipal investment property and proposed future uses. SPLUMA Meeting Minutes Local Economic Development Policy Tariff of Charges | N/A
9 | FLEET MANAGEMENT | Inadequate fleet to perform municipal functions optimally. | Develop and implement Fleet Management Strategy and Plan Development and implementation of the vehicle maintenance plan Develop and implement a insurance and fuel management policies Develop and implement vehicle replacement plan | In-house | In-house Provincial Support Package | MM, Director: Technical Services, Director: Community Services, Director: Planning and Development | 2023-04-01 | 2024-03-31 | Approved Fleet Management Strategy and Plan and implemented Developed planned service schedule, including costs Controlled and planned servicing and maintenance of vehicles Implemented functional Fleet and Fuel Management System Cost saving in fleet and fuel management Reduced theft and abuse Replacement of redundant/ obsolete fleet Reduced vehicle downtime and increased utilisation/ uptime Modernised and reliable feet | In line with approved Budget and Mobilised Funding
10 | FLEET MANAGEMENT | Inadequate maintenance of municipal fleet | Establish and equip workshop with basic tools and equipment and stock for priority, medium term operations Fleet maintenance team to comply to OHS standards All operable vehicles to be checked for roadworthiness repaired and certified as roadworthy. If unsalvageable then use as scrap parts or auction off vehicle in terms of legislation and policy | In-house | In-house | MM, Director: Technical Services, Director: Community Services, Director: Planning and Development | 2023-04-01 | 2024-03-31 | Functional equipmentx Workshop operating at minimum OHS standards Valid roadworthy certificates for all operable vehicles | N/A
11 | PROJECT MANAGEMENT UNIT(PMU) | Capacitation of the unit to achieve 100% expenditure on all capital execution projects | Development and implementation of the procurement plans | In-house | In-house | MM, Director: Technical Services | 2023-04-01 | 2024-03-31 | Improved forward planning and implementation of projects Improved service delivery | N/A
12 | LANDFILL SITE | Lack of maintenance and operations at landfill sites, Licensing of the existing landfill site, Non-compliance with Environmental Legislations | Approve and Implement Integrated Waste Management Plan Adhere to legislation to become compliant landfill site operator Review tariffs and policy. Promulgate updated by-laws as required. Install weighbridges on landfill sites or use an alternative waste measurement method. Landfill Site Mediation Agreement | In-house | In-house | MM, Director: Technical Services, Director: Community Services, Director: Planning and Development | 2023-04-01 | 2024-03-31 | Approved and implemented Integrated Waste Management Plan Functional Plant and Equipment Updated tariffs, policy and by-laws. Revenue collected in line with usage | N/A
13 | SECURITY SERVICES | Municipal property must be protected from vandalism. | Develop Security Policy that covers internal and outsources security services. Review security strategy to incorporate the guarding of municipal property, staff, customers and equipment. | In-house | In-house | MM, Director: Community Services | 2023-04-01 | 2024-03-31 | Asset Management Policy to include how assets within the municipality are protected. Asset Management Policy to include how assets within the municipality are protected. | N/A
14 | LOCAL ECONOMIC DEVELOPMENT | Inadequate preparation of enabling environment for economic activities and investments, Lack of land for development | Develop LED strategy and implementation plan . | In-house | In-house | MM, Director: Planning and development | 2023-04-01 | 2024-03-31 | LED Strategy Tariff of charges | LED Strategy

## Phase 3 Sustainability
PHASE 3: SUSTAINABILITY
NO | FOCUS AREA | KEY ASSESSMENT FINDING (BASELINE) | KEY ACTIVITIES | RESOURCES REQUIRED | RESOURCES MOBILISED | RESPONSIBLE | START DATE | END DATE | KEY PERFORMANCE INDICATOR | PORTFOLIO OF EVIDENCE | BUDGET PARAMETER/ REVENUE TARGET/ SPENDING LIMIT | MUNICIPAL PROGRESS REPORT
[12 empty] | STEPS TAKEN | PROGRESS MADE | FINANCIAL IMPACT | OTHER NOTEWORTHY DEVELOPMENTS