## RESCUE PHASE 1
PHASE 1: FINANCIAL RESCUE
NO | FOCUS AREA | KEY ASSESSMENT FINDING (BASELINE) | KEY ACTIVITIES | RESOURCES REQUIRED | RESOURCES MOBILISED | RESPONSIBLE | START DATE | END DATE | KEY PERFORMANCE INDICATOR | PORTFOLIO OF EVIDENCE | BUDGET PARAMETER/ REVENUE TARGET/ SPENDING LIMIT | MUNICIPAL PROGRESS REPORT
[12 empty] | STEPS TAKEN | PROGRESS MADE | FINANCIAL IMPACT | OTHER NOTEWORTHY DEVELOPMENTS
PILLAR 1: GOVERNANCE
1 | Governance model ( Council and oversight structures/Committees) | The municipality has an elected Speaker, Acting Executive Mayor and Acting Chief Whip. | Permanent Executive Mayor and Chief Whip to be electing as a court order has been made. | In house | In house, CoGTA NT PT | CM | 01/09/2023 | 31/12/2023 | Improved governance and accountability. Statutory reports submitted timeously. Roles clarified. | Council resolution on the elections | Financial benefits to be achieved through improved operational efficiencies
|  | All section 79 and 80 oversight structures are in place however not functional, after a period of instability experienced by the municipality. Chairperson of MPAC not in place. Terms of reference for the Programming Committee not developed yet. | MPAC chairperson to be elected/ appointed. | In house | Inhouse | HOD: Corporate Services | 01.09.2023 | 31/12/2023 |  | Council resolution. Approved Terms of reference.
|  | The municipality has a manual resolutions register but not being effectively monitored for implementation. | Council resolutions implementation to form part of Executive management for effective monitoring and the status be tabled at Council regularly. | In house | In house | Speaker | 01/09/2023 | Quarterly |  | EMC minutes
|  |  | The FRP must be included as a standard item on the agenda of the Section 79 and 80 committees, as well as all Council meetings. | In house | In house | Speaker | 01/09/2023 | Annually |  | Minutes of meetings
|  | The municipality has one public entity which is 100% owned by the municipality. The SLA with CENTLEC provide for revenue of R 120 million per annum to be transferred to the municipality. Centlec provides in kind services such as MMM's building electricity consumption, street-light electricity consumption, repairs and maintenance, and free basic electricity with a total amount owed by the municipality of R 506 245 572.97 as at 30 April 2023. | Council should urgently review the SLA with Centlec. | In house | In house COGTA | CFO | 01.09.2023 | 31/12/2023 |  | Reviewed SLA
|  |  | The Municipality should recover lost/untransferred revenue from CENTLEC. | In house | In house | CFO | 01.09.2023 | 31/12/2023 | Increased revenue | Revenue recovery plan
|  |  | Implement the resolutions of the Council report on consideration for the sale of business agreement on Centlec. | In house | In house | CM | 01.09.2023 | 31/12/2023 |  | Viability Report
|  |  | Develop a strategic partnerships strategy such as PPP for alternative revenue streams. | In house | In house | CFO | 01.09.2023 | 31/12/2023 |  | Approved Strategic Partnerships Strategy
|  | Disciplinary Board not in place and therefore not functional. | Re-advert to be placed urgently for the appointment of the new Disciplinary Board. | In house | In house | CFO | 01/09/2023 | Monthly | Financial misconduct recorded. | Copy of the advert
|  | Councillors and staff declare their interests in registers but there is no monitoring process of the status of the declarations. | Councillors and staff need to declare their interest annually. | In house | In house | Speaker | 01/09/2023 | Quarterly | Quarterly reports | Process plan for monitoring declarations. Council resolutions of approved reports.
|  | Council does not approve statutory reports timeously in line with the approved MFMA calendar, e.g MPAC report, Annual Report for 2022/23 not yet tabled, budget not yet passed, etc. | Council to consider and approve all all statutory reports in line with the MFMA calendar.
|  |  | Develop and approve an annual Institutional Calander for Council, committees and disciplinary board. | In house | In house | CM | Annually | Annually | Approved Institutional Calander | Approved Institutional Calander
|  |  | Submit to Council a report on Councillors and staff in arears for services rendered on a monthly basis. | In house | In house | CFO | Monthly | Monthly | Monthly Council Report and signed resolution | Monthly Council Report and signed resolution
|  |  | Enter into payment arrangements with Councillors and staff in arears. | In house | In house | CFO | Quaterly | Quaterly | Monthly Council Report and signed resolution | Monthly Council Report and signed resolution
|  |  | Report on arears collected from Councillors and staff on a monthly basis. | In house | In house | CFO | Monthly | Monthly | Monthly Council Report and signed resolution | Monthly Council Report and signed resolution
2 | Political Interference | It is alleged that politicians interfere in the administration and specifically in staff appointments and procurement. There are tensions between Council and senior Management and mutual mistrust exist, whether permanent, acting or deployed officials. | The Speaker must enfore the code of conduct for Councillors on political interferance. | In house | In house, CoGTA NT PT | Speaker | 01/09/2023 | 31/12/2023 | Improved governance and accountability. | Opened criminal cases Escalation report | Financial benefits to be achieved through improved operational efficiencies
|  |  | National Treasury should institute a forensic investigation on all fraud and corruption allegations covering a period of 3 years ending June 2023 in all relevant departments. | Outsourced | National Treasury | National Treasury | 01/09/2023 | 31/12/2023 | Forensic Investigation Report | Forensic Investigation Report
3 | System of Delegations | The system of delegations is outdated and in certain areas not in line with local government recent legislative amendments. | Develop process plan for the development of a corporate system of delegations with clear deliverables and timeframes and identify responsible officials , develop delegations register. | In house | In house | HOD. Corporate Service | 01/09/2023 | 31/12/2023 | Systems of delegations in place | Process plan, Approved Delegations of authority and delegations register. | Financial benefits to be achieved through improved operational efficiencies
|  |  | Approve a reviewed corporate system of delegations. | In house | In house | HOD. Corporate Service | 01/09/2023 | 31/12/2023
|  | There are no updated delegation registers in place. | Sub-delegate powers and functions to Heads of directorate. | In house | In house | HOD. Corporate Service | 01/09/2023 | 31/12/2023 | Enhanced accountability and, checks and balances. Sub-delegations in place Clarified roles | Signed sub-delegations and acknowledgement of receipt
|  | There are no written and signed sub-delegations below the City Manager. | Sub-delegate further to maximise administrative and operational efficiencies. | In house | In house | HOD. Corporate Service | 01/09/2023 | 31/12/2023
|  | The old system of delegations does not incorporate role clarification as required by law and are centralised at the level of heads of departments | Incorporate Role clarification in the system of delegations as required by Systems Act. | In house | In house | HOD. Corporate Service | 01/09/2023 | 31/12/2023 |  | Approved delegations that include role clarification.
|  |  | Conduct training/ workshop to Staff and Councilors on the system of delegations and role clarification through CoGTA, National or Provincial Treasury. Section 119 (1) of the Municipal Systems Act should be included in the training material. | Outsourced | Outsourced | National Treasury | 01/09/2023 | 31/12/2023 |  | Approved training programme, material, attendance register of councillors, training evaluation forms
|  | The City Manager did not delegate the powers and functions related to supply chain management and the establishment of Bid committees in line with statutory requirements. | Review and approve delegations of powers and functions for implementation of supply chain management policy including the establishment of Bid committees. | In house | In house | CM | 01/09/2023 | 31/12/2023 |  | Approved SCM Delegations of authority.
4 | By-laws | Most by-laws are outdated and not recently reviewed. There are no financial By-laws promulgated for the current financial year 2023/24 | Develop and implement a process plan for the review of by-laws. | In house | In house | CM | 01/09/2023 | 31/12/2023 | Enforcement of law | Appproved By-laws | Increased revenue through the enforcement of By-laws
|  | The Municipality does not have an effective reporting structure and system on revenue generated from enforcement of by-laws in place | Develop effective reporting structure system on reporting on revenue generated from enforcement of by-laws. | In house | In house | HOD. Corporate Service | 01.09.2023 | 31/12/2023 | Improved revenue management | Approved By-law revenue reporting structure and system
5 | UIF&W and Consequence Management | UIF&W is huge and increasing. The cumulate balances of UIF&W as at 30 June 2022 are as follows: Unauthorised: R 5.6 Billion. Irregular: R 3.1 Billion. Fruitless and Wasteful: R 240 Million. | Table UIF&W reports quaterly to the Executive Mayor and annual to Council. | In house | In house | CFO | Quarter | Annually | Reduction in historic UIFW expenditure Implementation of consequence management (disciplinary processes, recovery of money, reported criminal cases) | Approved UIF&W report Approved Reduction Plan | Financial benefits to be achieved through improved operational efficiencies
|  |  | Develop and approve a UIF&W expenditure reduction plan. | In house | In house | CFO | Quarter Annaully | Quarter Annually | UIF&W expenditure reduction plan | Quarterly UIF&W expenditure reduction plan
|  | There are no section 32 investigations that have been conducted. The analysis and identification of UIF&W was outsourced but the report is not being used by the municipality due to the irregular appointment of the service provider. | Conduct investigations on all reported allegations of financial misconduct including UIF&W expenditure . | In-house and NT-MF | In-house and NT-MFMA unit | CM | 01/09/2023 | 31/12/2023 | Legislative compliance Consequence management | Approved UIF&W expenditure reduction plan . Written outcome of disciplinary hearings
6 | Risk Management | The Municipality has a council approved Risk Management Policy that include the strategy and implementation plan. A new Risk Management Committee was appointed in March 2023 and was inducted in June 2023. The Municipality has a CRO in place. However, the Municipality does not have a Business Continuity Plan (BCP) in place. | Council must approve an enterprise-wide BCP that will include the ICT BCP. | In house | In house | CM | 01/09/2023 | 31/12/2023 | Monitored risks Approved Risk Management Policy Approved Ant-Corruption Policy | Quarterly risk management reports approved by Administrator. Risk monitoring report. Monthly FRP implementation progress reports Approved Risk Management Policy Approved Ant-Corruption Policy | Financial benefits to be achieved through improved operational efficiencies
Management should submit quarterly reports on implementation of annual risk management plan to Council.
Council to approve the annual Risk Management Documents including the risk register, Anti-corruption Policy etc.
7 | Contract Management | There is no functioning contract management system in place. Not clear where the function should be performed or located. There is no up-to-date contract register. | The Contract Management Committee to sit on a monthly basis. | In house | In house | CFO | 01/09/2023 | 31/12/2023 | Contract Management Committee and Online Document Management System | Contract Management Committe ToRs and minutes. Approved Structural amendments. Online document management system. Workshop programme and attendance registers. | Financial benefits to be achieved through improved operational efficiencies
|  |  | Develop a contract management system. | In house | In house | CFO | 01/09/2023 | 31/12/2023 | Contract Management System | Contract Management System | Reduction in contracted services
|  | The municipality has contracted services with service providers where there is staff employed to do the same work. Some contracts have not been signed by the previous MM. | Review existing contracts against the organisational structure and staff to determine duplication of services. | In house | In house | CFO | 01/09/2023 | 31/12/2023 | Improved contract management and accountability. | Review and investigation reports. | Financial benefits to be achieved through improved operational efficiencies
Terminate all irregular contracts.
|  | The municipality has evergreen contracts that are automatically renewed without going back to the market. These include contracts that have been in place since 1996, 2010 and 2013 indefinitely, and the value and impact of these contracts has not been established. | Identify and review Evergreen contracts. | In house | In house | CFO | 01/09/2023 | 31/12/2023 | List of Evergreen Contracts | List of Evergreen Contracts | Financial benefits to be achieved through improved operational efficiencies
|  | Contract management function is currently misplaced in Legal Services. | Segregate contract management between Legal services and SCM. | In house | In house | HOD: CORPORATE SERVICES | 01/09/2023 | 31/12/2023 | Segregate contract management between Legal services and SCM | Approved segregation of functions
|  | Reporting process in line withsection 116 of the MFMA is not adequately conducted. | Conduct monthly monitoring of contracts in compliance with section 116 of the MFMA . | In house | In house | HOD: CORPORATE SERVICES | 01/09/2023 | 31/12/2023 | Reviewed section 116 reporting process | Reviewed section 116 reporting process.
|  |  | Identify and list goods and services required on an on-going basis. | [5 empty] | List of goods and services required | List of goods and services required
|  |  | Determane the method of procurement on those goods and services required on an on-going basis to procure on a long-term contract. | [5 empty] | Long-term procurement contracts | Long-term procurement contracts
8 | Litigation and Contingent Liability | The legal department is not functioning optimally and seemed to fail in its function to mitigate risk to the Municipality | Conduct a legal assessment on reasonable prospects of success on all pending litigation matters. | In-house, PT | In-house, PT | HOD: Corporate Services | 01/09/2023 | 31/12/2023 | Improved legal support. | Process plan and assessment report. | Financial benefits to be achieved through improved operational efficiencies
It seems that the legal department is not consulted as it should that leads to poor contracting, that includes procurement, and management, high litigation instances, policies not reviewed as required, little to no consequence management for employees implicated in irregular, unauthorised and fruitless expenditure and implementation of by-laws.
Contingent liabilities as at 30 June 2022 was R 83.9 million. Legal fees budgeted for 2021/22 was R 26.7 million with actual legal fees incurred at R 52.7 million.
Poor contract management has led to high number of litigations from service providers due to the flawed procurement process, non-payment of service providers, political instability and politicized administration that leads to litigations.
|  | The municipality has an updated litigation register but the tracking of court matters is not efficient. | Monthly update of the litigation register. | In house | In house | HOD: Corporate Support Services | 01.09.2023 | Monthly | Improved litigation management | Litigation tracking system
|  | The municipality has a legal support protocols in the form of standard operating procedures. However, there is no adequate capacity to provide adequate legal support. | Review legal Services organisational structure to ensure appropriate provision of posts for effective legal support. | In house | In house | HOD: Corporate Support Services | 01.09.2023 | 31/12/2023 | Improved legal support. | Approved organisational structure amendments
|  | The municipality has a legitimate appointed panel of attorneys procured through an open tender process which ends in March 2023. However, they have taken the municipality to court due to non-payment caused by poor budgeting. | Budget for litigation/legal costs should be reviewed in line with municipality’s operational needs. | In house | In house | HOD: Corporate Services | 01/09/2023 | 31/12/2023 | Improved legal support. | Approved adjusted budget, ToRs for panel of attorneys.
|  |  | Develop and approve a fee structure for the new term of panel of attorneys. | [5 empty] | Approved fee structure | Approved fee structure
|  |  | Appointment of a panel of attorneys through an open tender process. | [5 empty] | New legal panel appointment | New legal panel appointment
|  |  | Conduct a diagnostic analysis on root causes of all pending litigation matters. | [5 empty] | Diagnostic Analysis Report | Diagnostic Analysis Report
9 | Information and Communication Technology | The ICT department has had instability and lack of leadership as there has been no Chief Technology Officer (CTO) since 2019 and no permanent managers since 2011. | Develop and implement an Integrated ICT Strategy. | In house | In house | HOD: Corporate Services | 01/09/2023 | 31/12/2023 | Improved ICT governane compliance | Approved appointments | Financial benefits to be achieved through improved operational efficiencies
|  | There is therefore no ICT strategy or centralisation and oversight of ICT. As a result, key systems are not in place such as document management system, contract management system and time and attendance. | Develop and implement a clearly defined and resourced ICT Plan. | In house | In house | ICT Manager | 01/09/2023 | 31/12/2023 |  | Approved ICT Strategy and resourced ICT Plan
|  | Municipality does not have a list of licences and software currently in place and are paying for licences that are not being utilised as indicated by their excessive software license fees. | Review all licenses and their level of utilisation and terminate those under or unutilized to save costs. | In house | In house | ICT Manager | 01/09/2023 | 31/12/2023 | Improved records management | Review report
|  |  | Conduct training for maximum use of underutilised software. | [6 empty] | Training programme, attendance registers.
|  | The internal audit department does not have the resources and skills to carry out ICT audits. | Review internal audit capacity on ICT. | [6 empty] | Review report.
|  | Automated functions such as leave and overtime are not being optimally utilised. | Implement all automated functions. | In house | In house | ICT Manager | 01.09.2023 | Ongoing | Efficient systems utitalisation | ICT automation optimization strategy
10 | Audit action plans (internal and external) | The Municipality received qualified audit outcomes for 2017/18 and 2018/19, improved to unqualified for 2019/20 and 2020/21 but regressed to qualified audit outcomes in the 2021/22. The past five financial years show stagnation in this regard. The Post Audit Action plan for the previous AG outcomes has not been tabled before Council for approval. The Action plan was discussed at the Mayoral Committee and EMT. | Develop and implement the post audit action plan. | In-house | In-house | CM | 01/09/2023 | Ongoing | Improved audit outcomes and/reduction of audit findings | Validated quarterly progress reports on the implementation of audit action plan and audit file | Financial benefits to be achieved through improved operational efficiencies
|  |  | Quarterly progress reports on the implementation of the post audit action plan to the audit committee and Council. | [5 empty] | Quarterly progress report | Quarterly progress report
11 | Internal Audit | The Municipality’s Internal Audit function is in place and functional. However, recommendations of the Audit Committee have been partially implemented by the Municipality. The term of the current Audit Committee has ended on 31 May 2023 and Council is in the process of finalising the appointment of the new members. | Internal Audit should provide support and monitor the implementation of Audit Committee recommendations by management. | In house | In house | CFO | 01/09/2023 | 31/12/2023 | Implementation of Audit Committee recommendations Appointing the new Audit Committee | Updated register of implementation of recommendations | Financial benefits to be achieved through improved operational efficiencies
Appoint members of the Audit Committee.
|  | Labour has made allegations of fraud and corruption within the municipality. | Alleged fraud and corruption should be investigated. | In house | In house | CM | 01.09.2023 | 31/12/2023 | Improved consequence management | Investigation report
12 | Immovable Property | The Municipality has an approved land alienation policy. Most lease agreements are not updated as most leases are now on a month-to-month basis. It could not be established whether the municipality collects market related rentals from Council leased property based on private property valuations. | Audit of all council owned immovable properties. | In house | In house | CM | 01/09/2023 | 31/12/2023 | Audit report on Council owned Immovable property | Audit report on Council owned Immovable property | Financial benefits to be achieved through improved operational efficiencies
|  |  | Review outdated leases for renewal. | [5 empty] | Reviewed lease agreements | Reviewed lease agreements
|  |  | Conduct a reconciliation between council resolutions on land alienation and the deeds office records. | [5 empty] | Report on council resolution on land alienation compared to the deeds office | Report on council resolution on land alienation compared to the deeds office
13 | Powers and functions | The municipality has not conducted a cost-benefit analysis of unfunded and under-funded mandates that it is implementing. | Conduct a cost-benefit analysis of existing unfunded and under-funded mandates with options to renegotiate or terminate. | In house | In house | CFO | 01.09.2023 | 31/12/2023 | Improved cost management | Cost-benefit analysis report | Financial benefits to be achieved through improved operational efficiencies
PILLAR 2: INSTITUTIONAL
1 | Operating Model | The municipality does not have an Operating Model as defined by the Municipal Staff Regulations. | Develop an Operating Model in line with the Municipal Staff Regulations including a cost benefit analysis on the use of contracted services vs internal resourcing. | In house | In house | HOD: Corporate Services | 01/09/2023 | 31/12/2023 | Viable Operating model | Approved Operating Model
2 | Organistional Structure | MMM does not have a well-defined and approved organisational structure to support the functioning of the Municipality. The process for the review of the organisational structure has been completed at the macro level but not at the other levels. | Finalise the review of the organisational structure in line with the Operating Model, current municipal budget & service delivery demands. | In-House | In house | HOD: Corporate Services | 01/09/2023 | 31/12/2023 | Organisational Structure aligned to the Operatig model | Approved reviewed Organisational structure | Financial benefits to be achieved through improved operational efficiencies
|  |  | Current staff below macro-structure to be considered not placed until a competitive placement process has been undertaken. | [6 empty] | Approved placement plan
|  | The whole Payroll function is incorrectly located in HR with no segregation of functions . | The Payroll function to be split between Finance and HR department with proper segregation of functions and map the processes for HR and Finance. | In house | In house | HOD: Corporate Services | 01.09.2023 | 31/12/2023 |  | Approved organisational structure amendments
|  | Inadequate integration of erstwhile municipalities into the Mangaung Metro municipality. | Develop a Placement Policy for approval for the process to place employees appropriately for full utilization, in consultation with Labour. | In house | In house | HOD: Corporate Services | 01/09/2023 | 31/12/2023 | Appropriately placed staff | Approved Placement Policy
|  | The municipality is still using an outdated Job Evaluation system | Initiate the process of migrating TASK Job Evaluation System | In house | In house | HOD: Corporate Services | 01/09/2023 | 31/12/2023 | Efficient Job Evaluation | TASK Job evaluation Reports
3 | Leadership and management | There is instability at MMM as the City Manager and Section 56 Appointments remain vacant or are filled with acting appointments. | Develop a Recruitment plan for the urgent filling CM and Section 56 Managers | In house | In house | HOD: Corporate Services | 01/09/2023 | 31/12/2023 | Improved leadership and operational management | Approved recruitment plan and appointments | Financial benefits to be achieved through improved operational efficiencies
4 | Employee Costs | Escalating employee costs due to unmanaged overtime, bloated salaries and acting allowances. The overspending on overtime costs and acting allowances resulted in an unfavourable variance of R105.808 million (5%) on the year-to-date adjusted budget. The overspending on overtime to date is R96. 630 million (Budget R90.709 million vs Actual R187.340) which resulted in unauthorised expenditure in most of the votes. Employee costs are currently 24.71% of the operating expenditure which is below the norm of 25%-40%. The low % could point to a high level of critical vacancies and general understaffing. | Conduct a Salaries benchmarking exercise to ensure employees are paid according to the correct grading. | In-House | In house | HOD: Corporate Services | 01/09/2023 | 31/12/2023 | Appropriately graded salaries | Benchmarking outcomes report | Achieve expenditure reduction financial targets per FRP parameters
|  |  | Develop a remuneration strategy based on affordability and LLF consultation. | In house | In house | HOD: Corporate Services | 01/09/2023 | 31/12/2023 |  | Approved Remuneration Strategy , LLF Consultation Report
|  |  | Job evaluation process to be undertaken | In-house | In house COGTA | HOD: Corporate Services | 01/09/2023 | 31/12/2023 |  | Job Evaluation Reports
|  |  | Consider the implementation of a shift work system, which will enable MMM on tracking work and service delivery. | In-house | In-house | HOD: Corporate Services | 01/09/2023 | 31/12/2023 | Shift work system | Shift work system | Reduction in overtime.
5 | Management of overtime | The overtime incurred for the 2021/22 FY is R209 510 763 (2021: R210 741 439; 2020:194 443 080) which is excessive and resulted in overspending and unauthorsed expenditure. | Conduct regular review and enforcement overtime policy in line with the Basic Conditions of Employment Act including adequate supervision. | In-House | In house | HOD: Corporate Services | 01/09/2023 | 31/12/2013 | Reduced Overtime costs | Overtime review report | Achieve expenditure reduction financial targets per FRP parameters
|  |  | Conduct quarterly monitoring of the implementation of the Overtime Policy by department. | In house | In house | HOD: Corporate Services | 01/09/2023 | Quarterly |  | Quarterly overtime monitoring reports
|  |  | Perform an audit of the overtime per each department. | In house | In house | CAE | 01/09/2023 | 31/12/2023 |  | Overtime internal audit report
|  |  | Review the system description relating to overtime and identify control issues. | In house | In house | CIO | 01/09/2023 | 31/12/2023 |  | System review report
6 | Performance management | Non- adhereance to performance management. Performance agreements are not in place and performance management not cascaded to lower level staff. No consequence management can be implemented. There is no orginisational performance framework. | Develop a functioning performance management system and implement consequence management for non-performance. Implementation of performance management agreements. | In-House | In house | HOD: Corporate Services | 01/09/2023 | 31/12/2023 | Improved performance management | Approved Organisational Review Report, Signed Performance Agreements. | In line with the approved budget and the funding plan.
Facilitate the deveoplment of a orginasational performance framework and the performance reporting framework.
Employee performance should align to orginisation performance.
Develop process plan and policy to Cascade Performance to levels below Senior Managers.
|  | No job descriptions and bloated salaries. | Conduct skills audit and define job descriptions. | [5 empty] | Clear roles and responsibilities. | Skill Audit Report Job descriptions
|  | Reported performance information is not reliable. | Develop performance information policy and procedures to include data collection tools and processes. | In house | In house | Head: PMS | 01/09/2023 | 31/12/2023 | Improved organisational performance management and reporting | Approved Performance Information Policy and procedures
7 | Filling of critical positions | There are delays in the filling of critical vacant posts with people that have the appropriate experience, skills and qualifications. There is a high vacancy rate of 50.58% in relation to all approved positions on the Staff Establishment . | Organisational restructuring by assessing the critical posts required to operate efficiently and effectively and staff excess to requirements of the Municipality Develop a Recruitment plan. | In-House | In-house, CoGTA and NT-MFMA unit | HOD: Corporate Service | 01.09.2023 | 31/12/2023 | Capacitated municipality | Organisational restructuring report, Recruitment plan | Only use mobilised resources.
|  |  | Develop an HR strategy and Plan that guides recruitment, placement of staff, retention of staff, performance management and disciplinary processes. |  |  |  | 01/09/2023 | 31/12/2023 |  | Approved HR Strategy and Plan
|  | The moratorium of the filling of posts has been lifted. | The lifted moratorium on filling of posts should ensure that it is alignedent with the budget parameters. | In house | In house | HOD: Corporate Service | 01/09/2023 | 31/12/2023 | Appropriately placed staff | Staffing Report.
8 | Disciplinary Board | The disciplinary board is not functional, and there isn't an updated register. | Establish a functioning disciplinary board. | In-house | In-house | HOD: Corporate Service | 01/09/2023 | 31/12/2023 | Functioning Disciplinary Board | Functioning Disciplinary Board | Financial benefits to be achieved through improved operational efficiencies
|  |  | Develop and regularly update the disciplinary case management register. | [5 empty] | Approved disciplinary case management register | Approved disciplinary case management register
9 | Consequence Management | Lack of accountability and consequence management in the municipality impacts service delivery and municipal finance management. | Develop and implement of Consequence Management Policy. | In-house | In-house | HOD: Corporate Service | 01/09/2023 | 31/12/2023 | Approved Consequence management policy | Financial assessment reports | Financial benefits to be achieved through improved operational efficiencies
|  |  | Conduct Workshops to communicate the Code of Conduct for staff and Councillors. | [6 empty] | Attendance register for workshop
|  |  | Develop process to report and monitor cases . | [6 empty] | Approved Consequence management SOPs
10 | Physical Verification of staff and qualifications | Existence of employees unaccounted for (‘ghost workers’). | Conduct an employee head count and identify any ghost employees or employee’s surplus to the organisation, on the payroll. | In-house | In-house | HOD: Corporate Service | 01/09/2023 | 31/12/2023 | Completeness of employee related costs | Employee Verification Report | Reduction in employee cost
|  |  | Employee disclosure in terms of Municipal staff regulations. | [6 empty] | Disclosure of all staff in terms of Municipal staff regulations
Employees holding political offices should declare their status, either resign or make a choice as to where they belong.
|  |  | Implement an attendance register be it electronic or manual. | [6 empty] | Daily attendacne register
11 | Records Management | Poor record keeping due to decentralisation of records management and limited capacity. Missing documents. No records disposal being undertaken. Loss of municipality records. | Develop a file plan in accordance with the National and Provincial Archives Services guidelines. | In-house | In-house | HOD: Corporate Service | 01/09/2023 | 31/12/2023 | Improved records management. Improved audit outcomes. | Approved File Plan | Financial benefits to be achieved through improved operational efficiencies
Provide Training for all staff on importance of document management and POPIA act.
Develop a Records Centralisation process plan for implementation.
Implement a records system that is compliant with National Archives and National Treasury.
12 | Key HR Policies | Policies are outdated and last reviewed during 2017 and there is no clarity on who is responsible for drafting and reviewing policies. | Develop a process plan to review outdated policies and develop policies not in place. | In-House | In house | HOD: Corporate Service | 01.09.2023 | 31/12/2023 | Improved policy management. Legislative compliance | Policy review and development process plan. Approved policies | Financial benefits to be achieved through improved operational efficiencies
|  | Poorly capacitated or lack of competence in the HR department. | Conduct Competency audit on HR department. | In house | In house | HOD: Corporate Service | 01.09.2023 | 31/12/2023 | Adequately capacited an competent HR department | HR Competency Audit Report
13 | Change Management | Change Management is not implemented. | Sensitise employees and organised labour about the current financial state and the introduction of the FRP. | In-house | Director Corporate Services NT-MFRS | HOD: Corporate Service | 01/09/2023 | 31/12/2023 | Achieved buy-in and support/ Set tone for change. Staff morale boosted. Enhanced service delivery & performance. Increased productivity to support Revenue Management operations. | Attendance Register | Financial benefits to be achieved through improved operational efficiencies
|  |  | Undertake a diagnostic process (climate survey) to determine the level of staff morale and satisfaction. | [6 empty] | Completed Employee satisfaction Survey Questions and Report
|  |  | Develop a change management strategy and NCR and HODs to put an effort to drive change management in the municipality. | [6 empty] | Change Manegement Strategy Council resolution
PILLAR THREE: FINANCIAL MANAGEMENT
1 | Funded Budget and Budget Spending Limits | During the 2020/21 and 2021/22 financial years, MMM budgeted surpluses of R 1,035 billion (2020/21) and R 622,7 million (2021/22). The financial results for the two years reflected deficits of R 20,2 million (2020/21) and a deficit of R 872,7 million (2021/22) which clearly indicate that the budgets were not funded. Poor budgeting techniques and insufficient provision for the impairment of bad debt are the main contributors. In 2021/22 in respect of impairment of bad debts R933.4 million was budgeted and R1.8 billion had to be provided for. MMM had audited deficits for the past three financial years, and budget for surpluses for the MTREF period, which are not cash backed. The analysis of the operating surplus / (deficit) by service indicates that there is a disconnect between the budget and the historical audited results. MMM experienced significant losses since 2018/19 in the non-trading side of the business (General) and were unable to offset these losses against the barely profitable trading services. These losses have been significantly reduced in the MTREF period 2023 – 2025. With further analysis it was identified that the reason for the improvement in the budget is not with unrealistic increases in operating revenue (2022/23: 5%; 2023/24: 8%; and 2024/25: 6%) but rather a 15% reduction in operating expenditure for 2022/23 and 5% and 4% increases in 2023/24 and 2024/25 respectively. Whether this is achievable is questionable based on historical trends. | Prepare, approve, and implement a Budget Funding Plan for the MTREF period linked to the FRP strategies and financial targets (NT Support). Progress must be reported monthly and include targets as KPIs in performance plans. | In-house | LGBA | CFO | 01/09/2023 | 31/12/2023 | 3-Year Budget Funding Plan Monthly BFP Progress Reports Credible 2023/24 MTREF Budget Plan for phasing in of cost-reflective tariffs | Approved 2023/24 MTREF Budget Approved Budget Funding Plan (BFP) BFP Progress Reports Cost-reflective tariff strategy | 100% adherence to approved 3-Year Budget Funding Plan FRP MTREF Financial Targets Target cash flow improvement per annum (in line with FRP targets)
Accurate budgeting for linked to cash collection.
Provide realistic allocations for the provision for debt impairment.
Ensure cost reflective tariffs and scrutinise expenditure for unnecessary expenditure.
Implement accurate budgeting for non-cash items to prevent unauthorised expenditure.
Projected revenue should consider the low historical and future collection rates and use a probabilistic method of projecting for revenue.
Interest on debtors should only be charged on recoverable debts and review the allocation methodology. When the payment is received on outstanding amounts the allocation must prioritise the interest.
Track the expenses not in accordance with the budget and the votes for the past three years, establish a statistical relation with other elements of financials and revise the budget parameters for the expenses using the historical audited expenses, with inflation adjustment, as a base for forecasting.
Undertake a line item analysis of all budget line items to ensure that a realistic cash backed budget is approved.
2 | Funded Budget Status – Capital Budget | The capital budgets for 2020/21 and 2021/22 were only 80.6% and 46.23% spent respectively. This is because of poor cash flow and planning, as well as issues resulting from their poor supply chain management processes. As at 30 June 2022 cash on hand was R728.3 million with liabilities for payables and unspent conditional grants of R2.6 billion. There was an underspend of capital budget for each category of service lines except for Roads Infrastructure, which validates the point of poor cashflow and non-credible budgeting techniques. A high reliance was placed on grant funding to fund capital expenditure during the 2020/21 and 2021/2022 financial years. Compared to the budget MMM is relying on own sources (internally generated funds and loans) to fund planned capital expenditure. This is not realistic due to the current solvency and cash flow constraints. Capital expenditure should therefore be reprioritised within its spending capacity and cashflows. | Compile credible and cash-backed capital budgets linked to the IDP’s capital project priorities. Compile realistic and credible cashflow budgeting that accounts for all outstanding payments and monthly payments of conditional grants. | In-house | CFO with NT Oversight | CFO | 01/09/2023 | 31/12/2023 | 3-Year Budget Funding Plan Monthly BFP Progress Reports Credible 2023/24 MTREF Budget Plan for phasing in of cost-reflective tariffs | Approved 2023/24 MTREF Budget Approved Budget Funding Plan (BFP) BFP Progress Reports Cost-reflective tariff strategy | 100% adherence to approved 3-Year Budget Funding Plan FRP MTREF Financial Targets Target cash flow improvement per annum (in line with FRP targets)
Implement the approved procurement plan on capital projects. Monitoring and tracking project implementation plans (PIP).
Consequence management be implemented where there is evidence of non performance .
Ringfencing and monitoring of unspent conditional grants. Conditional grants must be cash backed not utilized for operating needs.
Provide monthly progress reports detailing the implementation of both the procurement plan and project implementation plans. .
3 | Revenue Management | The total outstanding gross consumer receivables from exchange transactions was R 6,690,341,584 with the total allowance for impairment at R 5,309,741,295 as at 30 June 2022 which is 79% of outstanding debt. The annual collection rate for the three financial years under review were 83.12% (2019/20), 81.16% (2020/21) and 79.44% (2021/22). The norm is 95%. The inability to collect revenue and thereby convert revenue to cash is contributing the cash flow challenges being experienced by the Municipality. The calculated impact of the low collection ratio on cash flow for MMM indicate R914 million lost through poor collections in 2021/22 which equates to 66% of total revenue generated through property rates. Critical vacant posts are not filled. Broken meters not being fixed. Billing is inaccurate and not timeously sent out. The non-implementation of revenue enhancement measures. Inability to perform a debt collection drive as MMM can’t utilise power-cuts for collection of other outstanding service charges owned by consumers. | Perform a thorough and comprehensive assessment of irrecoverable debts, along with an in-depth analysis of debtor profiling. Following the assessment's results, provide recommendations for the write-off of irrecoverable debts in accordance with the approved credit control and debt collection policy. | In-house | CFO | CFO | 01/09/2023 | 31/12/2023 | Increased own revenue Increased collection rate | Monthly reconciliations VR reconciliation S71 Reports | Per set revenue targets
Implement revenue enhancement initiatives including robust billing, collection, and credit control procedures that must be adhered to.
Fill critical vacancies and ensure that the revenue value chain activities are streamlined.
Conducting quarterly VR reconciliation with the billing system to improve the revenue on property rates. Metering (verification, auditing, and consistent reading of meters and addressing cstomer queries.
The previous cost of supply studies must be updated, and tariffs structures must be applied and implemented and for electricity NERSA’s approval.
Implement aggressive debt collection mechanisms by taking legal action.
Implement credit control on government departments owing the municipality and enter into the payment terms. If that fails seek Provincial Treasury intervention.
Prioritise the finalisation of the SLA with Centlec.
MMM and Centlec need to combine all Municipal services on one invoice.
Implement and update standard operating procedures for debtors’ management and training of internal staff.
Implement integrated billing system for the consumers to receive on account.
Engage debtors to agree on payment arrangements.
4 | Cost-reflective Tariffs – Water and Electricity Services | The deficits for the 2020/21 and 2021/22 financial years show that cost reflective tariffs have not been set which indicates bad budgeting processes. The cost of sales of water exceeds the selling price, which is a direct result in losses. This is an indication that the tariffs charged are not cost reflective. Forecasted water and electricity tariffs are set without considering the growth rate in tariffs set by Eskom and Bloem Water. | Conduct a cost of supply study reflective and introduce cost reflective tariffs considering affordability of consumers. | In-house | In-house | CFO | 01/09/2023 | 31/12/2023 | Cost-reflective tariffs Cost-of-Supply Studies Trading Services Surpluses | Cost-of-Supply Reports Tariff Structures | Inrease in Revenue, based on the revised tariffs
Perform cost-volume profit analysis before setting the base tariff for water electricity.
Align the forecasted tariffs with the rate of growth of tariffs forecasted by Bloem Water for the MTREF cycle.
Negotiations should be held with Bloem Water on bulk tariffs .
Forecast tariffs that align with the rate of growth of tariffs forecasted by ESKOM.
5 | Indigent Management | The indigent policy was reviewed during June 2022 however not yet approved and adopted. It has 52 925 active accounts and 1 261 inactive accounts. The indigent register is not updated and reviewed on a regular basis, that can lead to cash leakage and misalignment with the equitable share allocation. Revenue billing and collection targets will not be reached as customers may inappropriately receive free basic services. Revenue Loss. Indigent register not credible. | Report to council on mobilisation programme for registration of Indigents. | In-house | In-house | CFO | 01/09/2023 | 31/12/2023 | Updated Indigent Management Policy Complete Indigent Register Adjusted Debtors Book | Indigent Management Policy Updated Indigent Register | Reduction in expenditure from curbing the supply of services to non-indigents
A quantitative Cost Benefit Analysis should be carried out to determine the most financially optimal option for the verification of indigent household. This is essentially an evaluation of manual verification compared to obtaining a system.
Updating and cleansing of data on the system to provide correct details of customers.
Review of the data captured on the system by senior personnel for accuracy and completeness.
Correction of accounts on a monthly basis.
6 | Supply Chain Management Compliance and Value for Money Procurement | Unspent conditional grants as at 30 June 2022 total R571.0 million. There is insufficient cash on hand to cover payables and unspent conditional grants hence underspending on the capital budget. This is an indication that conditional grants have been spent on operating expenditure. Insufficient financial and project management. None performance of demand management before tenders are advertised and contracts entered into resulting in over-payment on contractors. Contracts entered into without due dates. As at 30 June 2022 MMM has already committed R 258 million on capital projects which they have not yet provided funding for. High unauthorised, irregular and fruitless and wasteful expenditure (UIF&W) is disclosed in the financial statements. As at 30 June 2022 the situation is as follows: Unauthorised: R 5.6 billion. Irregular: R 3.1 billion. Fruitless and Wasteful: R 240 million. There was an increase in UIF&W of R 1,7 billion (24%) from the 2020/21 to the 2021/22 financial year. Capital projects and operating services provided by contractors are not monitored. SCM Policy not adhered to. Disregard for SCM policy and regulations. | UIF&W expenditure to be interrogated with reasons therefore and to be submitted to Council for their decision on what action should be taken based on management’s recommendations. Institute legal action and consequence management based on the outcomes of the investigations. | In-house | In-house | CFO | 01/09/2023 | 31/12/2023 | SCM Policy SOPs UIF&W Investigation Consequence Management Disciplinary Board PMU Office | SCM Policy SOPs approved and implemented Functioning Disciplinary Board Functioning PMU Office | Reduction in UIF&W based on FRP targets
Develop and approve SOP's for SCM.
Adhere to SCM Policy and Regulations and report irregularies to council for early intervention.
Update the contract register monthly and report irregular expenditures for early investigation and possible termination.
MMM should establish a Project Management Office to ensure that contract management and value for money monitoring are affected.
Provincial or National Treasury to provide regular SCM regulations training to the SCM staff.
7 | Debtors Management | Inefficient and ineffective internal controls. Disruptions on implementation of credit control. Reconciliations not performed monthly. Category of Debtors’ Residential and Sundry R 4,444,074,799 (66%) Business / Commercial R 901,624,988 (14%) National and Provincial Government R 1,344,641,726 (20%) | Ensure that the remote offices are fully operational, Making the payment for services easier for the clients e.g. satellite offices in outlying areas, community halls, etc. | In-house | In-house | CFO | 01/09/2023 | 31/01/2023 | Appointment of Debt Collection Company Reduction in Government Debt Write off Bad Debt According to the Policy Key Customer Engagements SOP’s for Debtor Management | Appointment of Debt Collection Company Reduction in Government Debt Write off Bad Debt According to the Policy Key Customer Engagements SOP’s for Debtor Management | Reduction in outstanding Debtors.
Table Write-off of bad debts as per the approved credit control and debt collection policy.
Implement aggressive debt collection mechanisms by taking legal action.
Contact government departments that owe the municipality and establish the payment terms. If that fails seek Provincial Treasury intervention and/or cut off services.
Development of key customer engagements (quarterly) and relationship building.
Implement and update standard operating procedures for debtors’ management and training of internal staff.
Stratify debtors into different buckets based on the expected recoverability.
8 | Cost Containment and Realistic Cash Flow Management | The cash/ cost coverage ratio for 2021/22 was 0.31 months (2020/21: 0.36 months) when the norm is 1 to 3 months. The Municipality is not able to pay its short-term obligations as they fall due. Poor debtors’ collection rate which is the reason for the poor payment rate of MMM creditors. Lack of accountability and clear roles and responsibilities. Excessive expenditure with no system of control. Cost containment targets not included in performance contracts. Tariffs are not cost reflective. | Revise the Cost containment Policy in line with NT Municipal Cost Containment Regulations (2019). | In-house | In-house | CFO | 01/09/2023 | 31/01/2024 | Revised Cost containment Policy Cashflow Committee Adoption of a Cash Management System Inclusion of Cost Containment in Performance Agreements Development of a System of Expenditure Control | Revised Cost containment Policy Cashflow Committee Adoption of a Cash Management System Inclusion of Cost Containment in Performance Agreements Development of a System of Expenditure Control | Cash Coverage: 1.5 Month Improved Revenue Reduction in Expenditure
Implement the approved Cost Containment Policy.
Establishment and Weekly meetings of the Cashflow management committee.
Implement an active cash management system , forecasts, and actuals to be reported to the cash flow management committee.
Include cost containment targets in performance contracts.
Implement a system of expenditure control where no expenditure/ order is authorised unless it is provided for in the cash flow management sytem.
9 | Revenue Raising Measures | MMM is not optimising alternative revenue raising measures. | Conduct an audit on all Municipal owned billboards and facilities that can generate revenue. Implement by-laws and charge penalties where there is transgression. Implement billing at the landfill sites once the weighbridges are operational. | In-house | In-house | CFO | 01/09/2023 | 31/01/2023 | Increased revenue | Audit outcome report | Inrease in Revenues
10 | Creditor Management | A review of the amounts owed by the Municipality reflected the following: Creditors as at 30 June 2022 is R 2,4 billion. Creditors have increased by R 216.3 million year on year, between June 2021 and June 2022. 29% of the amounts owed by MMM relates to bulk water purchases with Bloem Water. Not performing creditors reconciliations. The entity defaulted on the payment of suppliers within 30 days. The average term of payment of trade creditors during 2021/22 were 115 days, (2021: 131 days). | Pay new creditors within 30 days and design a tool for monitoring of the payment and obtain CFO and CM sign off of the tool. | In-house | In-house | CFO | 01/09/2023 | 31/01/2023 | MFMA 30-day Payment Compliance Renegotiated Payment Terms Data Cleansing Bloem Water Bulk Supply Tariff Review Creditor Reconciliation | MFMA 30-day Payment Compliance Renegotiated Payment Terms Data Cleansing Bloem Water Bulk Supply Tariff Review Creditor Reconciliation | 100% adherence to payment arrangements Achieve expenditure financial targets per BFP parameters
Renegotiating parts of amounts owed such as penalties relating to Eskom.
Data cleansing should also be implemented for creditor information.
Creditor reconciliations should be performed weekly and reconciling items and disputed invoices must be resolved promptly.
Review the SLA with Bloem Water and re-negotiate the bulk supply tariffs.
11 | Financial Control Environment | The 2021/22 financial statements submitted were not prepared in all material respects in accordance with the requirements of Section 122(1) of the MFMA. There were material uncorrected misstatements. Qualified audit opinion. There were also material restated figures in the 2019/20 and 2020/21 AFS. High reliance on consultants for assistance in the preparation of the AFS. mSCOA strings are only 85 percent compliant. | Interim AFS should be prepared and assessed to form the base of the year-end AFS preparation. | In-house | In-house | CFO | 01/09/2023 | 31/12/2023 | Reviewed SOP's adopted Record Management Procedure Manual Complete Audit Files Reviewed Audit Action Plan mSCOA Training | Adopted SOP’s Record Management Procedure Manual Complete Audit File mSCOA Training Attendance Register | Training expense based on budget allocation
Management should ensure that there is proper record keeping, sufficient staff members assisting with the requested information by the auditors and should submit the information timeously. This will speed up the audit and it will result in reduced audit cost for the Municipality.
Review the progress of the audit action plan immediately after the issue of the audit report, provide practical action plan and track progress thereof.
Training of internal audit on the adequate review of AFS and before submission to the AG.
Review and update the mSCOA implementation strategy.
Training of finance staff regarding mSCOA.
12 | Customer Care Services | Inadequate Centralised Customer Care Call Centre. Inadequate customer turnaround times in addressing queries | Review of customer care technology. Service delivery standards with turn around times. | In house | In house | CFO | 01/09/2023 | 31/12/2023 | Report on service standards Operational CRM | Report on service standards Operational CRM
13 | Debt Restructuring | Escalating ESKOM debt. | Apply for MFMA Circular No. 124 – Municipal Debt Relief through National Treasury. | In house | In house | CFO | Immidiate | 12 Months | Monthly Provincial Treasury certification of Municipal compliance | Monthly Provincial Treasury certification of Municipal compliance | Municipal Eskom Debt Relief as prescribed by Circular No. 124
PILLAR FOUR: SERVICE DELIVERY
1 | Strategic positions | Key managerial technical positions as identified in the approved organogram must be filled to capacity MMM to ensure service delivery. | Appointment of permanent senior management position in line with MFMA regulations to enable service delivery. | In-house | In-house | HOD: Corporate Services | 01/09/2023 | 31/12/2023 | Filling of critical vacant positions | Critical vacant positions are filled | Per the BFP
2 | Asset Management | Asset register was found incomplete, inaccurate and not complaint with GRAP and mSOCA requirements | Condition assessment outcomes must reflect on the asset register of MMM. The Asset Register must be updated with the latest condition assessment outcomes. | In-house | In-house | CFO | 01/09/2023 | 31/12/2023 | Asset Register updated with Condition assessment outcomes | Asset Register updated with Condition assessment outcomes | GRAP Compliant Asset Register
|  |  | Undertake an asset completeness exercise to ensure the asset register is complete and all required information to comply with GRAP such as condition, asset type, Location, etc is captured. | External | External | CFO | 01/09/2023 | 31/12/2023 | All MMM assets are accounted for | New assets verification information Unbundled asset supporting verification and working papers | GRAP Compliant Asset Register
|  |  | Compile a GRAP compliant asset register using the outcomes of the asset completeness exercise to update the asset register. | In-house | In-house | CFO | 01/09/2023 | 31/12/2023 | Updated Asset Register | Updated Asset Register | GRAP Compliant Asset Register
|  |  | Using the conditional assessment outcomes, assess and update useful lives and residual values of assets. | In-house | In-house | CFO | 01/09/2023 | 31/12/2023 | Updated Asset Register | Updated Asset Register | GRAP Compliant Asset Register
|  |  | Investment is needed in a GIS system to manage all MMM assets by displaying the updated asset register within the system. | City Manager, CFO, GM Budget, Service Delivery Executive Managers | In-house | HOD: Corporate Services | 01/09/2023 | 31/12/2023 | System Landscape Analysis Report Implementation of a GIS System | System Landscape Analysis Report Implemented GIS System | Per the BFP
|  | Componentisation of completed projects | Asset hierarchy must be clearly identified and compliant with mSCOA and CIDMS. | In-house | In-house | CFO | 01/09/2023 | 31/12/2023 | Approved asset hierarchy as an appendix to the Asset Management Policy | Asset Management Policy | Per the BFP
|  |  | Contractors must submit a list of assets created as part of the project close out. This must align to the asset hierarchy and asset information required for capitalisation. | In-house | In-house | HOD: Engineering Services | 01/09/2023 | 31/12/2023 | Project asset listing | Project file documentation | Per the BFP
|  |  | Finance department must capitalise the spend on the project. | In-house | In-house | CFO | 01/09/2023 | 31/12/2023 | Capitalisation of Work in Progress | Financial records | Per the BFP
3 | Electricity | The municipality requires an Electricity Master plan for planning purposes. | Allocate budget, complete Electrical Master Plan and implement. | In-house | In-house | CEO CENTLEC | 01/09/2023 | 31/12/2023 | Masterplan for Electricity | Masterplan for Electricity | Revised projects list requiring funding
|  | SLA between MMM and CENTLEC not concluded. | Conclude SLA with CENTLEC. | In-house | In-house | CM | 01/09/2023 | 31/12/2023 | Signed SLA | Signed SLA between MMM and CENTLEC | Per the BFP
|  | The municipality has not indicated a clear strategy to deal future energy security, considering SSEG and risk mitigation for loadshedding. | Clearly define and document the Energy Security Strategy. | In-house | In-house | CEO CENTLEC | 01/09/2023 | 31/12/2023 | Energy Security Strategy | Maintenance Plan for Electricity | Revised maintenance budgets required
|  | Loss Reduction strategies need to be documented and must be measurable outcomes. | Formalise the loss reduction strategies deployed into the Loss Reduction Strategy document | In-house | In-house | CEO CENTLEC | 01/09/2023 | 31/12/2023 | Loss Reduction Strategy document | Loss Reduction Strategy document | Per the BFP
|  | Need for meter audits and 'SMART' technologies due to inaccurate meter database and poor revenue collected. Faulty meters, inaccurate billing and old meters leads to incorrect billing information and estimated billing which in turn results in inaccurate billing and inflated debt. Theft, illegal connections and Meter tampering result in Electricity losses of 10.92% (Technical and non-technical losses). Malfunctioning of bulk meters due to aging and tampering. Enhance revenue by installing Bulk meters and Zonal meters to curb revenue losses & to detect tampers remotely. Government debt is about R800m due to Government departments are not honouring their debt in full. Currently 4620 meters are not allocated to the financial system and information on installed meters do not always reach the finance office. | Targeted meter replacement priortised by largest loss impact on a yearly basis. | In-house | In-house | CEO CENTLEC | 01/09/2023 | 31/12/2023 | Prioritised list of target areas | Performance against list Revenue change per area | Improved revenue
|  |  | Prioritise budget for smart meter replacements. | In-house | In-house | CFO | 01/09/2023 | 31/12/2023 | Prioritised list of targeted meter replacements | Performance against list | Per the BFP
|  |  | Check meters to be installed in a phased approach. | In-house | In-house | CEO CENTLEC | 01/09/2023 | 31/12/2023 | Prioritised list of check meters to be installed | Performance against list | Per the BFP
|  |  | Install bulk smart meters for LPU customers. | In-house | In-house | CEO CENTLEC | 01/09/2023 | 31/12/2023 | Prioritised list of LPU smart meters | Performance against list | Per the BFP
|  |  | All municipal properties should have meters installed and the readings should be taken monthly. | In-house | In-house | CEO CENTLEC | 01/09/2023 | 31/12/2023 | List of Municipal properties with no meters | Performance against list with supporting meter installation certificate | Per the BFP
|  |  | Joint MMM teams (finance and engineering) should conduct in-loco inspections (audits) of metered customers. | In-house | In-house | CEO CENTLEC | 01/09/2023 | 31/12/2023 | Target 15% of metered customers per year for inspection | Inspection sheets and evidence of corrective actions (if any) | Per the BFP
|  |  | Departments in arrears with their accounts should be treated the same as customers in arrears. | In-house | In-house | CEO CENTLEC | 01/09/2023 | 31/12/2023 | Department accounts should not exceed 60 days | Creditors age analysis | Per the BFP
|  |  | Install bulk smart meters for LPU customers. | In-house | In-house | CEO CENTLEC | 01/09/2023 | 31/12/2023 | Prioritised list of LPU smart meters | Performance against list | Per the BFP
|  | Need for meter audits and 'SMART' technologies due to inaccurate meter database and poor revenue collected. | Meter readers should have technical skills and should report on illegal connections or meter tampering. | In-house | In-house | CEO CENTLEC | 01/09/2023 | 31/12/2023 | Meter reading exception reporting on tampering and illegal connections | Meter reading exception reporting on tampering and illegal connections | Per approved training budget allocation
4 | Water | The municipality requires a Water Master plan | Allocate budget, complete Water Master Plan and implement. | In-house | In-house | HOD: Engineering Services | 01/09/2023 | 31/12/2023 | Masterplan for Water | Masterplan for Water | Revised projects list requiring funding
|  | The municipality does not have a Water Conservation and Water Demand Management Plan (WCWDMP) Water losses attributed to meter tampering and illegal connections due to customers not prioritising the payment of services. Water losses are reported at 46% largely due to lack of proper network maintenance. | Allocate budget, complete WCWDMP and implement. | In-house | In-house | HOD: Engineering Services | 01/09/2023 | 31/12/2023 | Water Conservation and Water Demand Management Plan (WCWDMP) | Water Conservation and Water Demand Management Plan (WCWDMP) | Revised project lists and maintenance budgets required
|  |  | Implement Pressure and Network Zone Management. | In-house | In-house | HOD: Engineering Services | 01/09/2023 | 31/12/2023 | Water Conservation and Water Demand Management Plan (WCWDMP) | Comparative Water Demand analysis | Approximately R45 million
|  |  | Implement Pro-active leak detection and repair. | In-house | In-house | HOD: Engineering Services | 01/09/2023 | 31/12/2023 | Water Conservation and Water Demand Management Plan (WCWDMP) | Comparative Water Demand analysis | Approximately R87 million
|  |  | Implement Maselspoort Rising Main and Pipeline Upgrage. | In-house | In-house | HOD: Engineering Services | 01/09/2023 | 31/12/2023 | Water Conservation and Water Demand Management Plan (WCWDMP) | Comparative Water Demand analysis | Approximately R35 million
|  |  | Implement Maselspoort Rising Main and Pipeline Upgrage | In-house | In-house | HOD: Engineering Services | 01/09/2023 | 31/12/2023 | Water Conservation and Water Demand Management Plan (WCWDMP) | Comparative Water Demand analysis | Approximately R35 million
|  | The municipality does not have a Water Services Development Plan (WSDP) | Engage with the City Support Program Unit (CSP) to incorporate recommended stategies and align the development of the WSDP accordingly. | In-house | In-house | HOD: Engineering Services | 01/09/2023 | 31/12/2023 | Water Services Development Plan (WSDP) | Water Services Development Plan (WSDP) | Revised projects list requiring funding
|  |  | Allocate budget, complete WSDP and implement | In-house | In-house | HOD: Engineering Services | 01/09/2023 | 31/12/2023 | Water Services Development Plan (WSDP) | Water Services Development Plan (WSDP) | Revised projects list requiring funding
|  | The municipality has 7 supply systems according to the Blue Drop report with a Blue Drop Risk Rating (BDRR) of 72.5% (BDRR < 50% is low risk, 50%-70% is medium risk, 70%-90% is high risk, above 90% is critical risk). For five (Bloemfontein, Dewetsdorp, Wepener, Botshabelo and Thaba Nchu) of the seven supply systems, Bloem Water is the Water Services provider to the municipality. Bloemfontein, Dewetsdorp and Thaba Nchu supply systems achieved medium BDRR while Vanstadensrus and Wepener achieved high-risk ratings and Botshabelo and Soutpan are in the critical-risk rating category. Under operational capacity, only Dewetsdorp and Wepener have operational flow data while the remainder of the systems do not have information. | Implement the recommendations of the Blue Drop report | In-house | In-house | HOD: Engineering Services | 01/09/2023 | 31/12/2023 | Performance reporting | Blue Drop report | Revised projects list requiring funding
|  | Water Loss Management. Water losses are reported at 46% largely due to lack of proper network maintenance. Water Loss Management. Unmetered self consumption. Need for meter audits and 'SMART' technologies due to inaccurate meter database and poor revenue collected. Faulty meters, inaccurate billing and old meters leads to incorrect billing information and estimated billing which in turn results in inaccurate billing and inflated debt. Theft, illegal connections and Meter tampering result in Electricity losses of 10.92% (Technical and non-technical losses). Malfunctioning of bulk meters due to aging and tampering. Enhance revenue by installing Bulk meters and Zonal meters to curb revenue losses & to detect tampers remotely. Government debt is about R800m due to Government departments are not honouring their debt in full. Currently 4620 meters are not allocated to the financial system and information on installed meters do not always reach the finance office. | Targeted meter replacement priortised by largest loss impact on a yearly basis. | In-house | In-house | HOD: Engineering Services | 01/09/2023 | 31/12/2023 | Prioritised list of target areas | Performance against list Revenue change per area | Per the BFP
|  |  | Prioritise budget for smart meter replacements. | In-house | In-house | HOD: Engineering Services | 01/09/2023 | 31/12/2023 | Prioritised list of targeted meter replacements | Performance against list | Per the BFP
|  |  | Check meters to be installed in a phased approach. | In-house | In-house | HOD: Engineering Services | 01/09/2023 | 31/12/2023 | Prioritised list of check meters to be installed | Performance against list | Per the BFP
|  |  | Install bulk smart meters for LPU customers. | In-house | In-house | HOD: Engineering Services | 01/09/2023 | 31/12/2023 | Prioritised list of LPU smart meters | Performance against list | Per the BFP
|  |  | All municipal properties should have meters installed and the readings should be taken monthly. | In-house | In-house | HOD: Engineering Services | 01/09/2023 | 31/12/2023 | List of Municipal properties with no meters | Performance against list with supporting meter installation certificate | Increase revenue
|  |  | Joint MMM teams (finance and engineering) should conduct in-loco inspections (audits) of metered customers. | In-house | In-house | HOD: Engineering Services | 01/09/2023 | 31/12/2023 | Target 15% of metered customers per year for inspection | Inspection sheets and evidence of corrective actions (if any) | Approximately R0.475 million
|  |  | Departments in arrears with their accounts should be treated the same as customers in arrears. | In-house | In-house | HOD: Engineering Services | 01/09/2023 | 31/12/2023 | Department accounts should not exceed 60 days | Creditors age analysis | Increase revenue
|  |  | Install bulk smart meters for LPU customers. | In-house | In-house | HOD: Engineering Services | 01/09/2023 | 31/12/2023 | Prioritised list of LPU smart meters | Performance against list | Per the BFP
|  | There is inadequate credit control on both indigents and normal clients. Money owed by the municipality was not always paid within 30 days, as required by section 65(2)(e) of the MFMA. There is not loss reduction strategies in place to address this. | Allocate budget, complete Water Service Loss Reduction strategy document. | In-house | In-house | HOD: Engineering Services | 01/09/2023 | 31/12/2023 | Water Services Loss reduction strategies | Water Services Loss reduction strategies | Per the BFP
|  | 159km of abestos pipeline needed to be replaced. | Allocate budget, complete and implement Pipeline replacement project. | In-house | In-house | HOD: Engineering Services | 01/09/2023 | 31/12/2023 | 34% or 54km of Abestos pipelines replaced | 34% or 54km of Abestos pipelines replaced | Approximately R45.7 million
|  | Need for meter audits and 'SMART' technologies due to inaccurate meter database and poor revenue collected. | Meter readers should have technical skills and should report on illegal connections or meter tampering. | In-house | In-house | HOD: Engineering Services | 01/09/2023 | 31/12/2023 | Meter reading exception reporting on tampering and illegal connections | Meter reading exception reporting on tampering and illegal connections | Per approved training budget allocation
5 | Sanitation | The municipality requires a Sanitation Master plan | Allocate budget, complete and implement. | In-house | In-house | HOD: Engineering Services | 01/09/2023 | 31/12/2023 | Masterplan for Sanitation | Masterplan for Sanitation | Revised projects list requiring funding
|  | The municipality requires a Sanitation Infrastructure Maintenance plan Dilapidated components at Waste Water Treatment Works result in sewer spillage which is threat to water quality. Plant design capacity is 140Ml/d and is operating at 104% above capacity. The VROOM cost presents a ‘’very rough order of measurement” cost to return a WWTWs functionality to its original design is estimated at R164m. | Allocate budget, complete Sanitation Infrastructure Maintenance plan. | In-house | In-house | HOD: Engineering Services | 01/09/2023 | 31/12/2023 | Maintenance Plan for Sanitation | Maintenance Plan for Sanitation | Revised maintenance budgets required
|  |  | Identify implementable projects at critical plants to implement. Allocate budget and implement. | In-house | In-house | HOD: Engineering Services | 01/09/2023 | 31/12/2023 | List of implementable projects and budget allocation for the emergency works | List of implementable projects and budget allocation for the emergency works
|  | The Green Drop report shows the following plants as a Critical Risk Rating (Dewetsdorp, Vanstadensrus, Wepener, Soutpan) and these with a High Risk Rating (Bloemindustria, Bloemspruit, Botshabelo, Sterkwater, Thaba Nchu, Welvaart) | Implement the recommendations of the Green Drop report. | In-house | In-house | HOD: Engineering Services | 01/09/2023 | 31/12/2023 | Performance reporting | Green Drop report | Revised projects list requiring funding
|  | There is an influx of people to Mangaung resulting in an increase in population and informal settlements which adds to the backlogs. | Allocate budget for the eradicate the VIP toilets in a phase approach. | In-house | In-house | HOD: Engineering Services | 01/09/2023 | 31/12/2023 | Budget Documentation | Budget Documentation | Per the BFP
6 | Roads and Stormwater | The municipality is currently developing and concluding on the Roads and Stormwater Masterplan. | Allocate budget, complete Roads and Stormwater Master Plan and implement. | In-house | In-house | HOD: Engineering Services | 01/09/2023 | 31/12/2023 | Masterplan for Roads and Stormwater | Masterplan for Roads and Stormwater | Per the BFP
|  | Urgent Road Maintenance is needed to address the backlog | Allocate budget for repairs and maintenance of reported potholes, stormwater drainange, cleaning of blocked drains and urgent maintenance of surfaced roads | In-house | In-house | HOD: Engineering Services | 01/09/2023 | 31/12/2023 | Maintenance backlog | Maintenance backlog reporting | Per the BFP
7 | Solid Waste | The municipality is currently developing and concluding on the Integrated Waste Management Plan (IWMP). | Allocate budget, align to National strategies and complete IWMP and implement. | In-house | In-house | HOD: Waste and Fleet Management | 01/09/2023 | 31/12/2023 | Integrated Waste Management Plan | Integrated Waste Management Plan | Per the BFP
|  |  | Ensure the operations of transfer stations by repairing and maintaining them. | In-house | In-house | HOD: Waste and Fleet Management | 01/09/2023 | 31/12/2023 | Integrated Waste Management Plan | Integrated Waste Management Plan | Per the BFP
|  |  | Create, approve and implement seperation at source strategy. | In-house | In-house | HOD: Waste and Fleet Management | 01/09/2023 | 31/12/2023 | Integrated Waste Management Plan | Integrated Waste Management Plan | Per the BFP
|  |  | Implement Buy Back centers (Fixed and Mobile). | In-house | In-house | HOD: Waste and Fleet Management | 01/09/2023 | 31/12/2023 | Integrated Waste Management Plan | Operational Buy Back centers | Per the BFP
|  |  | Source markets for the sale of recycleable waste and compost. | In-house | In-house | HOD: Waste and Fleet Management | 01/09/2023 | 31/12/2023 | Integrated Waste Management Plan | Sales of recycable waste | Per the BFP
|  | Landfills are currently not complying to the legislation which could lead to licences been revoked. All existing landfill sites weighbridges are currently not functioning. The fences have also been stolen. There is currently no revenue collected at the landfill sites, gates except revenue from the destruction of condemned goods which is not frequent. There are no sufficient resources to cover areas that are badly affected by the illegal dumping. Furthermore, lack of sufficient human capacity to provide education and awareness to the community members. | Identify the non compliance criteria for licencing and minimum requirements for landfills. Create project lists and project implementation plans to ensure compliance. | In-house | In-house | HOD: Waste and Fleet Management | 01/09/2023 | 31/12/2023 | Landfill project list and accompaning project implementation plans | Landfill project list and accompaning project implementation plans
|  |  | Efficient management of Landfill sites. | In-house | In-house | HOD: Waste and Fleet Management | 01/09/2023 | 31/12/2023 | Management reports | Landfill management reports to the Regulator
|  |  | Repair and maintain existing Weighbridges on landfill sites. | In-house | In-house | HOD: Waste and Fleet Management | 01/09/2023 | 31/12/2023 | Weighbridges repaired and operational | Reporting on Weighbridge operations
|  |  | Install new Weighbridges where necessary at landfill sites. | In-house | In-house | HOD: Waste and Fleet Management | 01/09/2023 | 31/12/2023 | Weighbridges installed and comissioned | Project Completion Certification
|  |  | Collect revenue from users at landfill sites. | In-house | In-house | CFO | 01/09/2023 | 31/12/2023 | Increased revenue | Debtor statements | Increased revenue
|  |  | Collaborate with Private waste removal companies. | In-house | In-house | HOD: Waste and Fleet Management | 01/09/2023 | 31/12/2023 | Waste collection schedules are met | Waste collection schedules are met
8 | Community Facilities | The municipality needs to upgrade sports and recreation facilities and cemeteries. The municipality needs to have cost reflective tariffs for the use of its facilities. Poor revenue collection for use of facilities. The municipality owns a Nature Reserve facility that it has not been optimized for revenue collection. | Development and Implementation of a cultural and sport tourism strategy. | In-house | In-house | HOD: Corporate Services | 01/09/2023 | 31/12/2023 | Sports and Cultural Tourism strategy | Sports and Cultural Tourism strategy | Per the BDP
9 | Town Planning and Human Settlement | SPLUMA has been implemented however MMM takes too long to sign the SLA resulting in delays as the owner cannot install services. | MMM to adhere to timeframes recommended by SPLUMA and capacitate the department. | In-house | In-house | HOD: Planning | 01/09/2023 | 31/12/2023 | Adherance to SPLUMA guideline for timeframes | SLA's signed within the SPLUMA timeframes
|  | Lack of land for development. Loss of potential revenue. Slow local economic development. Informal Settlement Sprawl. | Review the process leading to approval of submissions by Council. | In-house | In-house | HOD: Planning | 01/09/2023 | 31/12/2023 | Revised process submitted for approvals | Revised process submitted for approvals
|  |  | Institute immediate legal action against all the habitual defaulters. | In-house | In-house | HOD: Corporate Services | 01/09/2023 | 31/12/2023 | List of habitiual defaluters and trial statuses | List of habitiual defaluters and trial statuses
|  |  | Delegate approvals of the short-term leases to the HOD: Human Settlements, subject to quarterly reporting to Council for noting. | In-house | In-house | HOD: Planning | 01/09/2023 | 31/12/2023 | Revised Delegation of Authority approved by Council | Revised Delegation of Authority approved by Council
|  |  | Prioritizing funding for the installation of services on all the land development initiatives for mixed development and sell newly developed sites to expand the revenue base. | In-house | In-house | HOD: Planning | 01/09/2023 | 31/12/2023 | Project Budget Allocations | Project Budget Allocations | Revised projects list requiring funding
|  |  | Prioritizing funding for the installation of services on all the industrial sites in Hamilton and Bloemdustria. | In-house | In-house | HOD: Planning | 01/09/2023 | 31/12/2023 | Project Budget Allocations | Project Budget Allocations | Revised projects list requiring funding
|  |  | Address building contraventions and enforce the building bylaws, this includes compliance with zoning status. | In-house | In-house | HOD: Planning | 01/09/2023 | 31/12/2023 | List of contraventions and issued fines | List of contraventions and issued fines
|  | 47 informal settlements which are home to an estimated 30 329 households, sporadic land invasion, accreditation and beneficiary management, Bulk Infrastructure for VISTA 3, challenges in the upgrading of informal settlements is the lack of bulk capacity especially for sanitation in regions of Thaba-Nchu and Botshabelo. | Exploring the alternative sanitation solutions to provide flushing toilets to households. | In-house | In-house | HOD: Engineering Services | 01/09/2023 | 31/12/2023 | Preferred alternate sanitation solution | Preferred alternate sanitation solution
|  |  | Council approval of commonage framework. | In-house | In-house | HOD: Planning | 01/09/2023 | 31/12/2023 | Council resolution | Council resolution
|  |  | Land audit exercise. | In-house | In-house | HOD: Planning | 01/09/2023 | 31/12/2023 | Land audit outcomes | Land audit outcomes | Per the BFP
10 | Integrated Public Transport Network (IPTN) | 37 Bus stops completed, 7 Bus shelters, 1 university stop. No operational license for buses, vandalism (batteries missing), vehicle inspection list completed. | Implementation of the Pilot & Go Live phase. | In-house | In-house | CM | 01/09/2023 | 31/12/2023 | Pilot and Go Live phase implemented | Pilot and Go Live phase implemented | Per the BFP
|  |  | Operation of the ticket sales office. | In-house | In-house | CM | 01/09/2023 | 31/12/2023 | Ticket sales office operational | Ticket sales office operational
|  |  | Completion of all bus stops. | In-house | In-house | CM | 01/09/2023 | 31/12/2023 | All bus stops completed and operational | All bus stops completed and operational
|  |  | Review the contract and ensure alignment for appointed operator. | In-house | In-house | CM | 01/09/2023 | 31/12/2023 | Appointed operator contract signed | Appointed operator contract signed
11 | Fresh Produce Market | Poor Facilities Management including poor management of loadshedding resulting in adverse impact on facility users. | Develop a facilities maintenance plan. | In-house | In-house | HOD: Planning | 01/09/2023 | 31/12/2023 | Facilities Maintenance plan | Facilities Maintenance plan | Per the BFP
|  |  | Allocate funding for the maintenance and implement to protect revenue that is currently being generated. | In-house | In-house | HOD: Planning | 01/09/2023 | 31/12/2023 | Maintenance budget allocations for R&M | Maintenance budget allocations for R&M | Revised maintenance budgets required
12 | Testing and Licencing | Outdated Service Level Agreement between the municipality and the Provincial Department of Safety. | Re-model cost of the licencing services. | In-house | In-house | Chief of Municipal Police Services | 01/09/2023 | 31/12/2023 | Cost model for licencing service | Cost model for licencing service | Per the BFP
13 | Fire Services | The municipality may be in violation of the Fire Services Brigade Act 99 0f 1987. The municipality has a limited number of trucks and inadequate fire fighting equipment. It is unclear if the fire hydrants are in a good working condition as there is no evidence of maintenance work done. There is poor enforcement of national fire code on buildings. Fire tariffs may not be cost reflective and may not be applied consistently. | Develop an optimal service delivery model for delivering the Fire Services. | In-house | In-house | HOD: Social Services | 01/09/2023 | 31/12/2023 | Service Delivery Model | Service Delivery Model | Per the BFP
|  |  | Tariffs for fire services must be cost reflective. | In-house | In-house | HOD: Social Services | 01/09/2023 | 31/12/2023 | Fire Services tariffs | Fire Services tariffs | Per the BFP
14 | Fleet | The municipality does not have Fleet Management Strategy | Allocate budget, complete and implement. | In-house | In-house | HOD: Waste and Fleet Management | 01/09/2023 | 31/12/2023 | Fleet Management Strategy | Fleet Management Strategy | Per the BFP
|  | The municipality does not have Fleet Management Policy | Allocate budget, complete and implement. | In-house | In-house | HOD: Waste and Fleet Management | 01/09/2023 | 31/12/2023 | Fleet Management Policy | Fleet Management Policy | Per the BFP
|  | Inadequate plant and equipment to manage the landfill sites. There is a refuse removal schedule, but it is frequently not adhered to due to lack of sufficient vehicles to remove waste and lack sufficient human resources (critical positions not filled). The mechanical workshop is in a good condition but under utilized due to budget constraints to procure adequate and specialized equipment and spares. Dysfunctional plant, equipment and fleet that cannot be repaired or salvaged should be disposed off. Parks has a maintenance strategy in place which stipulates the maintenance standards on how Parks have to be maintained and looked after however there are not enough vehicles are available due to breakdowns and there is no maintenance budget available. | A comprehensive needs analysis including cost benefit analysis on the maintenance costs and lease vs buy analysis should be implemented in the Fleet strategy. | In-house | In-house | HOD: Waste and Fleet Management | 01/09/2023 | 31/12/2023 | Fleet Management strategy | Fleet Management Strategy Cost benefit analysis on maintenance costs | Per the BFP
|  |  | Review the current existing lease agreements and perform a cost benefit analysis on leasing versus buying. | In-house | In-house | HOD: Waste and Fleet Management | 01/09/2023 | 31/12/2023 | Reviewed lease agreements | Lease vs buy analysis
|  |  | Incorporate the vehicle replacement plan under Fleet management strategy plan. | In-house | In-house | HOD: Waste and Fleet Management | 01/09/2023 | 31/12/2023 | Fleet Management strategy | Vehicle replacement plan
|  |  | Budget for the mechancial workshop must be provided for. | In-house | In-house | HOD: Waste and Fleet Management | 01/09/2023 | 31/12/2023 | Budget Documentation | Budget Documentation | Per the BFP
15 | Customer Service | No proper policy and service charter to improve customer service. | Service charter to align to NRS 047 and NRS 048 reporting requirements. | In-house | In-house | HOD: Engineering Services | 01/09/2023 | 31/12/2023 | Service charter aligned to NRS 047 and NRS 048 reporting requirements. | NRS 047 and NRS 048 reporting compliance | Per the BFP
|  |  | Allocate budget, complete and implement. | In-house | In-house | HOD: Engineering Services | 01/09/2023 | 31/12/2023 | Customer service charter | Customer service charter | Per the BFP
16 | Project Management | Time taken to reticulate peri-urban areas is too long leading to community protests. The rate of rehabilitation and development of sewer reticulation networks is very slow. Lack of funding for maintenance, refurbishment and capital projects has accelerated the decline in the condition of the infrastructure resulting in failing equipment. Loadshedding is another accelerant factor. Projects for refurbish /upgrade electrical network are delayed due to insufficient budgets. | Introduce a monitoring mechanism to track project progress against spend, be a repository for project capitalisation purposes to assist in the capitalisation process. | In-house | In-house | CFO | 01/09/2023 | 31/12/2023 | Implement a project tracking system | Project tracking system | 100% Capital Expenditure
|  |  | Review expenditure on Capital projects to ensure the funds received are spent in accordance with the given conditions. | In-house | In-house | CFO | 01/09/2023 | 31/12/2023 | No grant spending withdrawn due to not meeting the conditions of the Grant/s | Grant reporting frameworks
|  |  | An integrated approach is needed for multidiciplinary projects. | In-house | In-house | CFO | 01/09/2023 | 31/12/2023 | All project must have a Project Implementation Plan | Project Implementation Plan
|  |  | Project prioritsation matrix must be developed. | In-house | In-house | CFO | 01/09/2023 | 31/12/2023 | Implementation of a project prioritisation matrix | Project prioritisation matrix
|  |  | All projects must feed into the CAPEX plan and have an associated Project Implementation plan. | In-house | In-house | CFO | 01/09/2023 | 31/12/2023 | All project must have a Project Implementation Plan | Project Implementation Plan
|  |  | Provide training in grant conditions and guidelines. | In-house | In-house | CFO | 01/09/2023 | 31/12/2023 | Training of Project Managers on grant conditions and guidelines | Training attendance and certification
|  |  | Ring fence of grant funds and preferably pay service providers from this dedicated account in order to monitor and minimise misuse. | In-house | In-house | CFO | 01/09/2023 | 31/12/2023 | Timeous payment of service providers used on grant funded projects | Payment remittance
17 | Technical Systems | Basic technical systems are absent or inoperable. System licencing is not maintained. Technical data is not maintained. IT system landscape is not defined and implemented. No GIS system and competent personnel in place to prepare a GRAP and mSCOA compliant asset register inhouse. Provincial Road Asset Management (RAMs) project should be accelerated, and data verified before inclusion. Investment in a system/s allowing the Municipality to pinpoint areas where losses occur. Need for a digital fault/complaint reporting system. Need for a single meter database. | Conduct a system landscape analysis based on service delivery needs and integration requirements.All service delivery departments must be consulted and the analysis must include CoTS applications with minimal customisation. Integration and connectivity considerations must be included in the analysis. | In-house | In-house | HOD: Corporate Services | 01/09/2023 | 31/12/2023 | System Landscape Analysis Report Renewed Licenses Implemented GIS System Single Meter Database | System Landscape Analysis Report Renewed Licenses Implemented GIS System Single Meter Database | Per the BFP
Internal parties to be called out on non-attendance and oversight management to meet with them to discuss importance.
Investment is needed in a GIS system to enable spatial planning and reporting.
18 | Bloemfontein Airport | Poor administration of the facility. | Current management company is under liquadation, a new management company must be appointed. | In-house | In-house | CM | 01/09/2023 | 31/12/2023 | Signed SLA | Signed SLA
|  |  | Currently 76% of rental agreements have expired. Renew all expired leases. | [5 empty] | All leases reflect market related values | All leases reflect market related values
|  |  | Initiate legal processes where lessees are untraceable. | [5 empty] | Signed court orders | Signed court orders to recover lost revenue

## STABILISATION PHASE 2
PHASE 2: STABILISATION
NO | FOCUS AREA | KEY ASSESSMENT FINDING (BASELINE) | KEY ACTIVITIES | RESOURCES REQUIRED | RESOURCES MOBILISED | RESPONSIBLE | START DATE | END DATE | KEY PERFORMANCE INDICATOR | PORTFOLIO OF EVIDENCE | BUDGET PARAMETER/ REVENUE TARGET/ SPENDING LIMIT | MUNICIPAL PROGRESS REPORT
[12 empty] | STEPS TAKEN | PROGRESS MADE | FINANCIAL IMPACT | OTHER NOTEWORTHY DEVELOPMENTS
PILLAR ONE: GOVERNANCE
1 | Governance, Council and oversight structures/Committees | The municipality does not have a stakeholder engagement strategy and public participation policy in place. Disciplinary Board not in place and therefore not functional. | Develop and implement a stakeholder engagement strategy that introduces various stakeholder engagement forums such as bi-weekly MLM team chats with the Accounting Officer. | In house | In house | CM | 01.01.2024 | 31.01.2024 | By-in and informed stakeholders | Approved stakeholder engagment strategy an implemetation plan. | Financial benefits to be achieved through improved operational efficiencies
|  |  | Implement a register for open cases and status. | In house | In house | CFO | 01/01/2024 | Monthly | Financial misconduct recorded. | Financial misconduct register
|  |  | Disciplinary Board to report on investigation of all reported allegations of financial misconduct. | In house | In house | Disciplinary Board | 01/01/2024 | Quarterly | Quarterly reports | Council approved reports and resolutions
2 | System of Delegations | Non-compliance with legislation specifically Municipal Systems Act that requires review of system of delegations after every local government election. | Review and approve delegations of powers and functions for implementation of supply chain management policy. | In house | In house | CM | 01/01/2024 | 30.07.2024 | Enhanced accountability and, checks and balances. Sub-delegations in place | Approved SCM Delegations of authority | Financial benefits to be achieved through improved operational efficiencies
3 | UIF&W and Consequence Management | There are no section 32 investigations that have been conducted. The analysis and identification of UIF&W was outsourced but the report is not being used by the municipality due to the irregular appointment of the service provider. | Implement Consequence Management for historical Irregular expenditure and take steps to recover or rectify such expenditure and to prevent recurrence as prescribed by section 32 of the MFMA. | In house | In house | CFO | 01/01/2024 | 31/12/2024 | Transgressors disciplined | Written outcome of disciplinary hearings | Financial benefits to be achieved through improved operational efficiencies
4 | Audit action plans (internal and external) | AFS/APR may contain misstatement due to employee’s lack of knowledge or understanding of the current standards and regulations. | Provide budget for training. | In house | In house | CFO | 01/01/2024 | 31/12/2024 | Report tabled to Audit Committee, Mayoral Committee and Council | Agenda and minutes of Mayoral committee and Council, and recommendations and resolutions | Financial benefits to be achieved through improved operational efficiencies
5 | Risk Management | Inadequate diagnosis of all relevant risks being faced by MMM | Ensure that risk management is a standing agenda item for all scheduled management and Executive meetings. | In house | In house | CM | 01/01/2024 | 31/12/2024 | Monitored risks | Quarterly risk management reports approved by Administrator. Risk monitoring report. Monthly FRP implementation progress reports | Financial benefits to be achieved through improved operational efficiencies
6 | Information and Communication Technology | Internal Control Deficiencies. | Review, develop and implement ICT general controls (policies and SOPs). | In house | In house | ICT Manager | 01/01/2024 | 31/12/2024 | Improved intenal controls | Approved ICT policies and SOPs | Financial benefits to be achieved through improved operational efficiencies
PILLAR TWO: INSTITUTIONAL
1 | Operating Model | MMM does not have a well-defined and approved organisational structure to support the functioning of the Municipality. | The adoption and periodic review of the organisational structure in line with MMM’s approved operating model, strategy and governance structures. | In-house | In-house | HOD: Corporate Services | 01/01/2024 | 31/12/2024 | Credible staff establishment in line with the reviewed operating model. | Placement letters Copies of the job descriptions | In line with the approved budget and the funding plan.
|  | Inadequate day-to-day establishment management | Continued regular staff verification and implement the recommendations of the staff verification report.
2 | Employee costs | Employee costs are currently 24.71% of the operating expenditure which is below the norm of 25%-40%. The low % could point to a high level of critical vacancies and general understaffing. | Control over payroll by planning for the acquisition of skills in line with cash flow improvements. | In-house | In-house | CFO | 01/01/2024 | 31/12/2024 | Controlled employee costs | Skills Acquisition plan | Per BFP
3 | Management of overtime | Excessive Overtime. | Conduct quarterly monitoring of the implementation of the Overtime Policy by department. | In house | In house | HOD: Corporate Services | 01/01/2024 | Quarterly | Reduced Overtime costs | Quarterly overtime monitoring reports | Reduction in Employee cost
4 | Filling of critical positions | Limited capacity and skills to facilitate compliance with the Municipal Minimum Competency Framework. | Review Recruitment policy and procedures to ensure checks and balances that mitigate irregular practices. | In house | In house | CFO | 01/01/2024 | 31/12/2024 | Approved reviewed Recruitment policy | Approved reviewed Recruitment policy | Per approved budget allocation
Ringfence mandatory grant from LGSETA and other related capacity building grants for training and development of staff.
|  |  | Appoint accredited service provider to assist with the WSP implementation. | [6 empty] | Service Provider appointment letter & SLA | Per approved budget allocation
5 | Staff discipline | Ineffective disciplinary processes. | Utilise officials from other government departments, municipalities and or SALGA database to conduct disciplinary cases on behalf of the municipality. | Outsource | Outsource | CM | 01/01/2024 | Ongoing | Effective discipline management. | Signed Agreementswith SALGA and other departments, consultations outcomes. | N/A
6 | Consequence Management | Lack of accountability and consequence management in the municipality impacts service delivery and municipal finance management. | Continued monitoring of the implementation of the consequence management policy. | In-house | In-house | HOD: Corporate Services | 01/01/2024 | Ongoing | Consequence management policy implementation | Consequence management policy implementation | N/A
7 | Key HR Policies Management | Poor Human Resource Planning and excessive overtime. | Enforcement of compliance to the Basic conditions of Employment Act for the management of overtime by managers. | In-house | In-house | HOD: Corporate Services | 01/01/2024 | Ongoing | Reduced Overtime costs | Reduced Overtime costs | Reduction in Employee cost
8 | Change Management | Change Management is not implemented. | Continued monitoring of the change management strategy. | In-house | In-house | HOD: Corporate Services | 01/01/2024 | Ongoing | Change Manegement Strategy | Change Manegement Strategy | N/A
PILLAR THREE: FINANCIAL MANAGEMENT
1 | Adjustment Budget for 2023/24 | During the 2020/21 and 2021/22 financial years, MMM budgeted surpluses of R 1,035 billion (2020/21) and R 622,7 million (2021/22). The financial results for the two years reflected deficits of R 20,2 million (2020/21) and a deficit of R 872,7 million (2021/22) which clearly indicate that the budgets were not funded. MMM had audited deficits for the past three financial years, and budget for surpluses for the MTREF period, which are not cash backed. | Compile a 2023/24 adjustment budget in line with reviewed targets for realistically anticipated revenue and expenditure trends and ensure revised budget to be credible and cash funded. | In-house | In-house | CFO | 01/01/2024 | 30/05/2024 | Credible 2024/25 MTREF Adjustment Budget Cost Containment Improvement | Credible 2024/25 MTREF Adjustment Budget Cost Containment Improvement | Proper baseline for long term financial planning.
Projected revenue should consider the low historical and future collection rates and use a probabilistic method of projecting for revenue.
Austerity and cost cutting measures to be reflected in the 2023/24 adjustment budget.
2 | Supply Chain Management Compliance and Value for Money Procurement | Retention of supporting documentation not complete. Lack of record keeping. Lack of consequence management regarding irregular expenditure incurred. | Consequence management policy to be incorporated in HR. | In-house | In-house | CFO | 01/01/2024 | 31/12/2024 | Consequence Management Policy Attendance Register on Training Record Keeping System | Consequence Management Policy Attendance Register on Training Record Keeping System | Reduction in UIF&W based on FRP targets
Training of staff regarding the SCM processes.
Implementation of a record keeping system.
3 | ENTITY: CENTLEC | The principal activity of CENTLEC is the distribution of electricity to industries, businesses and households mainly in the Mangaung and Southern Free State areas. The relevant balances as at 30 June 2022 are: • Cash on hand R509.3 million; • Payables R890.8 million; • Deficit R189,5 million 2022 and R13.7 million 2021; • Employee related costs R425.6 million; • Duplication of management and board members; and • MMM not able to use electricity as a lever for collection of other debts e.g., rates, water, etc. From the above figures it is noted that Centlec has serious going concern challenges, operating on deficits and does not have sufficient cash at hand to settle short term liabilities. | Review the assessment conducted by EMS Solutions (Pty) Ltd on the consideration for the viability and implications of the sale of Centlec and incorporation of the Entity into MMM. | CM and CFO | NT Oversight | CM | 01/01/2024 | 31/12/2024 | Reviewed assessment report of EMS Solutions (Pty) S78 Assessment Report | Reviewed assessment report of EMS Solutions (Pty) S78 Assessment Report | Possible increase in revenue based on the outcome of the S78 investigation
Conduct a Section 78 study to see the possibility of incorporating CENTLEC into MMM. As it currently stands, and before re-incorporating this service into the Municipality, CENTLEC’s performance must be monitored continuously.
4 | ENTITY: FRESHCO | Per the consultation process, it was established that the non-payment of water and rental accounts followed the liquidation of the managing company, FRESHCO, and the takeover of administration by the Social Housing Regulatory Authority (SHRA) in 2019. As per the group AFS as at 30 June 2022, FRESCO had liabilities of R149.5 million. Poor financial performance and growing liabilities. | Conduct a Section 78 study to see the possibility of incorporating FRESHCO into MMM. As it currently stands, and before re-incorporating this service into the Municipality, FRESHCO’s performance must be monitored continuously. | CM and CFO | NT Oversight | CM | 01/01/2024 | 31/12/2024 | S78 Assessment Report | S78 Assessment Report | Possible increase in revenue based on the outcome of the S78 investigation
5 | Creditor Management | A review of the amounts owed by the Municipality reflected the following: Creditors as at 30 June 2022 is R 2,4 billion. Creditors have increased by R 216.3 million year on year, between June 2021 and June 2022. The entity defaulted on the payment of suppliers within 30 days. The average term of payment of trade creditors during 2021/22 were 115 days, (2021: 131 days). | Provide budgetary allocation in budget to meet the payment plans for long outstanding creditors. | In-house | In-house | CFO | 01/01/2024 | 31/12/2024 | Renegotiated Payment Terms Consequence Management | Renegotiated Payment Terms Consequence Management | 100% adherence to payment arrangements Achieve expenditure financial targets per BFP parameters
Implement consequence management.
6 | Debt Restructuring | Escalating ESKOM debt. | Apply for MFMA Circular No. 124 – Municipal Debt Relief through National Treasury. | In house | In house | CFO | 01/01/2024 | 12 Months | Monthly Provincial Treasury certification of Municipal compliance | Monthly Provincial Treasury certification of Municipal compliance | Municipal Eskom Debt Relief as prescribed by Circular No. 124
PILLAR FOUR: SERVICE DELIVERY
1 | Strategic positions | Key managerial technical positions as identified in the approved organogram must be filled to capacity MMM to ensure service delivery. | Appointment of permanent senior management position in line with MFMA regulations to enable service delivery. | In-house | In-house | HOD: Corporate Services | 01/01/2024 | 31/12/2024 | Filling of critical vacant positions | Critical vacant positions are filled | Per the BFP
2 | Asset Management | No Asset Management Strategy | Allocate budget, complete and implement. | In-house | In-house | CFO | 01/01/2024 | 31/12/2024 | Asset Management Strategy | Asset Management Strategy | Per the BFP
3 | Electricity | The municipality requires an Electricity Infrastructure Maintenance plan Lack of funding for maintenance, refurbishment and capital projects has accelerated the decline in the condition of the infrastructure resulting in failing equipment. Loadshedding is another accelerant factor. | Allocate budget, complete and implement. | In-house | In-house | CEO CENTLEC | 01/01/2024 | 31/12/2024 | Maintenance Plan for Electricity | Maintenance Plan for Electricity | Per the BFP
|  | The municipality requires an Electricity Infrastructure Maintenance plan Lack of funding for maintenance, refurbishment and capital projects has accelerated the decline in the condition of the infrastructure resulting in failing equipment. Loadshedding is another accelerant factor. | Identify implementable project at critical plants to implement. Allocate budget and implement. | In-house | In-house | CEO CENTLEC | 01/01/2024 | 31/12/2024 | List of implementable projects and budget allocation | List of implementable projects and budget allocation | Revised projects list requiring funding
|  | The municipality has not indicated a clear strategy to deal future energy security, considering SSEG and risk mitigation for loadshedding | Call for proposals based on othe outcomes of the Energy security Strategy. | In-house | In-house | CEO CENTLEC | 01/01/2024 | 31/12/2024 | RFP | RFP
|  | The municipality has not indicated a clear strategy to deal future energy security, considering SSEG and risk mitigation for loadshedding | Assess and engage to implement the Energy Security strategy. | In-house | In-house | CEO CENTLEC | 01/01/2024 | 31/12/2024 | Bankable and feasable project/s | Bankable and feasable project/s
|  | Loss Reduction strategies need to be documented and must be measurable outcomes | Deploy loss reduction strategies. | In-house | In-house | CEO CENTLEC | 01/01/2024 | 31/12/2024 | Reporting on the outcomes of Loss Reduction Strategies | Reporting on the outcomes of Loss Reduction Strategies | Increased revenue
|  | Need for meter audits and 'SMART' technologies due to inaccurate meter database and poor revenue collected. Faulty meters, inaccurate billing and old meters leads to incorrect billing information and estimated billing which in turn results in inaccurate billing and inflated debt. Theft, illegal connections and Meter tampering result in Electricity losses of 10.92% (Technical and non-technical losses). Malfunctioning of bulk meters due to aging and tampering. Enhance revenue by installing Bulk meters and Zonal meters to curb revenue losses & to detect tampers remotely. Government debt is about R800m due to Government departments are not honouring their debt in full. Currently 4620 meters are not allocated to the financial system and information on installed meters do not always reach the finance office. | Targeted meter replacement priortised by largest loss impact on a yearly basis. | In-house | In-house | CEO CENTLEC | 01/01/2024 | 31/12/2024 | Prioritised list of targeted areas to be updated bi-annually | Prioritised list of targeted areas to be updated bi-annually | Increased revenue
|  |  | Prioritise budget for smart meter replacements. | In-house | In-house | CEO CENTLEC | 01/01/2024 | 31/12/2024 | Secure budgets for Meter replacements | Secure budgets for Meter replacements | Per the BFP
|  |  | Zonal meters to be installed in a phased approach. | In-house | In-house | CEO CENTLEC | 01/01/2024 | 31/12/2024 | Secure budgets for Zonal meter installations | Secure budgets for Zonal meter installations | Per the BFP
|  |  | The calculation of distribution losses should correctly deduct internal usage and the Rand value should be based on the cost of purchase. | In-house | In-house | CEO CENTLEC | 01/01/2024 | 31/12/2024 | Loss calcuations must take into account own use | Loss calcuations must take into account own use
|  |  | Joint MMM teams (finance and engineering) should conduct in-loco inspections (audits) of metered customers. | In-house | In-house | CEO CENTLEC | 01/01/2024 | 31/12/2024 | Target 15% year on year for metered in-loco inspections | Target 15% year on year for metered in-loco inspections
|  |  | Enforce by-laws and disconnect illegal connections. | In-house | In-house | CEO CENTLEC | 01/01/2024 | 31/12/2024 | Removal of illegal connections | Removal of illegal connections
|  |  | Determine pattern of household usage and flag for any irregularities. | In-house | In-house | CEO CENTLEC | 01/01/2024 | 31/12/2024 | Established revenue loss recognition strategies | Established revenue loss recognition strategies
|  |  | Equip meter readers with technical skills so they can report on illegal connections or meter tampering. | In-house | In-house | CEO CENTLEC | 01/01/2024 | 31/12/2024 | Exception reporting from meter reads | Exception reporting from meter reads
4 | Water | The municipality requires a Water Infrastructure Maintenance plan Dilapidated components at Water Treatment Plants and sewer spillage upstream from Waste Water Treatment Works is a threat to water quality. Lack of funding for maintenance, refurbishment and capital projects has accelerated the decline in the condition of the infrastructure resulting in failing equipment. Loadshedding is another accelerant factor. | Allocate budget, complete Water Infrastructure Maintenance Plan and implement. | In-house | In-house | HOD: Engineering Services | 01/01/2024 | 31/12/2024 | Maintenance Plan for Water | Maintenance Plan for Water | Per the BFP
|  | The municipality requires a Water Infrastructure Maintenance plan Dilapidated components at Water Treatment Plants and sewer spillage upstream from Waste Water Treatment Works is a threat to water quality. Lack of funding for maintenance, refurbishment and capital projects has accelerated the decline in the condition of the infrastructure resulting in failing equipment. Loadshedding is another accelerant factor. | Identify implementable project at critical plants to implement. Allocate budget and implement. | In-house | In-house | HOD: Engineering Services | 01/01/2024 | 31/12/2024 | List of implementable projects and budget allocation | List of implementable projects and budget allocation | Revised projects list requiring funding
|  | The municipality does not have a Water Conservation and Water Demand Management Plan (WCWDMP) Water losses attributed to meter tampering and illegal connections due to customers not prioritising the payment of services. Water losses are reported at 46% largely due to lack of proper network maintenance. | Implement Maselspoort Treatment Upgrades. | In-house | In-house | HOD: Engineering Services | 01/01/2024 | 31/12/2024 | Report on key activities implemented from the Water Conservation and Water Demand Management Plan (WCWDMP) | Comparative Water Demand analysis | Approximately R994 million
|  | The municipality does not have a Water Conservation and Water Demand Management Plan (WCWDMP) Water losses attributed to meter tampering and illegal connections due to customers not prioritising the payment of services. Water losses are reported at 46% largely due to lack of proper network maintenance. | Implement Routine or domestic leak repairs. | In-house | In-house | HOD: Engineering Services | 01/01/2024 | 31/12/2024 | Report on key activities implemented from the Water Conservation and Water Demand Management Plan (WCWDMP) | Comparative Water Demand analysis | Approximately R99 million
|  | The municipality does not have a Water Conservation and Water Demand Management Plan (WCWDMP) Water losses attributed to meter tampering and illegal connections due to customers not prioritising the payment of services. Water losses are reported at 46% largely due to lack of proper network maintenance. | Implement SCADA and Telemetry. | In-house | In-house | HOD: Engineering Services | 01/01/2024 | 31/12/2024 | Report on key activities implemented from the Water Conservation and Water Demand Management Plan (WCWDMP) | Comparative Water Demand analysis | Approximately R59.5 million
|  | The municipality does not have a Water Conservation and Water Demand Management Plan (WCWDMP) Water losses attributed to meter tampering and illegal connections due to customers not prioritising the payment of services. Water losses are reported at 46% largely due to lack of proper network maintenance. | Implement Water Re-use. | In-house | In-house | HOD: Engineering Services | 01/01/2024 | 31/12/2024 | Report on key activities implemented from the Water Conservation and Water Demand Management Plan (WCWDMP) | Comparative Water Demand analysis | Approximately R307 million
|  | The municipality does not have a Water Services Development Plan (WSDP) | Implement key activites as required by the plan. | In-house | In-house | HOD: Engineering Services | 01/01/2024 | 31/12/2024 | Report on the implement key activites from the Water Services Development Plan (WSDP) | Report on the implement key activites from the Water Services Development Plan (WSDP)
|  | Need for meter audits and 'SMART' technologies due to inaccurate meter database and poor revenue collected. Faulty meters, inaccurate billing and old meters leads to incorrect billing information and estimated billing which in turn results in inaccurate billing and inflated debt. Theft, illegal connections and Meter tampering result in Electricity losses of 10.92% (Technical and non-technical losses). Malfunctioning of bulk meters due to aging and tampering. Enhance revenue by installing Bulk meters and Zonal meters to curb revenue losses & to detect tampers remotely. Government debt is about R800m due to Government departments are not honouring their debt in full. Currently 4620 meters are not allocated to the financial system and information on installed meters do not always reach the finance office. | Targeted meter replacement priortised by largest loss impact on a yearly basis. | In-house | In-house | HOD: Engineering Services | 01/01/2024 | 31/12/2024 | Prioritised list of targeted areas to be updated bi-annually | Prioritised list of targeted areas to be updated bi-annually | Per the BFP
|  |  | Prioritise budget for smart meter replacements. | In-house | In-house | HOD: Engineering Services | 01/01/2024 | 31/12/2024 | Secure budgets for Meter replacements | Secure budgets for Meter replacements | Per the BFP
|  |  | Zonal meters to be installed in a phased approach. | In-house | In-house | HOD: Engineering Services | 01/01/2024 | 31/12/2024 | Secure budgets for Zonal meter installations | Secure budgets for Zonal meter installations | Per the BFP
|  |  | The calculation of distribution losses should correctly deduct internal usage and the Rand value should be based on the cost of purchase. | In-house | In-house | HOD: Engineering Services | 01/01/2024 | 31/12/2024 | Loss calcuations must take into account own use | Loss calcuations must take into account own use
|  |  | Joint MMM teams (finance and engineering) should conduct in-loco inspections (audits) of metered customers. | In-house | In-house | HOD: Engineering Services | 01/01/2024 | 31/12/2024 | Target 15% year on year for metered in-loco inspections | Target 15% year on year for metered in-loco inspections
|  |  | Enforce by-laws and disconnect illegal connections. | In-house | In-house | HOD: Engineering Services | 01/01/2024 | 31/12/2024 | Removal of illegal connections | Removal of illegal connections
|  |  | Determine pattern of household usage and flag for any irregularities. | In-house | In-house | HOD: Engineering Services | 01/01/2024 | 31/12/2024 | Established revenue loss recognition strategies | Established revenue loss recognition strategies
|  |  | Equip meter readers with technical skills so they can report on illegal connections or meter tampering. | In-house | In-house | HOD: Engineering Services | 01/01/2024 | 31/12/2024 | Exception reporting from meter reads | Exception reporting from meter reads | Per approved training budget allocation
|  | There is inadequate credit control on both indigents and normal clients. Money owed by the municipality was not always paid within 30 days, as required by section 65(2)(e) of the MFMA. There is not loss reduction strategies in place to address this. | Implement loss reduction strategies. | In-house | In-house | HOD: Engineering Services | 01/01/2024 | 31/12/2024 | Reporting on the outcomes of Water Services Loss reduction strategies implemented | Reporting on the outcomes of Water Services Loss reduction strategies implemented
|  | 159km of abestos pipeline needed to be replaced. | Allocate budget, complete and implement. | In-house | In-house | HOD: Engineering Services | 01/01/2024 | 31/12/2024 | 66% or 105km of Abestos pipelines replaced | 66% or 105km of Abestos pipelines replaced
5 | Sanitation | The municipality requires a Sanitation Infrastructure Maintenance plan Dilapidated components at Waste Water Treatment Works result in sewer spillage which is threat to water quality. The Green Drop report shows the following plants as a Critical Risk Rating (Dewetsdorp, Vanstadensrus, Wepener, Soutpan) and these with a High Risk Rating (Bloemindustria, Bloemspruit, Botshabelo, Sterkwater, Thaba Nchu, Welvaart) Plant design capacity is 140Ml/d and is operating at 104% above capacity. The VROOM cost presents a ‘’very rough order of measurement” cost to return a WWTWs functionality to its original design is estimated at R164m. | Projects identified from the Maintenace Plan must go through the project budget cycle with Project Implementation Plans (PIP). | In-house | In-house | HOD: Engineering Services | 01/01/2024 | 31/12/2024 | List of projects with PIPs included in the budgety processes | List of projects with PIPs included in the budgety processes | Revised projects list requiring funding
|  | There is an influx of people to Mangaung resulting in an increase in population and informal settlements which adds to the backlogs. | Accelerate the implementation of new human settlements developments following an integrated approach across all departments aligned to the Project Management Focus area key activities. | In-house | In-house | HOD: Engineering Services | 01/01/2024 | 31/12/2024 | Project Implementation plan Project feasibility study Project priortised as per matrix Projects listed on MTRF | Project Implementation plan Project feasibility study Project priortised as per matrix Projects listed on MTRF | Per the BFP
6 | Roads and Stormwater | The municipality is currently developing and concluding on the Roads and Stormwater Infrastructure Maintenance plan Up to 90% of surfaced roads are in poor condition (reported potholes, stormwater drainage and related blocked drains). | Allocate budget, complete and implement. | In-house | In-house | HOD: Engineering Services | 01/01/2024 | 31/12/2024 | Maintenance Plan for Roads and Stormwater | Maintenance Plan for Roads and Stormwater | Per the BFP
|  | The municipality is currently developing and concluding on the Roads and Stormwater Infrastructure Maintenance plan Up to 90% of surfaced roads are in poor condition (reported potholes, stormwater drainage and related blocked drains). | Identify implementable project at critical plants to implement. Allocate budget and implement. | In-house | In-house | HOD: Engineering Services | 01/01/2024 | 31/12/2024 | List of implementable projects and budget allocation | List of implementable projects and budget allocation | Revised projects list requiring funding
7 | Solid Waste | Landfills are currently not complying to the legislation which could lead to licences been revoked. All existing landfill sites weighbridges are currently not functioning. The fences have also been stolen. There is currently no revenue collected at the landfill sites, gates except revenue from the destruction of condemned goods which is not frequent. There are no sufficient resources to cover areas that are badly affected by the illegal dumping. Furthermore, lack of sufficient human capacity to provide education and awareness to the community members. | Allocate budget for projects to remove non compliance. | In-house | In-house | HOD: Waste and Fleet Management | 01/01/2024 | 31/12/2024 | Secure budgets for projects | Budget documentation MTREF | Projects list requiring funding
|  |  | Implement projects to remove non compliance. | In-house | In-house | HOD: Waste and Fleet Management | 01/01/2024 | 31/12/2024 | Projects listed on MTREF Project have Project Implentation Plan Projects priortised as per project prioritasation matrix | Project implementation plan Project priortisation outcomes
|  |  | Design and implement Waste Management Maintenance and Refurbishment Plan. | In-house | In-house | HOD: Waste and Fleet Management | 01/01/2024 | 31/12/2024 | Implementation of Waste Management Maintenance and Refurbishment plan | Waste Management Maintenance and Refurbishment plan | Per the BFP
|  |  | Internalise waste removal service. | In-house | In-house | HOD: Waste and Fleet Management | 01/01/2024 | 31/12/2024 | Internal reporting on waste removal service delivery | Internal reporting on waste removal service delivery | Reduce contracted services
8 | Community Facilities | The municipality does have Communitity Facilities Maintenance Plan and Operation Plan but should be updated Parks has a maintenance strategy in place which stipulates the maintenance standards on how Parks have to be maintained and looked after however there are not enough vehicles are available due to breakdowns and there is no maintenance budget available. | Allocate budget, complete and implement. | In-house | In-house | HOD: Corporate Services | 01/01/2024 | 31/12/2024 | Communitity Facilities Maintenance Plan and Operation Plan | Communitity Facilities Maintenance Plan and Operation Plan | Per the BFP
|  | The municipality does have Communitity Facilities Maintenance Plan and Operation Plan but should be updated Parks has a maintenance strategy in place which stipulates the maintenance standards on how Parks have to be maintained and looked after however there are not enough vehicles are available due to breakdowns and there is no maintenance budget available. | Identify implementable project at critical plants to implement. Allocate budget and implement. | In-house | In-house | HOD: Corporate Services | 01/01/2024 | 31/12/2024 | List of implementable projects and budget allocation | List of implementable projects and budget allocation | Projects list requiring funding
|  | The municipality needs to upgrade sports and recreation facilities and cemeteries. The municipality needs to have cost reflective tariffs for the use of its facilities. Poor revenue collection for use of facilities. The municipality owns a Nature Reserve facility that it has not been optimized for revenue collection | The municipality must consider entering into partnerships with sporting bodies to maintain sports facilities. The Service Level Agreements must contain cost reflective tariffs to the sporting bodies. | In-house | In-house | HOD: Corporate Services | 01/01/2024 | 31/12/2024 | Service Level Agreements | Service Level Agreements
|  |  | Introduce a revenue collection mechanism including seasonal tokens for use of recreational facilities. | In-house | In-house | HOD: Corporate Services | 01/01/2024 | 31/12/2024 | Report on token sales | Report on token sales
9 | Town Planning and Human Settlement | Lack of land for development. Loss of potential revenue. Slow local economic development. Informal Settlement Sprawl | Acquire more land for forward land development planning and relocation of informal settlements located on unhabitable land. | In-house | In-house | HOD: Planning | 01/01/2024 | 31/12/2024 | List of contraventions and issued fines | List of contraventions and issued fines | Per the BFP
|  |  | Implement reviewed the process leading to approval of submissions by Council. | In-house | In-house | HOD: Planning | 01/01/2024 | 31/12/2024 | Revised process approved by Council | Revised process approved by Council
|  |  | Institute immediate legal action against all the habitual defaulters. | In-house | In-house | HOD: Planning | 01/01/2024 | 31/12/2024 | List of habitiual defaluters and trial statuses | List of habitiual defaluters and trial statuses
|  | 47 informal settlements which are home to an estimated 30 329 households, sporadic land invasion, accreditation and beneficiary management, Bulk Infrastructure for VISTA 3, challenges in the upgrading of informal settlements is the lack of bulk capacity especially for sanitation in regions of Thaba-Nchu and Botshabelo | Increase bulk infrastructure rollout to accommodate human settlements. | In-house | In-house | HOD: Planning | 01/01/2024 | 31/12/2024 | Bulk infrastructure Masterplans | Bulk infrastructure Masterplans | Projects list requiring funding
|  |  | Allocate funding for management of alternative sanitation systems. | In-house | In-house | HOD: Planning | 01/01/2024 | 31/12/2024 | Budget allocations | Budget allocations | Projects list requiring funding
|  |  | Relocation of illegal commonages. | In-house | In-house | HOD: Planning | 01/01/2024 | 31/12/2024 | Council resolution | Council resolution
|  |  | Relocation of communities (Gatvol, Khayelisha). | In-house | In-house | HOD: Planning | 01/01/2024 | 31/12/2024 | Council resolution | Council resolution
10 | Testing and Licencing | Outdated Service Level Agreement between the municipality and the Provincial Department of Safety. | Re-negotiate the licencing service level agreement with Provincial Department of Safety . | In-house | In-house | Chief of Municipal Police Services | 01/01/2024 | 31/12/2024 | SLA | SLA
11 | Fire Services | The municipality may be in violation of the Fire Services Brigade Act 99 0f 1987. The municipality has a limited number of trucks and inadequate fire fighting equipment. It is unclear if the fire hydrants are in a good working condition as there is no evidence of maintenance work done. There is poor enforcement of national fire code on buildings. Fire tariffs may not be cost reflective and may not be applied consistently. | Update and implement Fire Risk Management Plan. | In-house | In-house | HOD: Social Services | 01/01/2024 | 31/12/2024 | Fire Risk Management Plan | Fire Risk Management Plan | Per the BFP
|  |  | Develop a vehicle and equipment funding and replacement plan. | In-house | In-house | HOD: Social Services | 01/01/2024 | 31/12/2024 | Fire Risk Management Plan | Fire Risk Management Plan | Per the BFP
|  |  | Ensure safe working accommodation for fire station staff. | In-house | In-house | HOD: Social Services | 01/01/2024 | 31/12/2024 | Fire Risk Management Plan | Fire Risk Management Plan | Per the BFP
12 | Fleet | The Fleet Management Policy must be updated and the Vehicle Maintence plan detailed within the Policy | Allocate budget, complete and implement. | In-house | In-house | HOD: Waste and Fleet Management | 01/01/2024 | 31/12/2024 | Updated Fleet Management Policy | Updated Fleet Management Policy | Per the BFP
|  | MMM does not have separate Insurance and Fuel Management Policy. Vehicles are insured in line with the Asset Management Policy of the Municipality and the use of fuel is covered in the Fleet Management Policy. | Allocate budget, complete and implement. | In-house | In-house | HOD: Waste and Fleet Management | 01/01/2024 | 31/12/2024 | Vehicle Insurance Management Policy | Vehicle Insurance Management Policy | Per the BFP
|  |  | Allocate budget, complete and implement. | In-house | In-house | HOD: Waste and Fleet Management | 01/01/2024 | 31/12/2024 | Vehicle Fuel Management Policy | Vehicle Fuel Management Policy | Per the BFP
|  | Inadequate plant and equipment to manage the landfill sites. There is a refuse removal schedule, but it is frequently not adhered to due to lack of sufficient vehicles to remove waste and lack sufficient human resources (critical positions not filled). The mechanical workshop is in a good condition but under utilized due to budget constraints to procure adequate and specialized equipment and spares. Dysfunctional plant, equipment and fleet that cannot be repaired or salvaged should be disposed off. Parks has a maintenance strategy in place which stipulates the maintenance standards on how Parks have to be maintained and looked after however there are not enough vehicles are available due to breakdowns and there is no maintenance budget available. | Optimise the current fleet to provide maximum services. | In-house | In-house | HOD: Waste and Fleet Management | 01/01/2024 | 31/12/2024 | Fleet Management reporting | Fleet management system reporting
|  |  | Fleet records should be updated on time and accident committee should be established to monitor progress of all fleet damaged. | In-house | In-house | HOD: Waste and Fleet Management | 01/01/2024 | 31/12/2024 | Reporting from the fleet management system is acted timeously on | Fleet management system reporting
|  |  | Establish accident committee that will investigate all accidents and apply consequence management where necessary. | In-house | In-house | HOD: Waste and Fleet Management | 01/01/2024 | 31/12/2024 | Accident committee | Committee minutes and resolutions
|  |  | Budget for the mechancial workshop must be provided for. | In-house | In-house | HOD: Waste and Fleet Management | 01/01/2024 | 31/12/2024 | Budget documentation | Budget documentation | Per the BFP
13 | Customer Service | Up to 90% of surfaced roads are in poor condition (reported potholes, stormwater drainage and related blocked drains). Complaints from the community that the response time is too long to attending to all reported faults and blockages, addressing sewage spillages, and Reducing sewer blockages. | Allocate budget for digital channel reporting (Webpage, mobile application, Whatsapp) of service delivery issues and interuptions on Streetlights, Outages, Water leaks, Sewer Leaks, Water supply issues, Sewer spillages, potholes, blocked stormwater, etc. | In-house | In-house | HOD: Engineering Services | 01/01/2024 | 31/12/2024 | Implementation of at least one digital channel reporting platform for service delivery interuptions | Implementation of at least one digital channel reporting platform for service delivery interuptions | Per the BFP
14 | Project Management | Time taken to reticulate peri-urban areas is too long leading to community protests. The rate of rehabilitation and development of sewer reticulation networks is very slow. Lack of funding for maintenance, refurbishment and capital projects has accelerated the decline in the condition of the infrastructure resulting in failing equipment. Loadshedding is another accelerant factor. Projects for refurbish /upgrade electrical network are delayed due to insufficient budgets. | All projects must feed into the CAPEX plan and have an associated Project Implementation plan and Feasibility study. | In-house | In-house | CFO | 01/01/2024 | 31/12/2024 | Projects listed on MTREF Establishment of Local contractors database Implementation of a procument plan | MTREF Local contractor database Procurement plan | 100% Capital Expenditure
|  |  | Create a database for Local Subcontractors. | In-house | In-house | CFO | 01/01/2024 | 31/12/2024
|  |  | Implementation of procurement plan. | In-house | In-house | CFO | 01/01/2024 | 31/12/2024
|  |  | Capital projects should be included in the three-year rolling internal audit plan. | In-house | In-house | CFO | 01/01/2024 | 31/12/2024 |  |  | MTREF
15 | Technical Systems | Basic technical systems are absent or inoperable. System licencing is not maintained. Technical data is not maintained. IT system landscape is not defined and implemented. No GIS system and competent personnel in place to prepare a GRAP and mSCOA compliant asset register inhouse. Provincial Road Asset Management (RAMs) project should be accelerated, and data verified before inclusion. Investment in a system/s allowing the Municipality to pinpoint areas where losses occur. Need for a digital fault/complaint reporting system. Need for a single meter database. | Investment in a Scada system is required. | In-house | In-house | HOD: Corporate Services | 01/01/2024 | 31/12/2024 | Investment in a Scada System Implementation of Technical Systems as Required | Scada system | Per the BFP
Implement the technical system recommendation outcomes of the system landscape in a phased approach.

## SUSTAINABILITY PHASE 3
PHASE 3: SUSTAINABILITY
NO | FOCUS AREA | KEY ASSESSMENT FINDING (BASELINE) | KEY ACTIVITIES | RESOURCES REQUIRED | RESOURCES MOBILISED | RESPONSIBLE | START DATE | END DATE | KEY PERFORMANCE INDICATOR | PORTFOLIO OF EVIDENCE | BUDGET PARAMETER/ REVENUE TARGET/ SPENDING LIMIT | MUNICIPAL PROGRESS REPORT
[12 empty] | STEPS TAKEN | PROGRESS MADE | FINANCIAL IMPACT | OTHER NOTEWORTHY DEVELOPMENTS
PILLAR THREE: GOVERNANCE
To be informed by progress and achievements on Phase 1 and 2
PILLAR THREE: INSTITUTIONAL
To be informed by progress and achievements on Phase 1 and 2
PILLAR THREE: FINANCIAL MANAGEMENT
1 | Debt Restructuring | MMM has loans with DBSA, Standard Bank and Absa Bank valued at 30 June 2022 at R668 million (2020/21 R 776 million). These loans are often serviced late due to cash flow constraints. The loans in default as at 30 June 2022 totalled R382.1 million (2020/21 R 441.5 million), which is 57% of the outstanding balance. This is a further indication of the cash flow problems being experienced by MMM. During 2020, rating agency Moody’s downgraded MMM’s credit rating from B3 to Caa1. This has a negative effect on the Municipalities overall ability to obtain external funding and unfavourable interest rates. If a new rating would be done, the possibility of a further downwards adjustment is high given the current state of affairs in the Municipality. | Review the loans for a possibility to restructure, and re-negotiate payment terms. | In house | In house | CFO | 01/01/2024 | Ongoing | Loan Restructuring Revised Payment Terms Creditor Payment Negotiations | Loan Restructuring Revised Payment Terms Creditor Payment Negotiations | More Favourable Loan Repayment and Terms
Curtail unnecessary expenditure by putting controls in place.
Make arrangements with loan creditors to repay current and outstanding amounts.
Comply with the repayment arrangements by compiling a cash backed budget.
|  | Escalating ESKOM debt. | Apply for MFMA Circular No. 124 – Municipal Debt Relief through National Treasury. | In house | In house | CFO | 01/01/2025 | 12 Months | Monthly Provincial Treasury certification of Municipal compliance | Monthly Provincial Treasury certification of Municipal compliance | Municipal Eskom Debt Relief as prescribed by Circular No. 124
2 | Customer care and data accuracy | The customer care unit is dysfunctional. Critical vacancies in the Customer Care Unit are not being filled. | Fill critical vacancies and train staff in customer care techniques. | In-house | In-house | City Manager, CFO, Director Corporate Services | 01/01/2025 | Ongoing | Functioning Customer Care Unit System of Queries Resolved | Functioning Customer Care Unit System of Queries Resolved | Improved revenue collection through functioning customer care
Resuscitate the billing committee, town planning and key technical personnel to form part.
Meter readers should capture changes on the properties to update the user profile.
Commission the CRM module.
Use debt collectors when appointed to update the data for the customers.
PILLAR FOUR: SERVICE DELIVERY
1 | Technical Systems | Basic technical systems are absent or inoperable. System licencing is not maintained. Technical data is not maintained. IT system landscape is not defined and implemented. No GIS system and competent personnel in place to prepare a GRAP and mSCOA compliant asset register inhouse. Provincial Road Asset Management (RAMs) project should be accelerated, and data verified before inclusion. Investment in a system/s allowing the Municipality to pinpoint areas where losses occur. Need for a digital fault/complaint reporting system. Need for a single meter database. | Roll out scada system for Water and Electricity infrastructure. | In-house | In-house | HOD: Corporate Services | 01/01/2025 | Ongoing | Scada and Technical System Roll Out | Scada and Technical System Roll Out | Per the BFP
Implement the technical system recommendation outcomes of the system landscape in a phased approach.
2 | Electricity | There is no asset management strategy, policy or Asset Management Plans (AMPs) in place. | Allocate budget, complete and implement the Asset Management Plan. | In-house | In-house | CEO CENTLEC | 01/01/2025 | Ongoing | Asset Management Plan for Electrciity | Asset Management Plan for Electrciity | Per the BFP
|  | Loss Reduction strategies need to be documented and must be measurable outcomes | Refine the loss reduction strategies based on outcomes. | In-house | In-house | CEO CENTLEC | 01/01/2025 | Ongoing | Revised Loss Reduction Strategy document | Revised Loss Reduction Strategy document | Reduce losses
|  | Loss Reduction strategies need to be documented and must be measurable outcomes | Deploy refined loss reduction strategies. | In-house | In-house | CEO CENTLEC | 01/01/2025 | Ongoing | Reporting on the outcomes of Loss Reduction Strategies | Reporting on the outcomes of Loss Reduction Strategies | Reduce losses
|  | Need for meter audits and 'SMART' technologies due to inaccurate meter database and poor revenue collected. Faulty meters, inaccurate billing and old meters leads to incorrect billing information and estimated billing which in turn results in inaccurate billing and inflated debt. Theft, illegal connections and Meter tampering result in Electricity losses of 10.92% (Technical and non-technical losses). Malfunctioning of bulk meters due to aging and tampering. Enhance revenue by installing Bulk meters and Zonal meters to curb revenue losses & to detect tampers remotely. Government debt is about R800m due to Government departments are not honouring their debt in full. Currently 4620 meters are not allocated to the financial system and information on installed meters do not always reach the finance office. | Maintain meter replacement priortised by largest loss impact on a yearly basis. | In-house | In-house | CEO CENTLEC | 01/01/2025 | Ongoing | Prioritised list of targeted areas to be updated bi-annually | Prioritised list of targeted areas to be updated bi-annually | Improve revenue
|  |  | Maintain budget for smart meter replacements. | In-house | In-house | CEO CENTLEC | 01/01/2025 | Ongoing | Secure budgets for Meter replacements | Secure budgets for Meter replacements | IDP and MTREF processes
|  |  | Enforce by-laws and disconnect illegal connections. | In-house | In-house | CEO CENTLEC | 01/01/2025 | Ongoing | Removal of illegal connections | Removal of illegal connections | Reduce losses
|  |  | Determine pattern of household usage and flag for any irregularities. | In-house | In-house | CEO CENTLEC | 01/01/2025 | Ongoing | Established revenue loss recognition strategies | Established revenue loss recognition strategies | Reduce losses
3 | Water | The municipality does not have a Water Conservation and Water Demand Management Plan (WCWDMP) Water losses attributed to meter tampering and illegal connections due to customers not prioritising the payment of services. Water losses are reported at 46% largely due to lack of proper network maintenance. | Implement remaining activites as required by the plan. | In-house | In-house | HOD: Engineering Services | 01/01/2025 | Ongoing | Report on remaining activities implemented from the Water Conservation and Water Demand Management Plan (WCWDMP) | Report on remaining activities implemented from the Water Conservation and Water Demand Management Plan (WCWDMP) | Revised projects list requiring funding
|  | The municipality does not have a Water Services Development Plan (WSDP) | Implement key activites as required by the plan. | In-house | In-house | HOD: Engineering Services | 01/01/2025 | Ongoing | Report on the implement of remaining activites from the Water Services Development Plan (WSDP) | Report on the implement of remaining activites from the Water Services Development Plan (WSDP)
|  | There is no asset management strategy, policy or Asset Management Plans (AMPs) in place. | Allocate budget, complete and implement the Asset Management Plan. | In-house | In-house | HOD: Engineering Services | 01/01/2025 | Ongoing | Asset Management Plan for Water | Asset Management Plan for Water | Per the BFP
|  | Need for meter audits and 'SMART' technologies due to inaccurate meter database and poor revenue collected. Faulty meters, inaccurate billing and old meters leads to incorrect billing information and estimated billing which in turn results in inaccurate billing and inflated debt. Theft, illegal connections and Meter tampering result in Electricity losses of 10.92% (Technical and non-technical losses). Malfunctioning of bulk meters due to aging and tampering. Enhance revenue by installing Bulk meters and Zonal meters to curb revenue losses & to detect tampers remotely. Government debt is about R800m due to Government departments are not honouring their debt in full. Currently 4620 meters are not allocated to the financial system and information on installed meters do not always reach the finance office. | Maintain meter replacement priortised by largest loss impact on a yearly basis. | In-house | In-house | HOD: Engineering Services | 01/01/2025 | Ongoing | Prioritised list of targeted areas to be updated bi-annually | Prioritised list of targeted areas to be updated bi-annually | Improve revenue
|  |  | Maintain budget for smart meter replacements. | In-house | In-house | HOD: Engineering Services | 01/01/2025 | Ongoing | Secure budgets for Meter replacements | Secure budgets for Meter replacements | IDP and MTREF processes
|  |  | Enforce by-laws and disconnect illegal connections. | In-house | In-house | HOD: Engineering Services | 01/01/2025 | Ongoing | Removal of illegal connections | Removal of illegal connections | Reduce losses
|  |  | Determine pattern of household usage and flag for any irregularities. | In-house | In-house | HOD: Engineering Services | 01/01/2025 | Ongoing | Established revenue loss recognition strategies | Established revenue loss recognition strategies | Reduce losses
4 | Sanitation | There is no asset management strategy, policy or Asset Management Plans (AMPs) in place. | Allocate budget, complete and implement the Asset Management Plan. | In-house | In-house | HOD: Engineering Services | 01/01/2025 | Ongoing | Asset Management Plan for Sanitation | Asset Management Plan for Sanitation | Per the BFP
5 | Roads and Stormwater | There is no asset management strategy, policy or Asset Management Plans (AMPs) in place. | Allocate budget, complete and implement Asset Management Plan. | In-house | In-house | HOD: Engineering Services | 01/01/2025 | Ongoing | Asset Management Plan for Roads and Stormwater | Asset Management Plan for Roads and Stormwater | Per the BFP
6 | Solid Waste | There is no asset management strategy, policy or Asset Management Plans (AMPs) in place. | Allocate budget, complete and implement the Asset Management Plan. | In-house | In-house | HOD: Waste and Fleet Management | 01/01/2025 | Ongoing | Asset Management Plan for Solid Waste | Asset Management Plan for Solid Waste | Per the BFP
7 | Community Facilities | There is no asset management strategy, policy or Asset Management Plans (AMPs) in place. | Allocate budget, complete and implement the Asset Management Plan. | In-house | In-house | HOD: Corporate Services | 01/01/2025 | Ongoing | Asset Management Plan for Community Facilities | Asset Management Plan for Community Facilities | Per the BFP
8 | Town Planning and Human Settlement | Lack of land for development. Loss of potential revenue. Slow local economic development. Informal Settlement Sprawl | Institute immediate legal action against all the habitual defaulters. | In-house | In-house | HOD: Planning | 01/01/2025 | Ongoing | List of habitiual defaluters and trial statuses | List of habitiual defaluters and trial statuses
9 | Customer Service | Up to 90% of surfaced roads are in poor condition (reported potholes, stormwater drainage and related blocked drains). Complaints from the community that the response time is too long to attending to all reported faults and blockages, addressing sewage spillages, and Reducing sewer blockages. | Allocate budget for digital channel reporting (Webpage, mobile application, Whatsapp) of service delivery issues and interuptions on Streetlights, Outages, Water leaks, Sewer Leaks, Water supply issues, Sewer spillages, potholes, blocked stormwater, etc. | In-house | In-house | HOD: Corporate Services | 01/01/2025 | Ongoing | Implementation of at least three (in total) digital channel reporting platforms for service delivery interuptions | Implementation of at least three (in total) digital channel reporting platforms for service delivery interuptions | IDP and MTREF processes
10 | Project Management | Time taken to reticulate peri-urban areas is too long leading to community protests. | All projects must feed into the CAPEX plan and have an associated Project Implementation plan and Feasibility study. | In-house | In-house | CFO | 01/01/2025 | Ongoing | Project Implementation plan Project feasibility study Project priortised as per matrix Projects listed on MTRF | Project Implementation plan Project feasibility study Project priortised as per matrix Projects listed on MTRF | 100% Capital Expenditure
|  | The rate of rehabilitation and development of sewer reticulation networks is very slow. |  | In-house | In-house | CFO | 01/01/2025 | Ongoing
|  | Lack of funding for maintenance, refurbishment and capital projects has accelerated the decline in the condition of the infrastructure resulting in failing equipment. Loadshedding is another accelerant factor. |  | In-house | In-house | CFO | 01/01/2025 | Ongoing
|  | Projects for refurbish /upgrade electrical network are delayed due to insufficient budgets. |  | In-house | In-house | CFO | 01/01/2025 | Ongoing