## 2026-27 Annual PP
2026/27 ANNUAL PROCUREMENT PLAN - TRANSVERSAL CONTRACTS
Name of Department: National Tresury
Division: Office of the Chief Procurement Officer
Date: May 2026
No | Contract Classification (Curently running / New Contract? | Contract Reference Number | Project Manager | Project Description | Contract Duration in Months | Estimated Value (incl. taxes) | Method of procurement | Bid Specification Date | Bid Advert Date | Bid Closing Date | Bid Evaluation Date | Bid award Date | Contract Commence Date | Contract Expiry Date
1 | Running | RT8 | Mulatedzi Raudzingana | Transportation of cargo | 60 | TBC | Open Tender | 18 Spetember 2025 | 2026-05-29 | 2026-07-03 | 2026-08-02 | 2026-09-24 | TBC | 2031-03-31
2 | Running | RT11 | Supply and Delivery of Animal Feed to the State Period of 1 June 2027 to 31 May 2030 | Animal Feed | 60 | TBC | Open Tender | 2025-06-19 | 2026-08-03 | 2026-09-11 | 2026-11-30 | 2027-02-25 | 2027-06-01 | 2031-02-28
3 | New | RT18 | Ante and Post-Mortem blood alcohol kits | Ante and Post-Mortem blood alcohol kits | 36 | 7269751 | Open Tender | 2025-08-02 | 2026-08-21 | 2026-09-21 | 2026-10-01 | 2026-11-25 | 2026-12-15 | 2029-02-28
4 | Running | RT21 | Radiographic material | Radiographic material | 36 | 126112589 | Open Tender | 2025-09-02 | 2026-02-25 | 2026-03-26 | 2026-05-01 | 2026-06-25 | 2026-07-17 | 2029-03-31
5 | Running | RT24 | Hospital Furniture and Ward Requirements | Hospital Furniture and Ward Requirements | 60 | 880875649 | Open Tender | 2025-10-17 | 2026-04-22 | 2026-05-22 | 2026-08-01 | 2026-09-24 | 2026-10-01 | 2029-03-31
6 | Running | RT29-1 |  | Smart metering solution | 36 | 2000000000 | Open Tender |  | 2026-09-24 | 2026-10-30 | 2026-10-23 | 2027-03-25 | 2027-05-01
7 | New | RT30 |  | Funding Smart metering solution | 36 | TBC | Open Tender |  | 2026-09-24 | 2026-10-30 | 2026-10-23 | 2027-03-25 | 2027-05-01
8 | Running | RT35 | Voluntary medical male circumcision (MMC) | Voluntary medical male circumcision (MMC) | 60 | 319325765 | Open Tender | 2025-10-02 | 2026-04-24 | 2026-05-22 | 2026-06-01 | 2026-07-23 | 2026-08-10 | 2031-03-31
9 | Running | RT44 | Mulatedzi Raudzingana | B-BBEE Verification | 60 | TBC | Open Tender | 2025-06-14 | 2025-06-29 | 2025-08-03 | 2025-09-02 | 2025-09-29 | TBC
10 | Running | RT52 | Provision of full Maintenance Lease,Medium Term Vehicle Rentals and Chaffuer Drive Services for the Period 1 August 2026 to 30 September 2031 | Provision of full Maintenance Lease,Medium Term Vehicle Rentals and Chaffuer Drive Services | 60 | TBC | Open Tender |  | 2026-04-01 | 2026-05-04 | To be updated | To be updated | To be updated | 2026-01-31
11 | New | RT57 | RT57-2022: Supply and Delivery of Sedan, Light and Heavy Commercial Vehicles, Busses, Motor Cycles, Agricultural Tractors, Construction Plant and Equipment to the State Period From 1 October 2026 to 30 September 2029 | Sedan, Light and Heavy Commercial Vehicles, Busses, Motor Cycles, Agricultural Tractors, Construction Plant and Equipment | 36 | TBC | Open Tender | 2025-06-14 | 2026-04-14 | 2026-05-22 | 2026-07-30 | 2026-08-27 | 2026-10-01
12 | Running | RT64 | Supply and Delivery of Clothing the State Period 1 August 2026 to 31 July 2029 | Supply and Delivery of Clothing | 60 | TBC | Open Tender | 17 Spetember 2025 | 2025-09-29 | 2025-11-07 | 2026-05-29 | 2026-06-25 | 2026-08-01 | 2029-03-31
13 | Running | RT68 | Supply and Delivery of Clothing the State Period 1 August 2026 to 31 July 2029 | Provision of Finance and Administration of Subsidised Vehicles | 60 | TBC | Open Tender |  | 2026-04-13 | 2026-05-11 | 2026-05-29 | 2026-06-01 | 2026-07-01
14 | Running | RT69 | Zanele Mkhwanazi | Tyres and tubes | 36 | TBC | Open Tender | 2026-05-01 | 2025-11-01 | 2025-12-06 | 2026-01-05 | 2026-04-20 | TBC
15 | Running | RT70 | Manthepeng Tshinavha | Petrol and diesel | 36 | TBC | Open Tender | 2025-01-17 | 2025-12-05 | 2026-01-09 | 2026-02-08 | 2026-05-01 | TBC | 2030-07-31
16 | New | RT74 | Zanele Mkhwanazi | Prefabricated steel shelving | 60 | TBC | Open Tender | 2025-04-18 | 2025-04-26 | 2025-05-31 | 2025-06-30 | 2026-09-17 | TBC
17 | Running | RT75-1 |  | Male and female condoms and lubricant | 60 | 381063657 | Open Tender |  | 2026-03-06 | 2026-04-07 | 2026-05-19 | 2026-06-25 | 2026-07-24
18 | Running | RT76 | Medical examination and surgical gloves | Medical examination and surgical gloves | 60 | 350818918 | Open Tender | 2025-09-02 | 2026-02-27 | 2026-04-22 | 2026-06-01 | 2026-07-23 | 2026-08-10 | 2031-03-31
19 | Running | RT80 | Zanele Mkhwanazi | Cell locks, cell keys, cell doors, cell windows, cell steel bars, and accessories | 60 | TBC | Open Tender | 2025-01-29 | 2025-02-05 | 2025-03-12 | 2025-04-11 | 2027-04-26 | TBC
20 | Running | RT81 |  | Building Material | 60 | TBC | Open Tender |  | 1900-01-06 | 1900-02-10 | 1900-03-12 | 2027-02-23 | TBC
21 | New | RT83 | Mulatedzi Raudzingana | Supply and Delivery of Bulk Fuel Tanks to the State | 60 | TBC | Open Tender | 19 Spetember 2025 | 2026-02-27 | 2026-04-03 | 2026-05-03 | 2026-06-25 | 2026-08-01 | 2029-03-31
22 | Running | RT284 | Mulatedzi Raudzingana | Hypodermic syringes | 60 | TBC | Open Tender | 20 Spetember 2025 | 2025-11-01 | 2025-12-06 | 2026-01-05 | 2026-05-01 | TBC | 2031-03-31
23 | Running | RT296 |  | Dental consumables | 60 | TBC | Open Tender |  | 2026-10-20 | 2026-11-24 | 2026-12-24 | 2027-03-25 | TBC
Formulas:
Bid Closing Date = [Bid Advert Date]+35
Bid Evaluation Date = [Bid Closing Date]+30
Bid Advert Date = [Bid Specification Date]+15
Bid award Date = [Bid Evaluation Date]+27

## 2025-26 Annual PP (hidden)
2025/26 ANNUAL PROCUREMENT PLAN - TRANSVERSAL CONTRACTS
Name of Department: National Tresury
Division: Office of the Chief Procurement Officer
Date: 14 April 2025
No | Contract Classification (Curently running / New Contract? | Contract Reference Number | Project Manager | Project Description | Contract Duration in Months | Estimated Value (incl. taxes) | Method of procurement | Bid Specification Date | Bid Advert Date | Bid Closing Date | Bid Evaluation Date | Bid award Date | Contract Commence Date | Contract Expiry Date
1 | Running | RT12 | Mulatedzi Raudzingana | Agricultural remedies | 36 | 849655 | Open Tender | 2025-08-02 | 2025-10-01 | 2025-10-31 | 2025-11-30 | 2026-01-29 | 2026-03-01 | 2029-02-28
2 | Running | RT14 | Mulatedzi Raudzingana | Toilet paper and paper towels | 36 | 227521827 | Open Tender | 2025-09-02 | 2025-11-01 | 2025-12-01 | 2025-12-31 | 2026-03-01 | 2026-04-01 | 2029-03-31
3 | Running | RT21 | Manthepeng Tshinavha | Radiographic material | 36 | 81831589 | Open Tender | 2025-10-17 | 2025-12-16 | 2026-01-15 | 2026-01-30 | 2026-03-31 | 2026-04-01 | 2029-03-31
4 | Running | RT24 | Manthepeng Tshinavha | Hospital Furniture and Ward Requirements | 60 | 880875649 | Open Tender | 2025-10-02 | 2025-12-01 | 2025-12-31 | 2026-01-30 | 2026-03-31 | 2026-04-01 | 2031-03-31
5 | Running | RT46 | Mulatedzi Raudzingana | Fleet vehicle maintenance (Pool) | 60 | 8500000000 | Open Tender | 2025-09-02 | 2025-11-01 | 2025-12-01 | 2025-12-31 | 2026-03-01 | 2026-04-01 | 2031-03-31
6 | New | RT52 | Mulatedzi Raudzingana | Vehicle Full maintenance lease | TBC | TBC | Open Tender | 2025-06-14 | 2025-08-13 | 2025-09-12 | 2025-10-12 | 2025-12-11 | TBC
7 | Running | RT57 |  | Vehicles | 48 | 12551829751 | Open Tender |  | 2026-05-31 | 2026-05-01 | 2026-04-16 | 2026-03-17 | 2026-03-17 | 2026-01-31
8 | Running | RT58 | Mulatedzi Raudzingana | Insurance for subsidised vehicles | 60 | 1763326736.09 | Open Tender | 2025-06-19 | 2025-08-18 | 2025-09-17 | 2025-10-02 | 2026-12-01 | 2026-03-01 | 2031-02-28
9 | Running | RT59 | Mulatedzi Raudzingana | Footwear | 36 | 477436918 | Open Tender | 17 Spetember 2025 | 2025-11-16 | 2025-12-16 | 2025-12-31 | 2026-03-01 | 2026-04-01 | 2029-03-31
10 | Running | RT62 | Mulatedzi Raudzingana | Subsidised vehicle fleet | 60 | 179000000 | Open Tender | 18 Spetember 2025 | 2025-11-16 | 2025-12-16 | 2025-12-31 | 2026-03-01 | 2026-04-01 | 2031-03-31
11 | Running | RT64 | Mulatedzi Raudzingana | Clothing | 36 | 1857126192 | Open Tender | 19 Spetember 2025 | 2025-11-16 | 2025-12-16 | 2025-12-31 | 2026-03-01 | 2026-04-01 | 2029-03-31
12 | New | RT66 | Zanele Mkhwanazi | Tactical and crime scene equipment | TBC | TBC | Open Tender | 2025-04-18 | 2025-06-17 | 2025-07-17 | 2025-08-01 | 2025-09-30 | 2025-07-01
13 | Running | RT68 | Mulatedzi Raudzingana | Financing of subsidised vehicles | 60 | 200000000 | Open Tender | 20 Spetember 2025 | 2025-11-16 | 2025-12-16 | 2025-12-31 | 2026-03-01 | 2026-04-01 | 2031-03-31
14 | Running | RT70 | Zanele Mkhwanazi | Petrol and diesel | 60 | 6300000000 | Open Tender | 2026-05-01 | 2026-04-01 | 2026-03-17 | 2026-02-15 | 2026-01-31 | 2026-05-01
15 | Running | RT75 | Manthepeng Tshinavha | Male and Female Condoms and lubrication | 60 | 381063657 | Open Tender | 2025-01-17 | 2025-03-18 | 2025-04-17 | 2025-05-02 | 2025-07-01 | 2025-08-01 | 2030-07-31
16 | New | RT83 | Zanele Mkhwanazi | Bulk Fuel Tanks | TBC | TBC | Open Tender | 2025-01-29 | 2025-08-28 | 2025-09-27 | 2025-10-12 | 2025-12-11 | TBC
17 | New | RT52 | Mulatedzi Raudzingana | Vehicle Full maintenance lease | TBC | TBC | Open Tender | 2025-06-14 | 2025-08-13 | 2025-09-12 | 2025-10-12 | 2025-12-11 | TBC