## Instructions
Evaluation
1 | Set up meetings with as wide a range of involved stakeholders as possible
2 | Conduct interviews / discussions and site/project visits to develop a picture of the project
3 | Keep the relevant indicators in mind to ensure that you get as complete an information set as possible
4 | Remember to ask for as much supporting documentation as possible
5 | Once you have left the site/project, review your notes and any documents provided
6 | Rate each element according to the rating scale
7 | Capture ratings (whole numbers only) in the blue blocks provided
8 | The rating for each component and for the overall Project will be calculated automatically

## Sheet1 (hidden)
1.1.1 Clarity of governance and administration
Strong executive leadership is located within a recognised, functional organisational structure. Decision-making processes are transparent and as consultative as practical. Accountability is assured through regular communication and interrogation of progress.
1.1.2 Dedicated funding
The programme fund is available up front. This is then kept ring-fenced for the chosen projects; funds are not re-directed once allocated
1.1.3 Area focus
Projects focus on geographic areas with high priority needs and symbolic importance to the country
1.1.4 High impact, visible delivery
Emphasis within projects is placed on rapid delivery. Given the dire need for habitable housing and neighbourhoods, projects must make a strong positive impression on the community, and contribute to the visibility of the municipality’s delivery
1.1.5 Innovative transformation
Innovative solutions to continued adverse urban environments are encouraged. These should be linked to the transformation of government systems to increase the possibility of replication
1.1.6 External resource mobilisation
The programme operates on the basis that it is not the sole provider of funding for a project. This requires that there be counter-funding from other government departments and /or securing external funding sources
1.1.7 Sustainability
The urban services and amenities delivered through this programme must be sustainable in every sense: the longevity of the institutional /organisational arrangements, physical structures and maintenance commitments should all exceed that of the project itself

## Evaluation
Assessment
Department:
Name of Conditional Grant:
Date of Assessment:
Conducted By:
| Overall Assessment |  | #DIV/0!
RATING SCALE
0 | Not applicable, or sufficient information is not available to assess element | 0
1 | Needs urgent attention and improvement | 1
2 | Needs major improvement | 2
3 | Needs improvement | 3
4 | Needs improvement in limited aspects | 4
5 | Acceptable, room for some improvement | 5
6 | Acceptable, needs maintaining | 6
A | Governance (concerned with accountability and responsibilities) |  |  | #DIV/0!
AA | Organizational Structure and Culture |  | #DIV/0!
1 | Does the Conditional Grant funded programme have an organizational structure with clear lines of authority and responsibility
2 | Is there a defined national steering committee – oversight body for the programme
3 | Are there defined provincial steering committees
4 | Does each steering committee have defined point of reporting into the departmental structures
5 | Are there mechanisms in place for obtaining appropriate inputs from stakeholders
6 | Are job descriptions are clearly defined and reflected in performance agreements
7 | There is a defined reporting route and frequency between provincal and national departments
AB | Administrative Procedures |  | #DIV/0!
1 | Administrative procedures for the programme are linked to the department’s procedures
2 | The programme has an updated porgramme definintion document setting out programme authoprities, objectiuves , delivery mechnsims, budgeting and reporting procedures
3 | Administrative procedures are followed and adhered to
4 | Systems are in place to minimise the department’s abuse of resources
AC | Financial Management |  | #DIV/0!
1 | Financial procedures for the programme are in place
2 | Suitable qualified staff prepare, manage and implement the annual budget
3 | Budget is controlled on an on-going basis
4 | The budget is aligned with programme objectives, performne indicators and delivery targets per annual grant business plan
AD | Reporting |  | #DIV/0!
1 | The programme has ability to produce appropriate financial reports
2 | The programme has ability to produce appropriate activity reports
3 | The programme regularly publishes information on its operations
4 | Programme reports sre used on a regular and specified basis to monitor and evaluate progress against financial and non-fincial target per the annual business plan
B | Programme Team (Size, Structure & Skills) |  |  | #DIV/0!
BA | Size |  | #DIV/0!
1 | There is a dedicated National Programme manager
2 | There is a dedicated Provincial manager / coordinator
3 | The National Program team structure is defined
4 | The National Program team is fully staffed
5 | The Provincial Program team structures are defined
6 | The Provincial Programme teams are fully staffed
7 | The Local Program team structures are defined
8 | The Local Programme teams are fully staffed
Do the team members have the following specific skills?
BB | Project design skills |  | #DIV/0!
1 | Ability to define strategies / activities required to meet project objectives
2 | Ability to conceptualise alternatives that could be considered in meeting project outcomes
BC | Project Planning Skills |  | #DIV/0!
1 | Estimating resources needed for the project activities
2 | Scheduling of activities with consideration of precedence and interdependencies
3 | Multi - poject budget and cash flow
4 | Development of budgets and cash flows from the activity schedule
BD | Monitoring and reporting |  | #DIV/0!
1 | Developing reporting and monitoring systems and setting into operation
2 | Gathering and analysis of reported data
3 | Generation of consolidated reports
BE | Procurement |  | #DIV/0!
1 | Understanding of and experience with supply chain management (procurement) processes
2 | Management and monitoring compliance of all types of contracts
2 | Development of statements of work / terms of reference / specifications defining the work to be done and deliverables / products to be developed in the project
BF | Intergovernmental & Communication issues |  | #DIV/0!
1 | Managing implementation of programs across multiple levels of government
2 | Development of communication strategies
3 | Implementation of communications according to strategies
BG | Other skills & competencies needed for program management & Implementation |  | #DIV/0!
1 | Team work
2 | Communication skills
3 | Motivational skills
4 | Negotiation skills
5 | Report writing
6 | Word processing
7 | Spreadsheet development
8 | Management of consultants
9 | Interpretation of reports (financial, evaluation and monitoring)
C | Links to departmental mainstream activities |  |  | #DIV/0!
CA | Are the following links developed with capacity on the project side (to define what is required for the project to meet its purpose) and on the departmental side (to provide support needed by the Conditional Grant project/s) |  | #DIV/0!
1 | Policy section - for alignment with departmental policy
2 | HR – for the identification, secondment, recruiting of project staff
3 | Procurement - for support to procurement actions
4 | Finance - for support in aligning / integrating budgets with the MTEF
5 | Finance – for transfers of funds to provinces and districts
6 | Finance – for payment of service providers and suppliers
7 | Legal – for support in concluding contracts
CB | Specialist skills – based on the application environment |  | #DIV/0!
1 | Infrastructure
2 | Information Technology
3 | Social services
4 | Health
CC | Risk Management |  | #DIV/0!
1 | Ability to identify program risks
2 | Ability to develop risk abatement strategies
3 | Implementation of risk management and risk abatement actions